This document contains both ‘Part 1: Event Information’ AND ‘Part 2: Risk Assessment’. Both parts are required to be completed by the organising group.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Information |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact for The Event: Alfred Chung | Email Address for Main Contact: Ac24g22@soton.ac.uk | Club or Society Name: K-Pop Society | Contact Number: +44 7479 476624 |
| 1B) Event Information: |  |  |  |
| Event Name: K-Pop Society’s Inter-Uni Event | Event Date: 28TH February 2026 | Event Venue/s: Team Southampton Hall (Located in SUSU) | Total Attendees: ~300 |
| Event Timings: | Set Up: 11:00 Event Start: 11:30 Event End: 4:00 Pack Down: 4:00-4:30 |  |  |
| Event Breakdown This includes everything happening at your event, including fundraising, food provision, any performance or sporting activity, etc. | 11:00-11:30 – Committee Arrive at venue, clear any equipment left out, Doors Open 11:30-11:45 – Introduction to Event, Attendees Briefing (Fire Exits, Evacuation Procedures, Facilities) 11:45-12:50 – Dance Performances + Random Play Dance 12:50-1:20 – Lunch Break 1:20-2:30 – Dance Performances + Random Play Dance 2:30 – 2:45 – Break 2:45 – 4:00 – Dance Performances + Random Play Dance 4:00 – 4:30 – Outro, Guests Leave, Committee Clear Space |  |  |
| Overview of event concept Description of the activities taking place. This includes everything happening at your event e.g. fundraising, food provision and any performance or sporting activity) | K-Pop Society will be hosting an Inter-University Event where students from the University of Southampton and invited members of other university K-Pop societies will gather to watch and perform for one another. The event will feature a variety of performances throughout the day, including dance covers, vocal performances, and music segments, with each participating university allocated a designated performance slot. In addition to scheduled performances, there will be random play dance sessions, where songs will be played at random and the floor will be open to any attendee who wishes to participate. No sports equipment will be used during the event. The Society will not provide any catered food or alcoholic drinks. Attendees will be expected to bring their own food and beverages. Information will be provided regarding accessible water stations on campus, as well as nearby shops and food outlets should attendees wish to purchase refreshments. The event is intended to create a collaborative and welcoming environment for K-Pop societies to connect, showcase their talents, and engage in shared appreciation of K-Pop culture. The whole event will be located in one location throughout the day: Team Southampton Sports Hall in SUSU. The K-Pop Society takes responsibility for booking the facilities and the general running of the event in terms of promotion and setup. In addition, we take responsibility of all attendees (University of Southampton Students and Non-University of Southampton Students); all attendees will all be made aware of fire exits, evacuation procedures, and facilities they can use. SUSU is responsible for providing the booked facilities (The Team Southampton Hall). |  |  |
| Volunteers hosting the event List all committee and volunteers that will be present and responsible for the event, as well as their role. | Event lead/Host: Alfred Chung Doors: Evelyn Olusanya Volunteers for set up: Lydia Ma, Emma Ho, Alfred Chung |  |  |
| Food provision For full guidance on this click here. | Food will be individually provided by the attendees; the society will not provide any food or have catering. Attendees will be asked to bring their own lunch with them or directed to nearby shops to buy food for the day. |  |  |
| Security & First Aid Requirements Is external first aid or security being hired? Who are the qualified first aiders in the group should a medical emergency occur? | First Aid Trained Member: Ola Oludipe (Welfare Officer) |  |  |
| Provisional Budget If you would like a more extensive budget tracker, click here. | Projected Ticket Income: £600 (based on 80% of tickets being sold) Ticket Price: £2.50 Members £3.50 Non-Members Venue Hire (Total Cost): £500.50 Profit if 80% Tickets sold: £99.50 To break even we need to sell 66% of tickets |  |  |
| 1C) Only required if an external company/external speaker will be on site for the event - If you are inviting an external speaker to campus for your event, you are required to submit this form to legalservices@soton.ac.uk at least 15 working days before the event. For more guidance on this please click here. |  |  |  |
| Business Name: | Business Contact Name: | Email Address: | Contact Number: |
| Arrival On Site: Departure time: | Company’s Risk Assessment Link: | Company’s Insurance Link: | Company’s Public Liability Information Link: |

Part 2A

Risk Assessment

| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |  |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Slips, trips and falls | Physical injury | Event organisers and attendees | 2 | 3 | 6 | All boxes and equipment to be stored away from main meeting area, e.g. stored under tables. Floors to be kept clear and dry, and visual checks to be maintained throughout the meeting by organisers. Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. Report any trip hazards to facilities teams/venue staff asap. If cannot be removed, mark off with hazard signs. | 1 | 4 | 4 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible, ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. No Food will be brought into the sports hall |
| Manual handling, including setting up of equipment. E.g. table and chairs | Bruising or broken bones from tripping over table and chairs. | Meeting organisers and attendees | 2 | 3 | 6 | Follow manual handling guidelines. Ensure that at least 2 people carry tables or other bulky items. Setting up tables will be done by organisers. Work in teams when handling other large and bulky items. Request tools to support with the moving of heavy objects from SUSU Facilities/venue. E.g. hand truck, dolly, skates. Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable. | 1 | 3 | 3 | Seek assistance from facilities staff/venue staff if needed. Seek medical attention from SUSU/venue Reception if in need. Contact emergency services if needed. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Overcrowding / Inadequate Meeting Space | Physical injury, distress, exclusion | Event organisers and attendees | 2 | 3 | 6 | Do not push/shove. If large crowds form, request barriers from SUSU facilities team or external venue to assist with crowd management. Committee checks on space, lighting, access, tech available, etc. Use ticketing system (SUSU Box Office) event to avoid exceeding venue capacity (300) Ensure space meets needs of members e.g. considering location & accessibility of space (use AcessAble database to check accessibility information of venues). Committee to consult members on needs and make reasonable adjustments where possible | 1 | 3 | 3 | Seek medical attention if problem arises. Liaise with SUSU reception/Activities Team and Southampton sport available spaces for meetings. Postpone meetings where space cannot be found. Welfare Officer to complete WIDE training. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents causing reputational damage to the group, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name into disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring all members are reminded that they are representing the club/society, SUSU and the University, often in branded clothing. Members are reminded that they need to adhere to SUSU’s Code of Conduct. | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Report any incidents to the Activities Team. |
| Costumes/Fancy Dress | Props/costumes causing injury or offence | Participants Members of the public | 2 | 1 | 2 | Ask members to only bring small items and use sensibly. Members of the society are responsible for their own possessions and the use of them. Choose a theme unlikely to cause offence. Any participant wearing items deemed offensive asked to remove these. Society to follow and share with members Code of Conduct/SUSU Expect Respect policy. | 1 | 1 | 1 | SUSU Expect Respect policy to be followed. Committee WIDE training. Ensure that any incidents involving public or others are recorded and addressed. Report any incidents to the Activities Team. |
| Travel by car, train, bus, plane when leaving the local area. | Vehicle collision – causing anything from minor to severe injuries, as well as mental health issues. | Members, those driving, members of the public | 2 | 5 | 10 | Group committee to check that drivers have the relevant licences and insurance for the mode of travel. This includes if they have completed a SUSU minibus test. Members expected to drive or travel in a sensible manner, with those doing otherwise to face disciplinary action (from the club/society in the first instance). Can cause reputational issues, especially if driving SUSU branded vehicles. Importance of this to be reminded. | 1 | 5 | 5 | Contact emergency services as required 111/999. Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Medical emergency | Members may sustain injury /become unwell Pre-existing medical conditions, sickness, distress | Members | 1 | 5 | 5 | Advise participants to bring their personal medication if it might be required. Members/Committee to carry out first aid if necessary and only if qualified and confident to do so. Contact emergency services as required 111/999. Contact SUSU Reception/venue staff for first aid support. Members can be referred to The Student Hub (02380 599 599, studenthub@soton.ac.uk) in case of distress. | 1 | 4 | 4 | Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Fire | Smoke inhalation, burns. Risk of extreme harm. | All participants and organisers, any staff and spectators | 1 | 5 | 5 | Those leading the session must ensure they are aware of and fully understand the venue or location’s fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the participants the nearest emergency exit routes at the start of a session, and the importance of leaving calmly in case of an emergency. Avoid build-up of debris in the activity area. Consider accessibility requirements. | 1 | 4 | 4 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Anti-social, violent, or offensive behaviour | Disturbance to the neighbourhood, reputational damage, injury and distress as a result of violence | Event organisers, event attendees, public | 2 | 5 | 10 | Bouncers/security will be present at most licensed venues. Bar/venue security staff will need to be alerted and emergency services called as required. Do not personally engage with any violent behaviour. Stay safe and inform the bar staff/police if necessary. Society to follow and share with members Code of conduct/SUSU Expect Respect policy. | 1 | 3 | 5 | If the situation becomes very serious and results in the participant being arrested then it will be made clear that they cannot be accompanied to the police station. Follow SUSU incident report policy. Call emergency services as required. |
| Legal Compliance: Club or society activity going against set law. This includes breaches of the freedom of speech act | Fines imposed upon the student group as well as SUSU. Jail sentences. Reputational risk to the student group, SUSU and the wider University | The club or society, committee and members, SUSU or the Wider University. | 1 | 1 | 1 | All clubs and societies should ensure they are following set law at all times. If ever in doubt, they will contact the Activities team prior to the activity taking place. All who wish to bring in an external speaker must follow due process, available here This will be looked over by the University Legal Services team, and may require security being consulted and an extra risk assessment being submitted. | 1 | 1 | 1 |  |
| Financial risk | Group debt | Group members, SUSU | 4 | 3 | 12 | Financial Summary Total Cost: £500.50 Average Ticket Price: £3 Projected Ticket Income (80% sold): £600 Profit if 80% Tickets sold: £99.50 To break even we need to sell 66% of tickets | 2 | 3 | 6 | Contact SUSU Activities Team if you have any questions or concerns about this. |
| Dance and Random Play Dances |  |  |  |  |  |  |  |  |  |  |
| Events involving dance or performances | Participants who do not have the appropriate skill level may accidentally injure themselves during the activity | Participants | 2 | 3 | 6 | - Ensure all participants are aware of the space requirements and the required equipment in advance of the session - Remind participants of the required space and equipment at the start of the session - Remind participants of the required skill level at the start of the session | 1 | 3 | 3 | − Advise participants to sit out the session if their space and/or equipment makes the activity unsafe for them Notify the Activities Team at SUSU of any injuries resulting from any club/society activity |
| Fallin g while participating in activity | Injuries and Bruising | Participants | 3 | 1 | 3 | • Ensure all performances are well rehearsed. • When putting tricks into routines make sure the students are fully comfortable and have had sufficient practice with spotters/support around them. | 2 | 1 | 2 | If an individual is at risk of falling due to slippery footwear, ask them to change and dance in a more suitable and safe clothing If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Physical Exert ion/injury in performance | People may trip, fall, or slip, due to generally slippery flooring or due to trip hazards. | All those participating in the class | 2 | 3 | 6 | • Encourage all dancers to wear appropriate footwear and advise on what this is. • Ensure that trip hazards are identified and removed. • Ensure there are regular drinks breaks in performances especially in hot weather. • Ensure there is access to a first aid kit and ice packs encase of injury. | 1 | 3 | 3 | Ask the students Prior to the performance if they have had any recent injuries so they can accommodate for these. If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Exhaustion | Could Lead to an increased likelihood of injury or when hot, fainting. | All those participating in the class | 2 | 1 | 2 | - Ensure all dancers are aware of where they can get water. - Ensure there are plenty of water breaks in the classes. Especially in adverse weather conditions. Ensure no dancer feels obligated to over- exert themself. | 1 | 1 | 1 | If a student appears exhausted, be proactive in advising them to sit out and eliminate risk of further exhaustion. If Weather conditions are adverse eg: very hot president to make a call on if class should be on. if the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Setting up of dance equipment | Cause strain , injury, bruising or grazing | Students and teacher | 2 | 2 | 4 | - Limit carrying equipment to just committee members who have practice in handling them. - Train committee members in manual handling. | 1 | 2 | 2 | Ensure equipment is set up prior to letting students into class If a student appears hurt, be proactive in advising them to sit out and eliminate risk of further strain. If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Footwear: Correct Trainers | Injury, bruising, damage. | All participants and staff wearing these shoes | 2 | 3 | 6 | - Ensure all dancers have proper dance footwear. - Ensure the space is equipped for wearing shoes such as tap shoes. - Ensure any shoes and styles that require adequate training eg: pointe is checked before individuals are allowed to participate. - Ensure if people are borrowing dance shoes a committee member will advise on what size is correct. | 1 | 3 | 6 | Ensure equipment is set up prior to letting students into class If a student appears hurt, be proactive in advising them to sit out and eliminate risk of further strain. If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Electrical Equipment eg. Laptops/computers, speakers etc | Trip hazard and Fire hazard | All participants and organisers/staff and spectators | 2 | 3 | 6 | - Ensure no liquids are placed near electrical equipment. - Remind Dancers not to leave trailing wires. - Turn off plug sockets when not in use. | 1 | 3 | 3 | Seek medical attention if injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Security of Personal Belongings | Belongings being damaged or stolen | All participants and organisers/staff and spectators | 2 | 3 | 6 | - Remind Dancers to only bring essential items. - Remind dancers to take care of their belongings and that they are responsible for them. | 1 | 3 | 3 | Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Electronics | Risk of eye strain, injury, electric shock | Committee and attendees | 2 | 4 | 8 | Ensure regular breaks (ideally every 20mins) when using screens Ensure screen is set up to avoid glare, is at eye height where possible Ensure no liquids are placed near electrical equipment Ensure all leads are secured with cable ties/mats etc | 1 | 4 | 4 | Request support and advice from SUSU IT/Tech teams e.g. via activities team For external venues pre-check equipment and last PAT testing dates Seek medical attention as required |

| PART 2B – Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Assessment Action Plan |  |  |  |  |  |  |  |
| Part no. | Action to be taken, incl. Cost | By whom | Target date |  | Review date | Outcome at review date |  |
| 1 | Risk assessment shared with all organisers and checked through before the event | All Committee Members | 28/02/2026 |  | 28/02/2026 |  |  |
| 2 | Committee to read and share SUSU Expect Respect Policy | All Committee Members | 28/02/2026 |  | 28/02/2026 |  |  |
| 3 | Complete a financial assessment of the event | All Committee Members | 28/02/2026 |  | 28/02/2026 |  |  |
| 4 | Liaise with external companies (e.g. Southampton Sport) for all necessary paperwork. | All Committee Members | 28/02/2026 |  | 28/02/2026 |  |  |
| 5 | Ensure that all committee members and participants are aware of the fire evacuation procedures and where the evacuation points are | All Committee members | 28/02/2026 |  | 28/02/2026 |  |  |
| 6 | Ensure all medical emergencies are prepared for and there are qualified members for first aid attending | All Committee members | 28/02/2026 |  | 28/02/2026 |  |  |
| 7 | Ensure all equipment is away and, in a space, away from walking spaces. Ensure all trip hazards are made aware off and, if possible, placed in an area away from walking path. | All Committee members | 28/02/2026 |  | 28/02/2026 |  |  |
| 8 | Make sure is plenty of space for dancing or other physical activity and plan out time for a stretch session before physical activity. | All Committee members | 28/02/2026 |  | 28/02/2026 |  |  |
| Responsible committee member signature 1: S.Akintaju |  |  |  |  | Responsible committee member signature 2: second committee member signature At least 2 committee members need to sign Part B |  |  |
| Print name: Shiloh Akintaju |  |  |  | Date: 10/02/2026 | Print name: second committee member name |  | Date: Date of signature |

Assessment Guidance

| - Eliminate |  |  |  |  | Remove the hazard wherever possible which negates the need for further controls |  |  |  | If this is not possible then explain why |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Substitute |  |  |  |  | Replace the hazard with one less hazardous |  |  |  | If not possible then explain why |  |
| - Physical controls |  |  |  |  | Examples: enclosure, fume cupboard, glove box |  |  |  | Likely to still require admin controls as well |  |
| - Admin controls |  |  |  |  | Examples: training, supervision, signage |  |  |  |  |  |
| - Personal protection |  |  |  |  | Examples: respirators, safety specs, gloves |  |  |  | Last resort as it only protects the individual |  |
| LIKELIHOOD | 5 | 5 | 10 | 15 |  | 20 | 25 |
|  | 4 | 4 | 8 | 12 |  | 16 | 20 |
|  | 3 | 3 | 6 | 9 |  | 12 | 15 |
|  | 2 | 2 | 4 | 6 |  | 8 | 10 |
|  | 1 | 1 | 2 | 3 |  | 4 | 5 |
|  |  | 1 | 2 | 3 |  | 4 | 5 |
|  |  | IMPACT |  |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |