This document contains both ‘Part 1: Event Information’ AND ‘Part 2: Risk Assessment’. Both parts are required to be completed by the organising group.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Information |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact for The Event: Sai Mankhala | Email Address for Main Contact: sues@soton.ac.uk smrm1g24@soton.ac.uk | Club or Society Name: Engineering Society | Contact Number: 07421354813 |
| 1B) Event Information: |  |  |  |
| Event Name: STEM and Business Summer Ball 2026 | Event Date: Saturday 6th June 2026 | Event Venue/s: O2 Guildhall, West Marlands Road, Southampton, GB SO14 7FW | Total Attendees: 400 |
| Event Timings: | Set Up: 18:00 Event Start: 19:00 Event End: 23:00 Pack Down: 23:00+ |  |  |
| Event Breakdown This includes everything happening at your event, including fundraising, food provision, any performance or sporting activity, etc. | 12:00- Load in of Sai, Kez, and reps from maths and business and security arrival 14:00- Band setup and soundcheck 16:00-DJ setup and soundcheck 18:00 – Committee arrival to help set up 19:00 - 19:30 – Arrival 20:00 – 23:00 – Main event 23:00 – 00:00 – Pack up |  |  |
| Overview of event concept Description of the activities taking place. This includes everything happening at your event e.g. fundraising, food provision and any performance or sporting activity) | This event will also have a DJ for the entire event. The bar will be open the whole time and ID will be checked before entry. During the event attendees that would like to purchase food will have the opportunity to purchase from food trucks parked outside the O2 Guildhall. These trucks will be following Southampton City Council guidelines on food handling and have appropriate permissions to operate on the concourse of the venue. |  |  |
| Volunteers hosting the event List all committee and volunteers that will be present and responsible for the event, as well as their role. | Event lead: Keziban Mehmet (skm2g24) Event Co-leads: Samuel Irimagha (si2g23), Nick Chen (nhc1g23) Doors: Samuel Irimagha, Nick Chen, Various SUES and BizSoc committee members. Food Lead: TO BE DETERMINED; Food Trucks will be approved by SUSU to operate on university grounds. They would be provided to us working with the appropriate members of Susu staff to ensure appropriate measures are in place. We are currently in active conversation with Wayne Reddin (SUSU Business Development Team) Volunteers for set up: VARYING: SUES Committee, Business Society Committee. |  |  |
| Food provision For full guidance on this click here. | Food truck outside O2 Guildhall provided by: TO BE DETERMINED; Food Trucks will be approved by SUSU to operate on university grounds. They would be provided to us working with the appropriate members of Susu staff to ensure appropriate measures are in place. We are currently in active conversation with Wayne Reddin (SUSU Business Development Team) |  |  |
| Security & First Aid Requirements Is external first aid or security being hired? Who are the qualified first aiders in the group should a medical emergency occur? | O2 Guildhall are providing security and medics as part of our package but outside of that Ashley Wilson in our committee is a first aider Name of first aid provider or first aid trained member: Ashley Wilson |  |  |
| Provisional Budget If you would like a more extensive budget tracker, click here. | Projected Ticket Revenue: £8000 for total of 400 Tickets, £20 each average price (This is a minimum price. Prices for late bird tickets will be increased according to demand). Total cost for event: £7163.17 Profit: £836.83 -------------------- Venue Deposit: £1700 - security included in the venue cost |  |  |
| 1C) Only required if an external company/external speaker will be on site for the event - If you are inviting an external speaker to campus for your event, you are required to submit this form to legalservices@soton.ac.uk at least 15 working days before the event. For more guidance on this please click here. |  |  |  |
| Business Name: Awaiting specific details from Wayne (SUSU) | Business Contact Name: | Email Address: | Contact Number: |
| Arrival On Site: Departure time: | Company’s Risk Assessment Link: | Company’s Insurance Link: | Company’s Public Liability Information Link: |

Part 2A

Risk Assessment

| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |  |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Slips, trips and falls | Physical injury | Event organisers and attendees | 2 | 3 | 6 | All boxes and equipment to be stored away from main meeting area, e.g. stored under tables. Floors to be kept clear and dry, and visual checks to be maintained throughout the meeting by organisers. Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. Report any trip hazards to facilities teams/venue staff asap. If cannot be removed, mark off with hazard signs. | 1 | 4 | 4 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible, ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Manual handling, including setting up of equipment. E.g. table and chairs | Bruising or broken bones from tripping over table and chairs. | Meeting organisers and attendees | 2 | 3 | 6 | Follow manual handling guidelines. Ensure that at least 2 people carry tables or other bulky items. Setting up tables will be done by organisers. Work in teams when handling other large and bulky items. Request tools to support with the moving of heavy objects from SUSU Facilities/venue. E.g. hand truck, dolly, skates. Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable. | 1 | 3 | 3 | Seek assistance from facilities staff/venue staff if needed. Seek medical attention from SUSU/venue Reception if in need. Contact emergency services if needed. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Overcrowding / Inadequate Meeting Space | Physical injury, distress, exclusion | Event organisers and attendees | 2 | 3 | 6 | Do not push/shove. If large crowds form, request barriers from SUSU facilities team or external venue to assist with crowd management. Committee checks on space, lighting, access, tech available, etc. Use ticketing system (SUSU Box Office) for regular sessions/meetings to avoid exceeding venue capacity. Ensure space meets needs of members e.g. considering location & accessibility of space (use AcessAble database to check accessibility information of venues). If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. Committee to consult members on needs and make reasonable adjustments where possible Provide remote meeting options for members where possible. | 1 | 3 | 3 | Seek medical attention if problem arises. Liaise with SUSU reception/Activities Team and UoS Room Booking team on available spaces for meetings. Postpone meetings where space cannot be found. Welfare Officer to complete WIDE training. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents causing reputational damage to the group, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name into disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring all members are reminded that they are representing the club/society, SUSU and the University, often in branded clothing. Members are reminded that they need to adhere to SUSU’s Code of Conduct. | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Report any incidents to the Activities Team. |
| Costumes/Fancy Dress | Props/costumes causing injury or offence | Participants Members of the public | 2 | 1 | 2 | Ask members to only bring small items and use sensibly. Members of the society are responsible for their own possessions and the use of them. Choose a theme unlikely to cause offence. Any participant wearing items deemed offensive asked to remove these. Society to follow and share with members Code of Conduct/SUSU Expect Respect policy. | 1 | 1 | 1 | SUSU Expect Respect policy to be followed. Committee WIDE training. Ensure that any incidents involving public or others are recorded and addressed. Report any incidents to the Activities Team. |
| Alcohol consumption | Peer pressure/coercion, alcohol poisoning, spiking, increased risk to personal safety | Event organisers, event attendees, | 2 | 4 | 8 | Members are responsible for their individual safety though and are expected to act sensibly. Initiation behaviour not to be tolerated and drinking games to be discouraged. For socials at bars/pubs etc., bouncers will be present at most venues. Bar Security staff will need to be alerted and emergency services called as required. Where possible the consumption of alcohol will take place at licensed premises. The conditions on the license will be adhered to and alcohol will not be served to customers who have drunk to excess Committee to select ‘student friendly’ bars/clubs and contact them in advance to inform them of the event. Committee to advise and remind members to always watch their own drinks. Society to follow and share with members Code of conduct/SUSU Expect Respect policy. | 1 | 3 | 3 | Follow SUSU incident report policy. Call emergency services as required 111/999. Welfare Officer to complete WIDE training. |
| Spiked Drinks/Alcohol Poisoning | Illness, loss of consciousness, loss of self- control | Event organisers, event attendees, | 2 | 5 | 10 | Committee to supervise meetings/socials and attend each venue. Ideally, they will not drink to excess during the event. Bouncers/trained staff in pubs should watch for excessive drinking and watch people who are believed to have consumed a lot of alcohol. Report any suspicious/unusual behaviour to staff. Participants encouraged to stay with a nominated ‘buddy’ where possible. The organisers have confirmed the premise is licensed. Action organisers (Part B). The consumption of alcohol will take place at licensed premises. The conditions on the license will be adhered to and alcohol will not be served to customers who have drunk to excess. Members/participants are advised to watch their own drinks. Games involving binge drinking or the consumption of excessive amounts of alcohol are not to be undertaken.- Society to follow Code of conduct/Expect Respect policy | 2 | 3 | 6 | Members are responsible for their individual safety and are expected to act sensibly when walking around. For anyone who is too inebriated it will be suggested to them that they should return home rather than continue on the social. Taxis will be called if required (look at SUSU Safety Bus, Radio Taxis options). If they need to go to the hospital they will also be accompanied there. Participants advised to avoid leaving drinks unattended and if you think anything has been added to a drink; report it; try and retain the drink for testing. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Travel by foot | Disturbance to neighbourhood, participants getting lost, increased risk to personal safety, vehicle collision causing serious injury | Event organisers, event attendees, Members of the public | 4 | 3 | 12 | Members are responsible for their individual safety and are expected to act sensibly. Local venues known to UoS students chosen. Event organisers will be available to direct people between venues. Attendees will be encouraged to identify a ‘buddy’, this will make it easier for people to stay together. They will be encouraged (but not expected) to look out for one another and check in throughout the night where possible. Avoid large groups of people totally blocking the pavement or spilling in to the road. Anybody in the group who is very drunk or appears unwell and therefore not safe should be encouraged to go home ideally with someone else. If required a taxi will be called for them (ideally SUSU Safety Bus will be used, or Radio Taxis). Be considerate of other pedestrians and road users, keep disturbance and noise down. | 2 | fire | 4 | Where possible venue chosen for the event will be local/known to members and within a short travel distance for members. Contact emergency services as required 111/999. Incidents are to be reported as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Travel by car, train, bus, plane when leaving the local area. | Vehicle collision – causing anything from minor to severe injuries, as well as mental health issues. | Members, those driving, members of the public | 2 | 5 | 10 | Group committee to check that drivers have the relevant licences and insurance for the mode of travel. This includes if they have completed a SUSU minibus test. Members expected to drive or travel in a sensible manner, with those doing otherwise to face disciplinary action (from the club/society in the first instance). Can cause reputational issues, especially if driving SUSU branded vehicles. Importance of this to be reminded. | 1 | 5 | 5 | Contact emergency services as required 111/999. Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Medical emergency | Members may sustain injury /become unwell Pre-existing medical conditions, sickness, distress | Members | 1 | 5 | 5 | Advise participants to bring their personal medication if it might be required. Members/Committee to carry out first aid if necessary and only if qualified and confident to do so. Contact emergency services as required 111/999. Contact SUSU Reception/venue staff for first aid support. Members can be referred to The Student Hub (02380 599 599, studenthub@soton.ac.uk) in case of distress. | 1 | 4 | 4 | Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Fire | Smoke inhalation, burns. Risk of extreme harm. | All participants and organisers, any staff and spectators | 1 | 5 | 5 | Those leading the session must ensure they are aware of and fully understand the venue or location’s fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the participants the nearest emergency exit routes at the start of a session, and the importance of leaving calmly in case of an emergency. Avoid build-up of debris in the activity area. Consider accessibility requirements. | 1 | 4 | 4 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Anti-social, violent, or offensive behaviour | Disturbance to the neighbourhood, reputational damage, injury and distress as a result of violence | Event organisers, event attendees, public | 2 | 5 | 10 | Bouncers/security will be present at most licensed venues. Bar/venue security staff will need to be alerted and emergency services called as required. Do not personally engage with any violent behaviour. Stay safe and inform the bar staff/police if necessary. The consumption of alcohol will take place at licensed premises. The conditions on the license will be adhered to and alcohol will not be served to customers who have drunk to excess. Committee to select ‘student friendly’ bars/clubs and contact them in advance to inform them of the event. Society to follow and share with members Code of conduct/SUSU Expect Respect policy. | 1 | 3 | 5 | If the situation becomes very serious and results in the participant being arrested then it will be made clear that they cannot be accompanied to the police station. Follow SUSU incident report policy. Call emergency services as required. |
| Adverse weather | Hypo- or hyperthermia, illness, injury, slipping, burns | Event organisers, event attendees | 3 | 4 | 12 | Lead organiser to check the weather are suitable for activities on the day. Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites. In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, and to hydrate (especially if drinking alcohol). | 2 | 2 | 4 | If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date. Contact emergency services if needed. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Financial risk | Group debt | Group members, SUSU | 4 | 3 | 12 | We will cancel and refund members if we do not sell at least 380 tickets. The Engineering society has sufficient funds to pay the initial deposit. | 2 | 3 | 6 | Contact SUSU Activities Team if you have any questions or concerns about this – we would rather know sooner than later! |
| Events Involving Food | Allergies Food poisoning Choking | All | 3 | 5 | 15 | Our catering is cooked on site by a 3rd party food truck that follows all food hygiene regulations and has an appropriate EHO rating. TO BE DETERMINED; Food Trucks will be approved by SUSU to operate on university grounds. They would be provided to us working with the appropriate members of Susu staff to ensure appropriate measures are in place. We are currently in active conversation with Wayne Reddin (SUSU Business Development Team) Only order/buy food at establishments with appropriate food hygiene (EHO) rating. Food to only be provided/eaten when other activities are stopped. Follow good food hygiene practices - no handling food when ill, tie back hair, wash hands regularly using warm water and soap, refrigerate necessary products. For store-bought items/snacks, keep packaging to hand for ingredient and allergen information. | 1 | 5 | 5 | SUSU food hygiene level 2 course available for completion- requests made to Activities Team. Call for first aid/emergency services a required . Report incidents via SUSU incident report procedure. |
| Manual handling, including setting up of equipment. E.g. table and chairs. | Bruising or broken bones from tripping over table and chairs | Meeting organisers and attendees | 2 | 3 | 6 | Make those involved aware of the potential risks, follow manual handling guidelines. Ensure that at least 2 people carry tables or other bulky items. Setting up tables will be done by organisers. Work in teams when handling other large and bulky items. Request tools to support with move of heavy objects from SUSU Facilities/venue. E.g. hand truck, dolly, skates. Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable. | 1 | 3 | 3 | Seek assistance if in need of extra help from facilities/venue staff. Seek medical attention from SUSU Reception if in need. All incidents are to be reported as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Dropping or hitting instruments | - Damage to instruments - Injury to surrounding people - Damage to space being used | Those in the vicinity | 2 | 3 | 6 | - Make sure everyone is spaced out as much as possible so people can move around as much as possible - Larger instruments/instruments that move a lot (trombones) are given extra space - Instruments to be put in case or safely out of the way when not in use - Nothing to be kept on the floor unless essential | 1 | 3 | 3 | Committee to ensure room booking is adequate with enough space to accommodate larger instruments. Request room changes as needed - Seek medical attention from SUSU Reception/venue staff if in need - Contact facilities team via SUSU reception/venue staff - Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Moving/setting up instruments and stands | - Back/muscle strain from lifting items that are too heavy - Trapping fingers in stands or other items - Damaging equipment - Dropping equipment on feet/another person - Falling moving equipment on stairs | Those setting up and members nearby or assisting. | 2 | 3 | 6 | - Any heavy items lifted by multiple people - Use lifts where possible for heavy items, where not possible extreme caution to be used and additional members should be on hand to assist - Request tools to support with move of heavy objects- SUSU Facilities/venue. E.g. hand truck, dolly, skates - Teach members how to correctly carry equipment and how to safely set up specific items and don’t allow untrained members to assist - Those carrying things be accompanied by someone able to clear a pathway open door - Committee to ensure adequate time for set up and pack down is planned for /allocated when bookings are made | 1 | 3 | 3 | Committee to ensure tech team recruited/trained to move and set instruments - Seek medical attention from SUSU Reception/venue staff if in need - Contact facilities team via SUSU reception/venue staff - Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Unmonitored Speakers causing feedback/deafening noise | - Hearing damage - Disruption to unrelated activities/complaint | Those in the vicinity and potentially members of the public in the building/nearby | 4 | 3 | 12 | - Someone with relevant sound/tech training or know-how nearby to monitor levels - Microphones/speakers turned off when not in use - Volume kept low | 2 | 2 | 4 | - Seek medical attention from SUSU Reception/venue staff if in need - Contact facilities team via SUSU reception/venue staff - Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Consistent (intentional) loud noise | - Hearing damage | Those regularly in the rehearsal | 4 | 3 | 12 | - Recommend earphones are used by affected members - Position musicians appropriately so direct exposure is minimised - Mutes/screens utilised if/where appropriate - Avoid use of small confined spaces | 3 | 2 | 6 | - Seek medical attention from SUSU Reception/venue staff if in need - Contact facilities team via SUSU reception/venue staff - Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |

| PART 2B – Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Assessment Action Plan |  |  |  |  |  |  |  |
| Part no. | Action to be taken, incl. Cost | By whom | Target date |  | Review date | Outcome at review date |  |
| 1 | Risk assessment shared with all organisers and checked through before the event Follow SUSU Food Provision Guidance for events involving home-cooked/prepared food or external catering. | Sai Mankhala | 01/06/2026 |  | 03/06/2026 |  |  |
| 2 | Committee to read and share SUSU Expect Respect Policy | Sai Mankhala | 01/06/2026 |  | 03/06/2026 |  |  |
| 3 | Complete a financial assessment of the event | Noah Nutkins and Sai Mankhala | 01/06/2026 |  | 03/06/2026 |  |  |
| 4 | Liaise with external companies (e.g. venue, DJ, caterers) for all necessary paperwork. | Keziban Mehmet | 01/06/2026 |  | 03/06/2026 |  |  |
|  | Share event info and ticket link with all members. | Keziban Mehmet | 09/05/2026 |  | 10/05/2026 |  |  |
| Responsible committee member signature 1: |  |  |  |  | Responsible committee member signature 2: |  |  |
| Print name: Keziban Mehmet |  |  |  | Date: 04/05/2026 | Print name: Sai Mankhala |  | Date: 05/05/2026 |

Assessment Guidance

| - Eliminate |  |  |  |  | Remove the hazard wherever possible which negates the need for further controls |  |  |  | If this is not possible then explain why |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Substitute |  |  |  |  | Replace the hazard with one less hazardous |  |  |  | If not possible then explain why |  |
| - Physical controls |  |  |  |  | Examples: enclosure, fume cupboard, glove box |  |  |  | Likely to still require admin controls as well |  |
| - Admin controls |  |  |  |  | Examples: training, supervision, signage |  |  |  |  |  |
| - Personal protection |  |  |  |  | Examples: respirators, safety specs, gloves |  |  |  | Last resort as it only protects the individual |  |
| LIKELIHOOD | 5 | 5 | 10 | 15 |  | 20 | 25 |
|  | 4 | 4 | 8 | 12 |  | 16 | 20 |
|  | 3 | 3 | 6 | 9 |  | 12 | 15 |
|  | 2 | 2 | 4 | 6 |  | 8 | 10 |
|  | 1 | 1 | 2 | 3 |  | 4 | 5 |
|  |  | 1 | 2 | 3 |  | 4 | 5 |
|  |  | IMPACT |  |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |