This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group.

You will also need to complete a charity form linked here. Also all level 2 food hygiene certificates need to be sent to susurag@soton.ac.uk (Charity Fundraiser) or suactivities@soton.ac.uk (Internal Fundraiser) if you haven't completed the training you can sign up here.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: Olaide Oni | Email Address for Main Contact: oo2n22@soton.ac.uk | Club or Society: MedSoc | Contact Number:07410933200 |
| 1B) Event Information: |  |  |  |
| Event Name: MedSoc Scrubs and Bake Sale | Event Date:15/11/2025 | Event Venue/Venues: Redbrick | Total Attendees: 50 |
| Event Timings: 1:30-3:30 | Set Up: Table and collect SumUp machines at 12:30 (13:00: Ensure all allergens are displayed) Event Start: 13:30 Event End: 15:30 Pack Down: 15:30 |  |  |
| Event Break down: (This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity.) | Set Up: table and collect SumUp machines at 12:30 13:00: Ensure all allergens are displayed Event Start: 13:30 Will ensure stall is maned by at least 2 members for duration of bake/scrubs sale (13:30-15:30) Event End: 15:30 Pack Down: 15:30- onwards: return the SumUp Machine |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Boxoffice: You can set up Box-office tickets through your group's hub page for guidance on this click here: | No | How Much Are your Tickets? And how many are available? / | / |
| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | A Stall on the Redbrick selling baked goods (Cakes, Biscuits, Brownies) and labcoats/scrubs to raise money for the local charities Friends of Picu and WarChild as well as the Movember Foundation. All Donations will be taken by card on Sumup Machines and via the Movember JustGiving page through QR codes. All baked goods will have ingredients & allergens labelled. Anyone who handles or has made the baked goods will have completed the level 2 food Hygiene course. |  |  |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | Rota of who leading stall 13:30 – 15:30: Olaide(Charities Rep), Pedro(President) and Adham(Secretary) will be present to host and lead the stall |  |  |
| Tech Requirements (For a full list of what you can hire click here) | / |  |  |
| Facilities Requirements | 2x tables 2x chairs |  |  |
| Food Requirements (For full guidance on this click here) | Baked items prepared by students & who has the food hygiene training |  |  |
| Security & First Aid Requirements (Who are the qualified first aiders in the group should a medical emergency occur?) |  |  |  |
| Decorations that you are providing | Table cloths Decorative plates |  |  |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | Total Budget: £50 for ingredients |  |  |

| PART A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| General Considerations |  |  |  |  |  |  |  |  |  |  |
| Slips, trips and falls | Depending on weather – may be slippery and cause physical injury. | Committee members and general public | 2 | 3 | 6 | Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area if weather is bad or items fall. Equipment should be placed in a place out of the pathway where people are walking to avoid tripping | 1 | 3 | 3 | Seek medical attention immediately from SUSU Follow SUSU incident report policy. Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed |
| Fire | Smoke inhalation, burns and more severe. Risk of extreme harm. | All participants and organisers/staff and spectators | 1 | 5 | 5 | Those leading the session must ensure they are aware of and fully understand the venue or locations fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the Volunteers/Event Staff the nearest emergency exit routes at the start of a session, and the importance of assisting others to leave calmly in case of an emergency. Consider accessibility requirements | 1 | 4 | 4 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Setting up/moving or chairs/tables/other objects in the area. | Bruising or broken bones from tripping over table and chairs. | Meeting organisers and attendees | 2 | 3 | 6 | Make stall operators aware of the potential risks, follow manual handling guidelines Ensure that at least 2 people carry tables and large objects. Setting up tables will be done by organisers. - Work in teams when handling other large and bulky items. - Request tools to support with move of heavy objects- SUSU Facilities/venue. E.g. hand truck, dolly, skates Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable Work in teams when handling anylarge and bulky items. Request tools to support with move of heavy objects- SUSU Facilities/venue. E.g., hand truck, dolly, skates | 1 | 3 | 3 | Seek assistance if in need of extra help from facilities staff/venue staff if needed Seek medical attention from SUSU Reception if in need Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Overcrowding | Physical injury | Event organisers and attendees | 1 | 3 | 3 | - Committee check on Redbrick pre-booking, to ensure environment is clear and appropriate for the event - Ensure space meets needs of members e.g. considering location & accessibility of space - Committee to consult members on needs and make reasonable adjustments where possible | 1 | 3 | 3 | Seek medical attention if problem arises Liaise with security and SUSU on the need for security teams on the day Postpone event where space seems inadequate to meet needs of event |
| Electronics in involved in activities e.g. card machines, laptops, computers | Risk of eye strain, injury, electric shock | Committee and attendees | 2 | 4 | 8 | Ensure regular breaks (ideally every 20mins) when using screens Ensure screen is set up to avoid glare, is at eye height where possible Ensure no liquids are placed near electrical equipment Ensure all leads are secured with cable ties/mats etc | 1 | 4 | 4 | Request support and advice from SUSU IT/Tech teams e.g. via activities team For external venues pre-check equipment and last PAT testing dates Seek medical attention as required |
| Accessibility: Entrances and Exits to the chosen area. | Participants may be prevented from attending the activity due to a lack of considerations of accessibility needs and requirements. They could also be prevented from leaving the area quickly in an emergency if the correct infrastructure and considerations have not been made. | Participants, committee | 1 | 5 | 5 | All areas chosen for activity will have their suitability checked. If a closed activity for members, members will be consulted to ensure there are no accessibility requirements. If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. | 1 | 5 | 5 | In case of an emergency, call the emergency services on 999. If those with accessibility problems have not been able to exit from Redbrick, make the building manager and emergency services aware. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents during the bake and scrubs sale could pose a reputational risk to the club, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name into disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring that any incidents involving public or others are recorded and addressed. Ensuring all members are reminded that they are representing the club/society, SUSU and the University in (usually) branded clothing. | 1 | 1 | 1 |  |
| Financial Risk: For the club or society, or potentially even SUSU if the club/soc finds itself in difficulty. | The costs of the ingredients used to bake for the sale costing more than planned, weakening their financial position. Incidents with members of the public, participants, staff or members causing lawsuits and financial penalties. | The club or society Members subject to lawsuits SUSU if required to assist. | 1 | 1 | 1 | Clubs and societies required to complete financial forecasting and budget for the year. All encouraged to review membership fees yearly to ensure they are able to comfortably cover costs. SUSU can offer clubs and societies loans – these will need to be agreed and a payment schedule decided upon. Clubs and societies that have to rely on a loan will be subject to development plans to ensure their future is protected. | 1 | 1 | 1 |  |
| Legal Compliance: Bake and scrubs sale going against set law. This includes breaches of the freedom of speech act | Fines imposed upon the student group as well as SUSU. Jail sentences. Reputational risk to the student group, SUSU and the wider University | The club or society, committee and members, SUSU or the Wider University. | 1 | 1 | 1 | All clubs and societies should ensure they are following set law at all times. If ever in doubt, they will contact the Activities team prior to the activity taking place. All who wish to bring in an external speaker must follow due process, available here This will be looked over by the University Legal Services team, and may require security being consulted and an extra risk assessment being submitted. | 1 | 1 | 1 |  |
| Medical Issues: Pre-existing medical conditions, sickness, distress | Illness, death | Members, committee | 3 | 5 | 15 | All clubs and societies should have a process for if a medical issue occurs for e.g. epipens if exposed to allergen accidentally - Members/Committee to carry out first aid if necessary and only if qualified and confident to do so Members do not need to disclose medical information to committee (GDPR), but all committee should know how to find a first aider and help quickly. Contact reception in medical emergency for support. If no-one can be found, contact campus Security – 02380 59331 | 3 | 5 | 15 | In an emergency, contact 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Charity Fundraising |  |  |  |  |  |  |  |  |  |  |
| Handling and Storing Money – MedSoc | Theft, Individuals being mugged. | Members, charity and participants | 3 | 4 | 12 | Transactions will be done via card payment only. Only Medsoc committee members will have access to these card readers and will be advised to keep it on them for the whole event. Additional fundraising can also be completed via QR code to the Movember JustGiving Page | 2 | 3 | 6 | No Cash to be accepted at all. MedSoc will not use Personal Card machines to take payments. |
| Handling and storing card readers – MedSoc Charity Bake Sale | - Theft - Individuals being mugged/robbed - Loss/misplacement leading to financial loss | Members and Participants | 3 | 4 | 12 | Southampton RAG procedures will be followed: - Charity Event form completed, and RAG approval will be given - All food hygiene certificates and event risk assessment to be approved by activities team - Sum-up Card machine to be requested and collected from SUSU reception. - Should not be storing money all donations to be taken via Sumup Machine or Just Giving Pages | 2 | 3 | 6 | No Cash to Be Accepted at all. No card machines to be left unattended. No Volunteers to be left alone with the card machine In the event of theft committee members will: - Highlight the incident to any community police officers in the area/report to 111 - Report to SUSU Duty manager and Complete a SUSU incident report |
| Abuse of Members and Volunteers | Members of the public or students may act violently towards volunteers. - Assault, violence, threatening and aggressive behaviours | Committee members and attendees | 3 | 4 | 12 | No Volunteers are ever to be left alone. Always have at least 2 people at a stall or at an Event. - Event planned for Redbrick – a student based area - Leaders to advise all attendees to not engage/respond to any protests, aggressive behaviour- if safe to do so will encourage group to move on and remove themselves from situation- - The event will be ended and students advised to return to other areas on campus if this continues or back to their homes - Prior information about event and what to expect given out so participants know what to expect via social media posts - Attendees made aware they could join and leave the event at any time. | 2 | 3 | 6 | - Report to SUSU Duty manager and Complete a SUSU incident report - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Venue/Location considerations | Require certain licenses/sign off – SUSU signs off booking authorisation | Organisers, Attendees, SUSU | 1 | 4 | 4 | Ensure the venue has the relevant licenses from SUSU required for your event ahead of time. Ensure your event has the required sign off by the SUSU’s security teams. Ensure proper booking process is followed for ALL bookings on and off campus. With no event going forward without Activities Approving the Risk Assessment. On campus - Risk assessment - Contract | 1 | 2 | 2 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Lone working | Stolen goods, injury to individual misuse of card reader. | Committee | 3 | 3 | 9 | Ensure no one is left alone as a volunteer at the sale especially if using a Sum-up Card reader. Event led to brief volunteers to operate the card readers in pairs and briefed on how to handle situations surrounding these. | 3 | 1 | 3 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Adverse weather | Injury, Illness, Slipping, Burns | Event organisers, event attendees, | 4 | 3 | 12 | Lead organiser to check the weather is suitable for activities on the day Cancellation window (1-2 days prior to the event i.e. 13th or 14th November 2025) Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites If Cancellation is required ensure all relevant parties are contacted. SUSU – subookings@soto.ac.uk Uni – roombookings@soton.ac.uk Or your external contacts. | 4 | 1 | 4 | If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date |
| MedSoc Bake and Scrubs Sale | Slipping, Tripping over chairs or tables | Committee members, General public |  |  |  | Ensure the chairs are out of the pathway where the public are walking, keeping the area clear of obstacles |  |  |  | Ensuring we are wearing suitable footwear for the day and keeping the area dry where possible |
| Food |  |  |  |  |  |  |  |  |  |  |
| Serving and preparation of food | - Allergies - Food poisoning - Choking | All | 3 | 5 | 15 | - Homemade items to be avoided by those with allergies - precautions should be made by those with appropriate food hygiene training (Level 2 +) - Only order/buy food at establishments with appropriate food hygiene rating - Food to only be provided/eaten when other activities are stopped - Follow good food hygiene practices- no handling food when ill, tie back hair, wash hands and equipment regularly using warm water and cleaning products, refrigerate necessary products | 1 | 5 | 5 | SUSU food hygiene level 2 course available for completion- requests made to activities team Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Contamination of food through food preparation. | Illness, Food poisoning, Allergy. | ALL | 2 | 3 | 6 | - Ensure all food is prepared in advance and done in a clean and hygienic environment. In line with the level 2 food hygiene training. - Ensure all ingredients used when making items are withing there used by or best before dates. - Ensure all frozen food is thoroughly defrosted before use. - Endeavour to not cross contaminate foo such as nuts and let customers know if cross contamination is a possibility. | 1 | 3 | 3 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Storage and Display of Food | Illness, Food poisoning, Allergy. | All | 2 | 3 | 6 | Keep any products containing fresh produce in the fridge. Do not leave any food out for longer than 4 hours. - Store all products in a clean sealable container away from raw foods. - Transport cakes in a clean sealable container. | 1 | 3 | 3 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Food Allergies and Dietary requirements | Illness, Allergic reaction | Customers | 3 | 5 | 15 | - Where possible remove common allergens form ingredients. allergen-chart-1.docx (live.com) Lists all 14 of the core allergens. - Ensure each cake is labelled with its name and list of ingredients. - Have a list available of all ingredients for any products sold at the stall. - Always use recipes from reputable sources. - Make sure to keep any packaging. | 1 | 5 | 5 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. - For more information on allergens: Providing food at community and charity events ¦ Food Standards Agency Follow SUSU incident report policy |
| Electrical Issues | Serious/ Fatal injuries because of electric shock | Volunteers and customers | 2 | 4 | 8 | - Equipment to |  |  |  |  |
| Gas hobs and ovens used to prepare bakes | Serious or Fatal injuries as a result of explosion/release of gas or hot oven. | Committee members | 2 | 5 | 10 | - Always use protective equipment such as oven gloves when cooking. - Only use Gas hobs and ovens that are functional and appropriate - Make sure anyone using the appliances are confident to do so. | 1 | 5 | 5 | - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. Follow SUSU incident report policy |
| Stock/Food Falling | Physical Injury, Illness, Food poisoning | All Participants | 3 | 2 | 6 | - Ensure all stock is stored correctly and not stacked to high. - If any products fall that these are not sold and disposed of in food waste. | 1 | 2 | 2 | - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. - SUSU food hygiene level 2 course available for completion- requests made to activities team Follow SUSU incident report policy |
| Food Temperature | Food poisoning, illness, perished stock | All public and committee | 2 | 3 | 6 | - Do not leave any food out for longer than 4 hours. - Ensure all products or produce are stored as describe on packaging. - Ensure all items are baked to correct temperatures from reputable recipes or packaging. | 1 | 3 | 3 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Use of Knives for Cutting Food | Cuts and injuries | Volunteers and stall operators | 2 | 2 | 4 | - Make stall operators aware of the potential risks. - Where possible use wooden cutlery. - Knife not to be left unattended and stored away safely when not in use. - Ensure the Knife is suitable for the task and the food you are cutting. - When carrying the Knife ensure the blade is pointing down. |  |  |  | - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. Follow SUSU incident report policy |
| Allergies - food and drink | Allergic reactions to food and drink when out | Event organisers, event attendees, | 3 | 5 | 15 | Attendees responsible for own welfare I such instances- follow guidelines of venues. First aid requested from bar staff as required. | 1 | 5 | 5 | Call Emergency Services/alert bar staff Follow SUSU incident report policy |

| # PART B – Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # Risk Assessment Action Plan |  |  |  |  |  |  |  |
| # Part no. | # Action to be taken, incl. Cost | # By whom | # Target date |  | # Review date | # Outcome at review date |  |
|  | Committee to send copies of all food hygiene training certificates to suactivities@soton.ac.uk | Olaide Oni Adham Al-Utayem | 11/11/2025 |  | # 11/11/2025 |  |  |
|  | Committee members to create and display lists of ingredients (with allergens written in bold) at the stall | Olaide Oni | 15/11/2025 |  | # 11/112025 |  |  |
|  | Committee to read and share SUSU Expect Respect Policy | Olaide Oni | 11/11/2025 |  | # 11/11/2025 |  |  |
|  | Complete a Charity Event form and send this to suactivties@soton.ac.uk | Olaide Oni | 11/11/2025 |  | # 11/11/2025 |  |  |
|  | Committee to Read and share SUSU Expect respect policy | Olaide Oni | 11/11/2025 |  | # 11/11/2025 |  |  |
|  | Set Up Just Giving/Fundraising Platform and/or book Sum-up Card Machines | Olaide Oni Pedro Caballero Krishna Kini Adham Al-Utayem | 11/11/2025 |  | # 11/11/2025 |  |  |
| # Responsible committee member signature: |  |  |  |  | # Responsible committee member signature: |  |  |
| # Print name: Olaide Oni |  |  |  | # Date 11/11/2025 | # Print name: Pedro Caballero |  | # Date 11/11/2025 |

Assessment Guidance

| - Eliminate | Remove the hazard wherever possible which negates the need for further controls | If this is not possible then explain why |  |
| --- | --- | --- | --- |
| - Substitute | Replace the hazard with one less hazardous | If not possible then explain why |  |
| - Physical controls | Examples: enclosure, fume cupboard, glove box | Likely to still require admin controls as well |  |
| - Admin controls | Examples: training, supervision, signage |  |  |
| - Personal protection | Examples: respirators, safety specs, gloves | Last resort as it only protects the individual |  |

| LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 | 4 | 8 | 12 | 16 | 20 |
|  | 3 | 3 | 6 | 9 | 12 | 15 |
|  | 2 | 2 | 4 | 6 | 8 | 10 |
|  | 1 | 1 | 2 | 3 | 4 | 5 |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  |  | IMPACT |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

Risk process

- Identify the impact and likelihood using the tables above.

- Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.

- If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.

- If the residual risk is green, additional controls are not necessary.

- If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable.

- If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.

- Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.

- The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |