
This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group. Please edit or remove sections that are not relevant or add specifics to this template before submitting to GroupsHub under the Risk Assessments tab according to your individual event plans.

	Part 1

	 Event Information

	1A) Contact Information:

	Main Contact for The Event: 
Aaron Campbell


	Email Address for Main Contact:
Ac7g23@soton.ac.ukk
	Club or Society Name: 
Renewable Engineering Society University of Southampton (RESUS)
	Contact Number:
07305790729

	1B) Event Information: 

	Event Name: 
Turbine Display for Freshers
	Event Date:
15/09/2026
	Event Venue/s:
Grass outside susu

	Total Attendees: 
2 members of the society supervising each stall at all times. Open to members of the public/ students

	Event Timings:
0800-1800
	Set Up: 0800-0900
Event Start: 0900
Event End: 1700
Pack Down: 1700-1800


	Event Breakdown

This includes everything happening at your event
	Example:
0600-0615 – President to confirm weather is suitable and to inform committee
0745-0800 – SUSU Facilities team to provide barriers
0800-0815 – Committee briefing including indoor table
0815-0845 – Committee to set up turbine
0845-0900 – Committee to confirm barriers are suitable and set up advertisement 
0900-1700 – Committee to supervise the stalls (turbine and interior) with regular rotations (see below)
1700-1730 – Committee to disassemble turbine and pack away
1730-1745 – Committee debrief
1745-1800 – Buffer time on pack down

	Overview of event concept

Description of the activities taking place. This includes everything happening at your event

	Additional advertisement for the society at bunfight through the display of our turbine and opportunities for committee to discuss our society - and renewable engineering as a whole – with prospective members.

	Volunteers hosting the event

List all committee and volunteers that will be present and responsible for the event, as well as their role.
	
Event lead: Aaron Campbell
Host: SUSU
Volunteers for set up: Aaron, Jamie, _ , _
Volunteers for pack down: Aaron, Sam, Sophie?, _



	PART A 

	(1) Risk identification
	(2) Risk assessment
	(3) Risk management

	Hazard
	Potential Consequences

	Who might be harmed

(user; those nearby; those in the vicinity; members of the public)

	Inherent
	
	Residual
	Further controls (use the risk hierarchy)

	
	
	
	Likelihood
	Impact
	Score
	Control measures (use the risk hierarchy)
	Likelihood
	Impact
	Score
	

	General Considerations 

	Slips, trips and falls
	Soft tissue injury e.g., sprain, bruising. Potential broken ankle or other breaks i.e. wrists etc. Links directly to weather and ground surfaces.
	All participants and organisers/staff and spectators  
	2
	3
	6
	Check venue conditions for holes, lumps, and other obstacles. 
	1
	3
	3
	If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately.
Call 999 in an emergency.
Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy.

	Fire
	Smoke inhalation, burns and more severe. Risk of extreme harm.
	All participants and organisers/staff and spectators  
	1
	5
	5
	Those leading the session must ensure they are aware of and fully understand the venue or locations fire procedures. 

Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. 

Highlight to all the Volunteers/Event Staff the nearest emergency exit routes at the start of a session, and the importance of assisting others to leave calmly in case of an emergency. 

Consider accessibility requirements 
	1
	4
	4
	In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. 

Once in a safe position to do so, call the emergency services on 999. 

Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy.

	Setting up/moving or chairs/tables/other objects in the area. 
Including the turbine (note turbine is aprox 15kg assembled but breaks into parts no more than 1kg)
	Bruising or broken bones from tripping over table and chairs.
Bruising or broken bones from the turbine components falling on people.
	Meeting organisers and attendees
	2
	3
	6
	Make Event Volunteers aware of the potential risks, follow manual handling guidelines

Ensure that at least 2 people carry tables and large objects.
Setting up tables will be done by organisers.

Work in teams when handling other large and bulky items.

Turbine to be assemble in parts by the team used to constructing it with the main base transported between two people if moved assembled.

Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable.


	1
	3
	3
	Seek assistance if in need of extra help from facilities staff/venue staff if needed

Seek medical attention from SUSU Reception if in need

Contact emergency services if needed 

All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy

	Overcrowding
	Physical injury 
	Event organisers and attendees
	1
	3
	3
	Do not push/shove

If large crowds form, barriers can be requested by SUSU facilities team (if available on the day) to assist with crowd management.

Book during quieter times when less activities taking place on Redbrick/book all available space 
Inform other bookings on the Redbrick/in the area of the event
	1
	3
	3
	Seek medical attention if problem arises

With support from a SUSU Activities coordinator Inform UoS security team of the event (– on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk) and liaise with them on need for security teams on the day

Security team may inform police of the event if required (e.g. marches)


	Electronics
	Risk of eye strain, injury, electric shock
	Committee and attendees

	2
	4
	8
	Ensure regular breaks (ideally every 20mins) when using screens 

Ensure screen is set up to avoid glare, is at eye height where possible

Do not use laptops for advertisement if it is possible to rain or no cover is available

	1
	4
	4
	Request support and advice from SUSU IT/Tech teams e.g. via activities team

For external venues pre-check equipment and last PAT testing dates 
Seek medical attention as required

	Accessibility:

Entrances and Exits to the chosen area. 
	Participants may be prevented from attending the activity due to a lack of considerations of accessibility needs and requirements. 

They could also be prevented from leaving the area quickly in an emergency if the correct infrastructure and considerations have not been made.  
	Participants, committee
	1
	5
	5
	All areas chosen for activity will have their suitability checked. 

If a closed activity for members, members will be consulted to ensure there are no accessibility requirements. 

If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. 

Please note that the grass area is SUSU or UoS selected so the incline and other such safety aspects can only be mitigated not avoided
	1
	5
	5
	In case of an emergency, call the emergency services on 999. 

If those with accessibility problems have not been able to exit, make the building manager and emergency services aware. 

Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy.

	Reputational Risk: 

For the club or society, as well as to SUSU and the University
	Incidents during club or society activity could pose a reputational risk to the club, Southampton University Students’ Union or Southampton University itself. 

This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name intro disrepute. 
	The club, SUSU or the University’s reputation
	2
	1
	2
	Ensuring all parts of this risk assessment are adhered to. 

Ensuring that any incidents involving public or others are recorded and addressed. 

Ensuring all members are reminded that they are representing the club/society, SUSU and the University in (usually) branded clothing. 


	1
	1
	1
	

	Financial Risk:

For the club or society, or potentially even SUSU if the club/soc finds itself in difficulty. 
	Club or society activity costing more than planned, weakening their financial position. 

Incidents with members of the public, participants, staff or members causing lawsuits and financial penalties.
	The club or society

Members subject to lawsuits

SUSU if required to assist.
	1
	1
	1
	Clubs and societies required to complete financial forecasting and budget for the year. 

All encouraged to review membership fees yearly to ensure they are able to comfortably cover costs. 

	1
	1
	1
	

	Legal Compliance:

Club or society activity going against set law. 

This includes breaches of the freedom of speech act
	Fines imposed upon the student group as well as SUSU. 

Jail sentences. 

Reputational risk to the student group, SUSU and the wider University 
	The club or society, committee and members, SUSU or the Wider University. 
	1
	1
	1
	All clubs and societies should ensure they are following set law at all times. If ever in doubt, they will contact the Activities team prior to the activity taking place. 

	1
	1
	1
	

	Medical Issues: 

Pre-existing and process for any that appear during 
	Illness, death 
	Members, committee 
	3
	5
	9
	All clubs and societies should have a process for if a medical issue occurs. 

All should know the location of the nearest first aider. Members do not need to disclose medical information to committee (GDPR), but all committee should know how to find a first aider and help quickly. 

If in a Southampton Sport space, contact reception. If in SUSU, contact reception. If no-one can be found, contact campus Security – 02380 59331




	1
	1
	1
	In an emergency, contact 999. 

Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy.

	Fundraising 
	
	
	
	
	
	
	
	
	
	

	Abuse of Members and Volunteers 
	Members of the public or students may act violently towards volunteers. Eg: Because they disagree with the cause.

	Volunteers and Participants 
	4
	3
	12
	No Volunteers are ever to be left alone. Always have at least 2 people at a stall or at an Event.
	2
	3
	6
	· Report to SUSU Duty manager and Complete a SUSU incident report
· Event organisers to call University Security if necessary.
· Emergency contact number for Campus Security:
Tel: +44 (0)23 8059 3311
· (Ext: 3311) 
· Building 32, University Road Highfield Campus.



	Venue/Location considerations
	Require certain licenses/sign off
	Organisers, Participates, SUSU
	1
	4
	4
	Ensure the venue has the relevant licenses required for your event ahead of time. 
Ensure your event has the required sign off by the venue's security teams.
Ensure proper booking process is followed for ALL bookings on and off campus. With no event going forward without Activities Approving the Risk Assessment. 
Booking has been approved in writing by SUSU (Mollie Lee)
	1
	2
	2
	· Event organisers to call University Security if necessary.
· Emergency contact number for Campus Security:
Tel: +44 (0)23 8059 3311
· (Ext: 3311) 
· Building 32, University Road Highfield Campus.



	Lone working
	Stolen goods, injury to individual 
	Volunteers
	3
	3
	9
	Ensure no one is left alone as a volunteer. All handovers as to happen at the turbine.
	3
	1
	3
	· Event organisers to call University Security if necessary.
· Emergency contact number for Campus Security:
Tel: +44 (0)23 8059 3311
· (Ext: 3311) 
· Building 32, University Road Highfield Campus.



	Adverse weather
	Injury, Illness, Slipping, Burns 
	Event organisers, event attendees,  
	4
	3
	12
	Lead organiser to check the weather is suitable for activities on the day (0600)

Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites

In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, hydrate 

If Cancellation is required ensure all relevant parties are contacted.
SUSU – subookings@soton.ac.uk
Uni – roombookings@soton.ac.uk 
And Mollie Lee

	4
	1
	4
	If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date

	Violent or offensive behaviour

	Members of the public may act violently towards participants. 
	Event organisers, event attendees,  
	2
	4
	8
	Do not engage with aggressive behaviour

Contact University Security (details can be found on the back of student ID cards)
Follow SUSU incident report policy




	1
	4
	4
	Call emergency services as required

	
Loss of valuables
	 
Lost items
	 
Students
 
	 
2
	 
2
	 
4
	 
All attendees will be warned prior to the activity to keep valuables secure and hidden, including ID and bank cards.

Advise participants to bring only what they need.
	 
1
	 
2
	 
2
	 
· Organisers or student to contact venue for any missing items
· If ID is lost, make an official report to the venue


	Uncontrolled turbine spinning
	Blunt force trauma or cutting injuries, damage to property, damage to turbine
	All
	1
	4
	4
	Turbine pole to have a breaking system fully engaged for the duration of the display

2.5mx2.5m exclusion zone to be set up with barriers around the turbine

Blades to be blunted
	1
	3
	3
	Weather assessment is to include a wind assessment to ensure the turbine will not suffer structural failure or slip free of the breaking system






	PART B – Action Plan

	Risk Assessment Action Plan

	Part no.
	Action to be taken, incl. Cost
	By whom
	Target date
	Review date
	Outcome at review date

	
	Committee to read and share SUSU Expect Respect Policy 
	Relevant committee members – president to ensure complete.
	14/09/2026
	15/09/2026
	

	
	Safety check to be conducted on the turbine
	Aaron Campbell
	14/09/2026
	N/A
	

	
	Weather to be checked 
	Aaron Campbell
	15/09/2026 (0600)
	N/A
	

	Responsible committee member signature: Aaron Campbell

	Responsible committee member signature: 

	Print name: 
[image: ]

	Date Insert date completed
	Print name: Sophie Ridgewell
	Date Insert date completed







Assessment Guidance 
	1. Eliminate
	Remove the hazard wherever possible which negates the need for further controls
	If this is not possible then explain why
	

	2. Substitute
	Replace the hazard with one less hazardous
	If not possible then explain why
	

	3. Physical controls
	Examples: enclosure, fume cupboard, glove box
	Likely to still require admin controls as well
	

	4. Admin controls
	Examples: training, supervision, signage
	
	

	5. Personal protection
	Examples: respirators, safety specs, gloves
	Last resort as it only protects the individual
	


	LIKELIHOOD
	5
	5
	10
	15
	20
	25

	
	4
	4
	8
	12
	16
	20

	
	3
	3
	6
	9
	12
	15

	
	2
	2
	4
	6
	8
	10

	
	1
	1
	2
	3
	4
	5

	
	1
	2
	3
	4
	5

	
	IMPACT


 
	Impact

	Health & Safety

	1
	Trivial - insignificant
	Very minor injuries e.g. slight bruising

	2
	Minor
	Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered.  

	3
	Moderate
	Injuries or illness e.g. strain or sprain requiring first aid or medical support.  

	4
	Major 
	Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks.

	5
	Severe – extremely significant
	Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work.  


Risk process
1. Identify the impact and likelihood using the tables above.
2. Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.
3. If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.
4. If the residual risk is green, additional controls are not necessary.  
5. If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable. 
6. If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.
7. Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.
8. The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.


	Likelihood

	1
	Rare e.g. 1 in 100,000 chance or higher

	2
	Unlikely e.g. 1 in 10,000 chance or higher

	3
	Possible e.g. 1 in 1,000 chance or higher

	4
	Likely e.g. 1 in 100 chance or higher

	5
	Very Likely e.g. 1 in 10 chance or higher
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