This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group. You will also need to complete a charity form linked here.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: Renee Everest | Email Address for Main Contact: re3g23@soton.ac.uk | Club or Society: Amnesty International | Contact Number: +447425318494 |
| 1B) Event Information: |  |  |  |
| Event Name: Refugee Awareness Trivia Night | Event Date: 10/10/2025 | Event Venue/Venues: 06/1081 | Total Attendees: 40 |
| Event Timings: | Set Up: 18:00 Event Start: 18:30 Event End: 20:30 Pack Down: 21:00 |  |  |
| Event Break down: (This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity.) | 18:00 – 18:20: Committees set up table and room layout, speech (SolidariTee), presentation and food 18:10 – 18:20: Designated committee member(s) to have Box Office scanner ready at the door 18:20: Doors open 18:20 – 18:30: Attendees arrive 18:30 – 18:45: Speech from SolidariTee Southampton student representatives 18:45 – 19:05: Joint presentation from Amnesty International, SolidariTee Southampton, Palestine Solidarity Society and Hands of Light committees 19:05 – 19:20: Speech from Hands of Light committee 19:20 – 19:45: Food break 19:45 – 20:15: Kahoot quiz 20:15 – 20:30: Attendees leave 20:30 – 21:00: Pack Down |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Boxoffice: You can set up Box-office tickets through your group's hub page for guidance on this click here: | ## Refugee Awareness Trivia Night | How Much Are your Tickets? And how many are available? | £3 x unlimited tickets £2 x unlimited tickets Maximum total of 40 tickets allowed only. |
| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | Joint charity fundraising trivia event with the Amnesty International society, the Hands of Light society, the Palestine Solidarity Society and student representative from SolidariTee Southampton. It is based on the theme of refugee awareness and consists of a speech from SolidariTee by their committee, a joint presentation by students from all committees and Kahoot quizzes on refugee awareness. Store-bought food will be available for attendees with potential allergens marked, and attendees will require a paid ticket for entry, the proceeds of which will go towards the SolidariTee charity. |  |  |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | Hosts: Points of contact for attendees; make final decisions on the running of the event; hosts for the quiz; hold critical logins for services such as Kahoot for the quiz and Canva for the presentation - Heads of each group: Amnesty International President, Hands of Light President, Palestine Solidarity Society President, SolidariTee Southampton team lead (Tamara) Volunteers: Help with setting up and packing down; ensuring order in the event; some to be involved in the speech, presentation and organising the quiz - All committee members from all three groups Food lead: Serve food to attendees; disclose all allergens; ensure food is not tampered with - All holders of Level 2 Food Hygiene and Safety certificates (Renee Everest) Doors: Confirm tickets before attendees enter, account for any attendees that choose to exit temporarily or leave the event altogether - Secretaries from all three groups |  |  |
| Tech Requirements (For a full list of what you can hire click here) | None |  |  |
| Facilities Requirements | None |  |  |
| Food Requirements (For full guidance on this click here) | Store-bought food (small baked goods and non-alcoholic drinks), served only by holders of Level 2 Food Hygiene and Safety certificates (Renee Everest) |  |  |
| Security & First Aid Requirements (Who are the qualified first aiders in the group should a medical emergency occur?) | None |  |  |
| Decorations that you are providing | None |  |  |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | Total Budget: £100 Ticket Income: £90 Food: £50 £40 Revenue (Proceeds of which will go to the designated charity through RAG) |  |  |
| 1C) Only Required If External Company/External Speaker On Site For Event |  |  |  |
| Business Name: | Business Contact Name: | Email Address: | Contact Number: |
| Arrival On Site: Departure time: | Companies Risk Assessment link: | Companies Insurance Link: | Companies Public Liability Information Link: |

If you are inviting a external company or individual on to campus for your event you will be required to submit this form to legalservices@soton.ac.uk at least 15 working days before the event. For more guidance on this please click here.

| PART 2 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| General Considerations |  |  |  |  |  |  |  |  |  |  |
| Slips, trips and falls | Physical injury | Event organisers and attendees | 2 | 3 | 6 | All boxes and equipment to be stored away from main meeting area, e.g. stored under tables. Any cables to be organised as best as possible, e.g. cable ties to be used if necessary. Floors to be kept clear and dry, and visual checks to be maintained throughout the meeting by organisers. Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. Report any trip hazards to facilities teams/venue staff asap. If cannot be removed, mark off with hazard signs. | 1 | 3 | 3 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible, ensuring duty manager/health and safety officers have been informed. Follow SUSU incident reporting guide |
| Fire | Smoke inhalation, burns. Risk of extreme harm. | All participants and organisers, any staff and spectators | 2 | 5 | 10 | Those leading the session must ensure they are aware of and fully understand the venue or location’s fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the participants the nearest emergency exit routes at the start of a session, and the importance of leaving calmly in case of an emergency. Avoid build-up of debris in the activity area. Consider accessibility requirements. | 1 | 5 | 5 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident reporting guide |
| Manual handling, including setting up of equipment. E.g. table and chairs | Bruising or broken bones from tripping over table and chairs | Meeting organisers and attendees | 2 | 3 | 6 | Follow manual handling guidelines. Ensure that at least 2 people carry tables or other bulky items. Setting up tables will be done by organisers. Work in teams when handling other large and bulky items. Request tools to support with the moving of heavy objects from SUSU Facilities/venue. E.g. hand truck, dolly, skates. Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable. | 1 | 3 | 3 | Seek assistance from facilities staff/venue staff if needed. Seek medical attention from SUSU/venue Reception if in need. Contact emergency services if needed. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident reporting guide |
| Overcrowding / Inadequate Meeting Space | Physical injury, distress, exclusion | Event organisers and attendees | 2 | 3 | 6 | Do not push/shove. If large crowds form, request barriers from SUSU facilities team or external venue to assist with crowd management. Committee checks on space, lighting, access, tech available, etc. Use ticketing system (SUSU Box Office) for regular sessions/meetings to avoid exceeding venue capacity. Ensure space meets needs of members e.g. considering location & accessibility of space (use AcessAble database to check accessibility information of venues). If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. Committee to consult members on needs and make reasonable adjustments where possible Provide remote meeting options for members where possible. | 1 | 3 | 3 | Seek medical attention if problem arises. Liaise with SUSU reception/Activities Team and UoS Room Booking team on available spaces for meetings. Postpone meetings where space cannot be found. Welfare Officer to complete WIDE training. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident reporting guide |
| Electronics | Eye strain, electric shock, burns, injury due to trip hazards, causing fire | Event organisers and attendees | 2 | 4 | 8 | Ensure regular breaks (ideally every 20mins) when using screens. Ensure screen is set up to avoid glare, is at eye height where possible. Ensure no liquids are placed near electrical equipment. Ensure all leads are secured with cable ties/mats, etc. For external venues, pre-check equipment and last PAT testing dates. | 1 | 4 | 4 | Request support and advice from SUSU IT/Tech teams e.g. via Activities Team. Seek medical attention as required. Follow SUSU incident reporting guide |
| Accessibility: Entrances and Exits to the chosen area. | Participants may be prevented from attending the activity due to a lack of considerations of accessibility needs and requirements. They could also be prevented from leaving the area quickly in an emergency if the correct infrastructure and considerations have not been made. | Participants, committee | 1 | 5 | 5 | All areas chosen for activity will have their suitability checked. If a closed activity for members, members will be consulted to ensure there are no accessibility requirements. If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. | 1 | 5 | 5 | In case of an emergency, call the emergency services on 999. If those with accessibility problems have not been able to exit, make the building manager and emergency services aware. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents causing reputational damage to the group, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name into disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring all members are reminded that they are representing the club/society, SUSU and the University, often in branded clothing. Members are reminded that they need to adhere to SUSU’s Code of Conduct. Consider risks at activities as well as digital presence (e.g. social media posts) | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Follow SUSU incident reporting guide |
| Medical emergency | Members may sustain injury /become unwell Pre-existing medical conditions, sickness, distress | Members | 1 | 5 | 5 | Advise participants to bring their personal medication if it might be required. Members/Committee to carry out first aid if necessary and only if qualified and confident to do so. Contact emergency services as required 111/999. Contact SUSU Reception/venue staff for first aid support. Members can be referred to The Student Hub (02380 599 599, studenthub@soton.ac.uk) in case of distress. | 1 | 4 | 4 | Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident reporting guide |
| Adverse weather | Hypo- or hyperthermia, illness, injury, slipping, burns | Event organisers, event attendees, | 3 | 4 | 12 | Lead organiser to check the weather are suitable for activities on the day. Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites. In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, and to hydrate (especially if drinking alcohol). | 2 | 2 | 4 | If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date. Contact emergency services if needed. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident reporting guide |
| Charity Fundraising |  |  |  |  |  |  |  |  |  |  |
| Fundraising for charity | Financial Loss, reputational damage | Members, participants, charity | 2 | 3 | 6 | Southampton RAG procedures will be followed: Charity Event form completed for each fundraising event, and RAG approval will be given. For bake sales: all food hygiene certificates and individual event risk assessment to be approved by the Activities Team. Request card machines from SUSU RAG if needed. Agree time for payment to the charity with SUSU Activities Team. Clearly state purpose of fundraising activity in event promotion and signage. Include the registered charity number if possible. | 1 | 3 | 3 | No cash to be accepted at all. No card machines to be left unattended. No volunteers to be left alone with the card machine. In the event of theft, committee members will: Highlight the incident to any community police officers in the area/report to 111. Follow SUSU incident reporting guide |
| Handling and storing card readers | - Theft - Individuals being mugged/robbed - Loss/misplacement leading to financial loss | Members and Participants | 3 | 4 | 12 | Southampton RAG procedures will be followed: - Charity Event form completed, and RAG approval will be given - All food hygiene certificates and event risk assessment to be approved by activities team - Sum-up Card machine to be requested and collected from SUSU reception. - Should not be storing money. ALL donations to be taken via Sumup Machine or Just Giving Pages | 2 | 3 | 6 | No Cash to Be Accepted at all. No card machines to be left unattended. No Volunteers to be left alone with the card machine In the event of theft committee members will: - Highlight the incident to any community police officers in the area/report to 111 - Report to SUSU Duty manager and Complete a SUSU incident report |
| Abuse of Members and Volunteers | Members of the public or students may act violently towards volunteers. Eg: Because they disagree with the cause. | Volunteers and Participants | 4 | 3 | 12 | No Volunteers are ever to be left alone. Always have at least 2 people at a stall or at an Event. | 2 | 3 | 6 | - Report to SUSU Duty manager and Complete a SUSU incident report - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Venue/Location considerations | Require certain licenses/sign off | Organisers, Participates, SUSU | 1 | 4 | 4 | Ensure the venue has the relevant licenses required for your event ahead of time. Ensure your event has the required sign off by the venue's security teams. Ensure proper booking process is followed for ALL bookings on and off campus. With no event going forward without Activities Approving the Risk Assessment. On campus - Ivvy Booking/uni room booking - Risk assessment - Contract Off campus - Risk assessment - Any bookings/contracts with external providers. | 1 | 2 | 2 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. - Follow SUSU incident reporting guide |
| Lone working | Stolen goods, injury to individual misuse of card reader. | Volunteers | 3 | 3 | 9 | Ensure no one is left alone as a volunteer at a fundraising event especially if using a Sum-up Card reader. Event led to brief volunteers to operate the card readers in pairs and briefed on how to handle situations surrounding these. | 3 | 1 | 3 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. - Follow SUSU incident reporting guide |
| Events involving Food | Allergies , food poisoning, choking | All | 3 | 5 | 15 | An additional event risk assessment needs to be carried out for gatherings involving members making and/or serving food. An additional event risk assessment needs to be carried out for events with hired catering services. Further guidance on food provision can be found here Only order/buy food at establishments with appropriate food hygiene (EHO) rating. Food to only be provided/eaten when other activities are stopped. Follow good food hygiene practices - no handling food when ill, tie back hair, wash hands regularly using warm water and soap, refrigerate necessary products. For store-bought items/snacks, keep packaging to hand for ingredient and allergen information. | 1 | 5 | 5 | SUSU food hygiene level 2 course available for completion- requests made to Activities Team. Call for first aid/emergency services a required . Report incidents via SUSU incident report procedure. |
| Members getting lost or separated. Members leaving an event/activity alone or without notifying others. | Getting lost, increased risk to personal safety. | Event organisers, event attendees, | 3 | 3 | 9 | If a person leaves without warning all efforts will be made to locate them. Stress however that attendees are responsible for their individual safety. Committee to supervise meetings/socials and attend each venue. Ideally, they will not drink to excess during the event. Venues chosen local and within a short distance from each other. Will look to select venues known to UoS students and within student areas. | 2 | 2 | 4 | Follow SUSU incident reporting guide Call emergency services as required. |
| Adverse weather | Injury, Illness, Slipping, Burns | Event organisers, event attendees, | 4 | 3 | 12 | Lead organiser to check the weather is suitable for activities on the day Seven days from completion of the risk assessment (13th—19th September 2025) Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, hydrate If Cancellation is required ensure all relevant parties are contacted. SUSU – subookings@soto.ac.uk Uni – roombookings@soton.ac.uk Or your external contacts. | 4 | 1 | 4 | If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date |
| Alcoholic/External Events |  |  |  |  |  |  |  |  |  |  |
| Alcohol consumption | Peer pressure/coercion, alcohol poisoning, spiking, increased risk to personal safety | Event organisers, event attendees | 2 | 4 | 8 | Alcohol not to be consumed in line with university regulations. Society to follow and share with members Code of conduct/SUSU Expect Respect policy. | 1 | 3 | 3 | For anyone who is too inebriated it will be suggested to them that they should return home rather than continue on the social. Taxis will be called if required (look at SUSU Safety Bus, Radio Taxis options). Follow SUSU incident reporting guide Call emergency services as required 111/999. Welfare Officer to complete WIDE training. |
| Allergies - food and drink | Allergic reactions to food and drink when out | Event organisers, event attendees, | 3 | 5 | 15 | Attendees responsible for own welfare I such instances- follow guidelines of venues. First aid requested from bar staff as required. | 1 | 5 | 5 | Call Emergency Services/alert bar staff |

| # PART 2B– Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # Risk Assessment Action Plan |  |  |  |  |  |  |  |
| # Part no. | # Action to be taken, incl. Cost | # By whom | # Target date |  | # Review date | # Outcome at review date |  |
| # 1 | # Complete a Charity Event form and send this to suactivties@soton.ac.uk | Secretary – president to ensure complete. | 20/09/25 |  |  |  |  |
| # 2 | # Set Up Just Giving/Fundraising Platform and/or book Sum-up Card Machines | Relevant committee members – president to ensure complete. | 20/09/25 |  |  |  |  |
| # 3 | Secondary review of area, equipment and conditions to ensure that the grounds are in the same appropriate condition they were in when we previously inspected, and that steps have been taken to make sure all equipment is safely set up. | Committee | 04/10/25 |  |  |  |  |
|  | # Committee to Read and share SUSU Expect respect policy | Secretary – president to ensure complete. | 10/10/25 |  |  |  |  |
| # Responsible committee member signature: |  |  |  |  | # Responsible committee member signature: |  |  |
| # Print name: Lonwabo Lazola Adonsi |  |  |  | # Date 02/10/25 | # Print name: Renee Everest |  | # Date 02/10/25 |

Assessment Guidance

| - Eliminate | Remove the hazard wherever possible which negates the need for further controls | If this is not possible then explain why |  |
| --- | --- | --- | --- |
| - Substitute | Replace the hazard with one less hazardous | If not possible then explain why |  |
| - Physical controls | Examples: enclosure, fume cupboard, glove box | Likely to still require admin controls as well |  |
| - Admin controls | Examples: training, supervision, signage |  |  |
| - Personal protection | Examples: respirators, safety specs, gloves | Last resort as it only protects the individual |  |

| LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 | 4 | 8 | 12 | 16 | 20 |
|  | 3 | 3 | 6 | 9 | 12 | 15 |
|  | 2 | 2 | 4 | 6 | 8 | 10 |
|  | 1 | 1 | 2 | 3 | 4 | 5 |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  |  | IMPACT |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

Risk process

- Identify the impact and likelihood using the tables above.

- Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.

- If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.

- If the residual risk is green, additional controls are not necessary.

- If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable.

- If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.

- Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.

- The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |