This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group. You will also need to complete a charity form linked here.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan- Please fill out all applicable fields |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: Amneet Sandhar | Email Address for Main Contact: as6g23@soton.ac.uk | Club or Society: Southampton Medical Student Equality, Diversity and Inclusion Committee | Contact Number: 07931014917 |
| 1B) Event Information: |  |  |  |
| Event Name: Talk on Inclusive Cancer Care | Event Date: 05/02/26 | Event Venue/Venues: The Bridge | Total Attendees: Currently unknown, <100 |
| Event Timings: | Set Up: None, organisers arrive 16:45 Event Start: 17:00 Event End: 20:30 Pack Down: None, leaving the bridge latest 21:00 |  |  |
| Event Break down: (This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity.) | Set Up: None, organisers arrive 16:45 Event Start: 17:00 - 17:00-19:00 Talk by Dr Alison Berner - 19:00-19:30 Break for refreshments - 19:30-20:30 Talk by Lee Dibben Event End: 20:30 Pack Down: None, leaving the bridge latest 21:00 |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Boxoffice: You can set up Box-office tickets through your group's hub page for guidance on this click here: | No | How Much Are your Tickets? And how many are available? | Not ticketed |
| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | Dr Alison Berner, dual trained adult gender identity doctor and oncologist, will be delivering a talk on Inclusive Cancer Care & Research for Trans and Gender Diverse People. She is also lead of UCATS, the U.K. cancer and transition service. We are also joined by Lee Dibben, who is a patient representative from OUTPatients, the UK’s only LGBTQIA+ cancer charity, to discuss the LGBTQIA+ cancer patient journey from GP through till palliative care. |  |  |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | President and Lead: Amneet Sandhar Support: Isabel Braithwaite Giving the talks: Dr Alison Berner and Lee Dibben |  |  |
| Tech Requirements (For a full list of what you can hire click here) | 2x microphones, speakers Already arranged through SUSU |  |  |
| Facilities Requirements | What is set up in the Bridge normally |  |  |
| Food Requirements (For full guidance on this click here) | None, we are providing squash and refreshments. Isabel Braithwaite has completed the Food Hygiene level 2 course offered by SUSU |  |  |
| Security & First Aid Requirements (Who are the qualified first aiders in the group should a medical emergency occur?) | Dr Alison Berner (medical doctor) Isabel Braithwaite and Amneet Sandhar have received NHS BLS and First aid training |  |  |
| Decorations that you are providing | None |  |  |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | 250 pounds provided by LGBTQIA+ history month SUSU Campaigns budget |  |  |
| 1C) Only Required If External Company/External Speaker On Site For Event |  |  |  |
| Business/External Speaker Name: Dr Alison Berner | Main Contact Name: Dr Alison Berner | Contact Email Address: alison.berner@nhs.net | Contact Number: N/A |
| Time of Arrival On Site: 16:30 Time of Departure: 20:45 | Companies Risk Assessment link: NHS England | Companies Insurance Link: NHS England | Companies Public Liability Information Link: NHS England |
| Business/External Speaker Name: Lee Dibben | Main Contact Name: Lee Dibben | Contact Email Address: lee@outpatients.org.uk | Contact Number: N/A |
| Time of Arrival On Site: 16:30 Time of Departure: 20:45 | Companies Risk Assessment link: OUTpatients UK | Companies Insurance Link: OUTpatients UK | Companies Public Liability Information Link: https://outpatients.org.uk/resources/ |

| PART 2A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Adverse Weather | - Injury - Illness - Slipping - Burns | All who attend | 4 | 3 | 12 | - Lead organiser to check the weather are suitable for activities on the day - Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites - In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, hydrate - Equipment such as gazebos can be requested from SUSU in advance of event. | 4 | 1 | 4 | - If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Slips, trips and falls | Physical injury | Event organisers and attendees | 2 | 4 | 8 | - All boxes and equipment to be stored away from main protest area, e.g. stored under tables - Floors to be kept clear and dry, and visual checks to be maintained throughout the event by organizers. - Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. - Report any trip hazards to facilities teams asap. If cannot be removed mark off with hazard signs | 1 | 4 | 4 | - Seek medical attention from SUSU Reception if in need - Contact facilities team via SUSU reception - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Setting up of Equipment. E.g. Table and chairs | Bruising or broken bones from tripping over table and chairs. | Event organisers and attendees | 2 | 3 | 6 | - Make stall operators aware of the potential risks, follow manual handling guidelines - Ensure that 2 people carry tables. - Setting up tables will be done by organisers. - Work in teams when handling other large and bulky items. | 1 | 3 | 3 | - Seek assistance if in need of extra help from facilities staff if needed - Seek medical attention from SUSU Reception if in need - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Overcrowding | Physical injury | Event organisers and attendees | 2 | 4 | 8 | - Do not push/shove - If large crowds form, barriers can be requested by SUSU facilities team (if available on the day) to assist with crowd management. - Book during quieter times when less activities taking place on Redbrick/book all available space - Inform other bookings on the Redbrick/in the area of the event | 1 | 4 | 4 | - Seek medical attention if problem arises - With support from a SUSU Activities coordinator Inform UoS security team of the event (– on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk) and liaise with them on need for security teams on the day - Security team may inform police of the event if required (e.g. marches) - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Disturbance to public, students and staff | Conflict, noise, crowds | Event organisers and attendees, general public | 2 | 2 | 4 | - Events planned for redbrick avoiding residential areas - UoS Security Teams informed of the event - Everybody will be encouraged to stay together as a group - shouting, chants, whistles etc. will be kept to a minimum around busy university buildings and residential areas - If applicable book space during quieter times when less activities taking place in local lecture theatres (lunch, Wednesday afternoons) | 1 | 2 | 2 | - With support from a SUSU Activities coordinator Inform UoS security team of the event -University Security 24 hours – on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk - Inform UoS/SUSU communications team of the event- can brief others via SUSSSED |
| Counter protest, discrimination against the demonstration | Assault, Violence or threatening/ Aggressive Behaviour | Event organisers and attendees | 2 | 4 | 8 | - Event planned for Highfield campus- a route well signposted and known for students - Leaders to advise all participants to not engage/respond to any protests, aggressive behaviour- if safe to do so will encourage group to move on and remove themselves from situation- The event will be ended and students advised to return to campus if this continues - Prior information about event and what to expect given out so participants know what to expect via Facebook/social media posts - Participants made aware they could join and leave the event at any time. - Ensure that people are aware that this is an open space for discussion to discourage protest. | 1 | 4 | 4 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. - Any incidents will be reported via UoS reporting tools - Contact emergency services if needed - Organisers will, following the event, share relevant information on support/signpost via social media channels etc. |
| Talks/debates - subjects that could be sensitive or personal to some members | The audience feels negative emotions around the topic or becomes distressed by images or events shown/discussed. | Members | 2 | 3 | 6 | Prior information about event and what to expect given out so participants know what to expect. Members made aware they could leave the event at any time. Members referred to enabling/signpost to support organisations (e.g. via presentation slide, or by speakers/committee members) SUSU reporting tool available | 1 | 3 | 3 | - Organisers will, following the event, share relevant information on support/signpost- Facebook/email/newsletter - Committee Wide Training - Seek guidance from activities/SUSU advice centre/UoS enabling team as required - committee WIDE training |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents during club or society activity could pose a reputational risk to the club, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name intro disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring that any incidents involving public or others are recorded and addressed. Ensuring all members are reminded that they are representing the club/society, SUSU and the University in (usually) branded clothing. Members are reminded that they need to adhere to SUSU’s Code of Conduct. Consider risks at activities as well as digital presence (e.g. social media posts) There will be a contract that will be uploaded signed by every dancer participating considering a full code on conduct regarding privacy and nudity during the event | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Follow SUSU incident reporting guide |
| Fire | Smoke inhalation, burns and more severe. Risk of extreme harm. | All participants and organisers/staff and spectators | 1 | 5 | 5 | Those leading the session must ensure they are aware of and fully understand the venue or locations fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the Volunteers/Event Staff the nearest emergency exit routes at the start of a session, and the importance of assisting others to leave calmly in case of an emergency. Consider accessibility requirements | 1 | 4 | 4 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy.SUSU incident reporting guide |

| # PART 2B – Action Plan |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # Risk Assessment Action Plan |  |  |  |  |  |  |  |  |
| # Part no. | # Action to be taken, incl. Cost | # By whom | # Target date |  | # Review date |  | # Outcome at review date |  |
| # 1 | # Event organisers to have submitted a SUSU groups External speaker form (if applicable) | # N/A | # N/A |  |  |  |  |  |
| 2 | Event organisers to ensure they have read and are familiar with the UoS Code of Practice on Freedom of speech and academic freedom. | # Isabel Braithwaite | # 29/01/26 |  |  |  |  |  |
| # 3 | UoS Security Team and legal services informed of event if applicable | # SUSU Activities Team | # Within 1 Week of submission of external speaker form. |  |  |  |  |  |
| 4 | Event purpose shared with participants-e.g. shared via social media channels, emails, ticketing platform | # Amneet Sandhar | # Within 1 Week of submission of external speaker form. |  |  |  |  |  |
| # 5 | # Events organiser to lead on an event briefing for volunteers/speakers/security staff | # Amneet Sandhar | # 3/02/26 |  |  |  |  |  |
| Responsible committee member signature: |  |  |  |  | Responsible committee member signature: |  |  |  |
| # Print name: Isabel Braithwaite |  |  |  | # Date: 28/01/26 |  | # Print name: Amneet Sandhar |  | # Date: 28.01.26 |

Assessment Guidance

| - Eliminate | Remove the hazard wherever possible which negates the need for further controls | If this is not possible then explain why |  |
| --- | --- | --- | --- |
| - Substitute | Replace the hazard with one less hazardous | If not possible then explain why |  |
| - Physical controls | Examples: enclosure, fume cupboard, glove box | Likely to still require admin controls as well |  |
| - Admin controls | Examples: training, supervision, signage |  |  |
| - Personal protection | Examples: respirators, safety specs, gloves | Last resort as it only protects the individual |  |

| LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 | 4 | 8 | 12 | 16 | 20 |
|  | 3 | 3 | 6 | 9 | 12 | 15 |
|  | 2 | 2 | 4 | 6 | 8 | 10 |
|  | 1 | 1 | 2 | 3 | 4 | 5 |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  |  | IMPACT |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

Risk process

- Identify the impact and likelihood using the tables above.

- Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.

- If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.

- If the residual risk is green, additional controls are not necessary.

- If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable.

- If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.

- Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.

- The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |