| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: William Jeffery | Email Address for Main Contact: wj1g21@soton.ac.uk | Club or Society: Ultimate Frisbee | Contact Number: 07484894409 |
| 1B) Event Information: |  |  |  |
| Event Name: Quiz and Cake Sale | Event Date: 19/11/25 | Event Venue/Venues: The Bridge | Total Attendees: 30 |
| Event Timings: | Set Up: 19:00 Event Start: 19:20 Event End: 21:40 Pack Down: 21:50 |  |  |
| Event Break down: | Tuesday 18/11/25: 14:00: Collect SumUp Machine Wednesday 19/11/25: 19:00: Set up electronic systems i.e. prepare speaker and projector systems. 19:05: Ensure all allergen information is displayed. 19:10: Take participation fee from attendees using SumUp machine. 19:30-21:40: Complete quiz, with regular 15 minute intermissions for cake. 21:50: Pack down. Thursday 20/11/25: 11:00: Return SumUp machine. |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Boxoffice: You can set up Box-office tickets through your group's hub page for guidance on this click here: | No | How Much Are your Tickets? And how many are available? | Tickets not required on Boxoffice. Event Directors will collect a £3.00 entry fee at the event. £1.00 per cake set to unlimited. |
| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | Pub-quiz style event. After rounds a short intermission will allow attendees to purchase home-made cakes. |  |  |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | Will Jeffery – Event director Benedict O’Connell – Quiz master Tate Hopkins – Quiz master |  |  |
| Tech Requirements (For a full list of what you can hire click here) | Will only require access to equipment that is already present in The Bridge: Projector Microphone TV Speaker system |  |  |
| Facilities Requirements | Nothing additional – the normal ‘The Bridge’ set up will be fine. |  |  |
| Food Requirements (For full guidance on this click here) | Baked items prepared by students who have completed the food hygiene training. |  |  |
| Security & First Aid Requirements (Who are the qualified first aiders in the group should a medical emergency occur?) | No qualified first aiders. |  |  |
| Decorations that you are providing | N/A |  |  |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | £30 Budget Break Down: £30 – Single use of speed quizzing website. |  |  |

| PART A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| General Considerations |  |  |  |  |  |  |  |  |  |  |
| Slips, trips and falls | Soft tissue injury e.g., sprain, bruising. Potential broken ankle or other breaks i.e. wrists etc. Links directly to weather and ground surfaces. | All participants and organisers/staff and spectators | 2 | 3 | 6 | Check venue conditions for holes, lumps, and other obstacles. | 1 | 3 | 3 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Fire | Smoke inhalation, burns and more severe. Risk of extreme harm. | All participants and organisers/staff and spectators | 1 | 5 | 5 | Those leading the session must ensure they are aware of and fully understand the venue or locations fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the Volunteers/Event Staff the nearest emergency exit routes at the start of a session, and the importance of assisting others to leave calmly in case of an emergency. Consider accessibility requirements | 1 | 4 | 4 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Setting up/moving or chairs/tables/other objects in the area. | Bruising or broken bones from tripping over table and chairs. | Meeting organisers and attendees | 2 | 3 | 6 | Make Event Volunteers aware of the potential risks, follow manual handling guidelines Ensure that at least 2 people carry tables and large objects. Setting up tables will be done by organisers. Work in teams when handling other large and bulky items. Request tools to support with move of heavy objects- SUSU Facilities/venue. E.g., hand truck, dolly, skates Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable. | 1 | 3 | 3 | Seek assistance if in need of extra help from facilities staff/venue staff if needed Seek medical attention from SUSU Reception if in need Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Overcrowding | Physical injury | Event organisers and attendees | 1 | 3 | 3 | Do not push/shove If large crowds form, barriers can be requested by SUSU facilities team (if available on the day) to assist with crowd management. Book during quieter times when less activities taking place on Redbrick/book all available space Inform other bookings on the Redbrick/in the area of the event | 1 | 3 | 3 | Seek medical attention if problem arises With support from a SUSU Activities coordinator Inform UoS security team of the event (– on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk) and liaise with them on need for security teams on the day Security team may inform police of the event if required (e.g. marches) |
| Electronics | Risk of eye strain, injury, electric shock | Committee and attendees | 2 | 4 | 8 | Ensure regular breaks (ideally every 20mins) when using screens Ensure screen is set up to avoid glare, is at eye height where possible Ensure no liquids are placed near electrical equipment Ensure all leads are secured with cable ties/mats etc | 1 | 4 | 4 | Request support and advice from SUSU IT/Tech teams e.g. via activities team For external venues pre-check equipment and last PAT testing dates Seek medical attention as required |
| Accessibility: Entrances and Exits to the chosen area. | Participants may be prevented from attending the activity due to a lack of considerations of accessibility needs and requirements. They could also be prevented from leaving the area quickly in an emergency if the correct infrastructure and considerations have not been made. | Participants, committee | 1 | 5 | 5 | All areas chosen for activity will have their suitability checked. If a closed activity for members, members will be consulted to ensure there are no accessibility requirements. If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. | 1 | 5 | 5 | In case of an emergency, call the emergency services on 999. If those with accessibility problems have not been able to exit, make the building manager and emergency services aware. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents during club or society activity could pose a reputational risk to the club, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name intro disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring that any incidents involving public or others are recorded and addressed. Ensuring all members are reminded that they are representing the club/society, SUSU and the University in (usually) branded clothing. | 1 | 1 | 1 |  |
| Financial Risk: For the club or society, or potentially even SUSU if the club/soc finds itself in difficulty. | Club or society activity costing more than planned, weakening their financial position. Incidents with members of the public, participants, staff or members causing lawsuits and financial penalties. | The club or society Members subject to lawsuits SUSU if required to assist. | 1 | 1 | 1 | Clubs and societies required to complete financial forecasting and budget for the year. All encouraged to review membership fees yearly to ensure they are able to comfortably cover costs. SUSU can offer clubs and societies loans – these will need to be agreed and a payment schedule decided upon. Clubs and societies that have to rely on a loan will be subject to development plans to ensure their future is protected. | 1 | 1 | 1 |  |
| Legal Compliance: Club or society activity going against set law. This includes breaches of the freedom of speech act | Fines imposed upon the student group as well as SUSU. Jail sentences. Reputational risk to the student group, SUSU and the wider University | The club or society, committee and members, SUSU or the Wider University. | 1 | 1 | 1 | All clubs and societies should ensure they are following set law at all times. If ever in doubt, they will contact the Activities team prior to the activity taking place. All who wish to bring in an external speaker must follow due process, available here This will be looked over by the University Legal Services team, and may require security being consulted and an extra risk assessment being submitted. | 1 | 1 | 1 |  |
| Medical Issues: Pre-existing and process for any that appear during | Illness, death | Members, committee | 3 | 5 | 9 | All clubs and societies should have a process for if a medical issue occurs. All should know the location of the nearest first aider. Members do not need to disclose medical information to committee (GDPR), but all committee should know how to find a first aider and help quickly. If in a Southampton Sport space, contact reception. If in SUSU, contact reception. If no-one can be found, contact campus Security – 02380 59331 | 1 | 1 | 1 | In an emergency, contact 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Charity Fundraising |  |  |  |  |  |  |  |  |  |  |
| Handling and storing card readers | - Theft - Individuals being mugged/robbed - Loss/misplacement leading to financial loss | Members and Participants | 3 | 4 | 12 | Southampton RAG procedures will be followed: - Charity Event form completed, and RAG approval will be given - All food hygiene certificates and event risk assessment to be approved by activities team - Sum-up Card machine to be requested and collected from SUSU reception. - Should not be storing money all donations to be taken via Sumup Machine or Just Giving Pages | 2 | 3 | 6 | No Cash to Be Accepted at all. No card machines to be left unattended. No Volunteers to be left alone with the card machine In the event of theft committee members will: - Highlight the incident to any community police officers in the area/report to 111 - Report to SUSU Duty manager and Complete a SUSU incident report |
| Abuse of Members and Volunteers | Members of the public or students may act violently towards volunteers. Eg: Because they disagree with the cause. | Volunteers and Participants | 4 | 3 | 12 | No Volunteers are ever to be left alone. Always have at least 2 people at a stall or at an Event. | 2 | 3 | 6 | - Report to SUSU Duty manager and Complete a SUSU incident report - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Venue/Location considerations | Require certain licenses/sign off | Organisers, Participates, SUSU | 1 | 4 | 4 | Ensure the venue has the relevant licenses required for your event ahead of time. Ensure your event has the required sign off by the venue's security teams. Ensure proper booking process is followed for ALL bookings on and off campus. With no event going forward without Activities Approving the Risk Assessment. On campus - Ivvy Booking/uni room booking - Risk assessment - Contract Off campus - Risk assessment - Any bookings/contracts with external providers. | 1 | 2 | 2 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Lone working | Stolen goods, injury to individual misuse of card reader. | Volunteers | 3 | 3 | 9 | Ensure no one is left alone as a volunteer at a fundraising event especially if using a Sum-up Card reader. Event led to brief volunteers to operate the card readers in pairs and briefed on how to handle situations surrounding these. | 3 | 1 | 3 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Food |  |  |  |  |  |  |  |  |  |  |
| Serving and preparation of food | - Allergies - Food poisoning - Choking | All | 3 | 5 | 15 | - Homemade items to be avoided by those with allergies - precautions should be made by those with appropriate food hygiene training (Level 2 +) - Only order/buy food at establishments with appropriate food hygiene rating - Food to only be provided/eaten when other activities are stopped - Follow good food hygiene practices- no handling food when ill, tie back hair, wash hands and equipment regularly using warm water and cleaning products, refrigerate necessary products | 1 | 5 | 5 | SUSU food hygiene level 2 course available for completion- requests made to activities team Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Contamination of food through food preparation. | Illness, Food poisoning, Allergy. | All | 2 | 3 | 6 | - Ensure all food is prepared in advance and done in a clean and hygienic environment. In line with the level 2 food hygiene training. - Ensure all ingredients used when making items are withing there used by or best before dates. - Ensure all frozen food is thoroughly defrosted before use. - Endeavour to not cross contaminate foo such as nuts and let customers know if cross contamination is a possibility. | 1 | 3 | 3 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Storage and Display of Food | Illness, Food poisoning, Allergy. | All | 2 | 3 | 6 | Keep any products containing fresh produce in the fridge. Do not leave any food out for longer than 4 hours. - Store all products in a clean sealable container away from raw foods. - Transport cakes in a clean sealable container. | 1 | 3 | 3 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Food Allergies and Dietary requirements | Illness, Allergic reaction | Customers | 3 | 5 | 15 | - Where possible remove common allergens form ingredients. allergen-chart-1.docx (live.com) Lists all 14 of the core allergens. - Ensure each cake is labelled with its name and list of ingredients. - Have a list available of all ingredients for any products sold at the stall. - Always use recipes from reputable sources. - Make sure to keep any packaging. | 1 | 5 | 5 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. - For more information on allergens: Providing food at community and charity events ¦ Food Standards Agency Follow SUSU incident report policy |
| Stock/Food Falling | Physical Injury, Illness, Food poisoning | All Participants | 3 | 2 | 6 | - Enusre all stock is stored correctly and not stacked to high. - If any products fall that these are not sold and disposed of in food waste. | 1 | 2 | 2 | - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. - SUSU food hygiene level 2 course available for completion- requests made to activities team Follow SUSU incident report policy |
| Use of Knives for Cutting Food | Cuts and injuries | Volunteers and stall operators | 2 | 2 | 4 | - Make stall operators aware of the potential risks. - Where possible use wooden cutlery. - Knife not to be left unattended and stored away safely when not in use. - Ensure the Knife is suitable for the task and the food you are cutting. - When carrying the Knife ensure the blade is pointing down. |  |  |  | - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. Follow SUSU incident report policy |

| # PART B – Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # Risk Assessment Action Plan |  |  |  |  |  |  |  |
| # Part no. | # Action to be taken, incl. Cost | # By whom | # Target date |  | # Review date | # Outcome at review date |  |
|  | Committee to send copies of all food hygiene training certificates to suactivities@soton.ac.uk | William Jeffery | 12/11/25 |  | # 14/11/25 |  |  |
|  | Committee members to create and display lists of ingredients (with allergens written in bold) at the stall | Reuben Fisher | 17/11/25 |  | # 18/11/25 |  |  |
|  | Committee to read and share SUSU Expect Respect Policy | Reuben Fisher | 17/11/25 |  | # 18/11/25 |  |  |
|  | Complete a Charity Event form and send this to suactivties@soton.ac.uk | William Jeffery | 10/11/25 |  | # 14/11/25 |  |  |
|  | Set Up Just Giving/Fundraising Platform and/or book Sum-up Card Machines | William Jeffery | 10/11/25 |  | # 14/11/25 |  |  |
| # Responsible committee member signature: |  |  |  |  | # Responsible committee member signature: |  |  |
| # Print name: William Jeffery |  |  |  | # Date 10/11/25 | # Print name: Reuben Fisher |  | # Date 10/11/25 |