This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group. You will also need to complete a charity form linked here.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: Theo Brown | Email Address for Main Contact: tb12g23@soton.ac.uk | Club or Society: SURGE Radio | Contact Number: 07392 090390 |
| 1B) Event Information: |  |  |  |
| Event Name: SURGE Turns 50: 24hr Broadcast | Event Date: 05/06/2025 12pm – 06/06/2025 12pm | Event Venue/Venues: Redbrick and Surge Studios (B42/2606) | Total Attendees: TBA (Radio Studio has a capacity of 5 as per General RA) |
| Event Timings: | General Set Up: 11:00 for the redbrick stream Event Start: 12:00 – 13:00 Redbrick stream Event End: 12:00 on the 6th Pack Down by 1pm on the 6th |  |  |
| Event Break down: (This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity.) | See separate document (Will be sent to Chelsea once finalised) |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Box office: You can set up Box-office tickets through your group's hub page for guidance on this click here: | No | How Much Are your Tickets? And how many are available? | N/A |
| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | 24hr radio broadcast starting with a one-hour intro in the redbrick, followed with the rest of the event being held in the studio. This will involve Surge Alumni as well as current hosts. All in aid for future funds for surge radio. A committee member will be on-site throughout the event |  |  |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | See rota |  |  |
| Tech Requirements (For a full list of what you can hire click here) | REDBRICK: Tent Sofas And Power REST OF THE EVENT: N/A |  |  |
| Facilities Requirements | Access to toilets, access to the studio, unlocking of the SU building. |  |  |
| Food Requirements (For full guidance on this click here) | Access to hot water/kettle Mini Fridge Fans |  |  |
| Security & First Aid Requirements (Who are the qualified first aiders in the group should a medical emergency occur?) | Theo Brown |  |  |
| Decorations that you are providing | What is in our Studio |  |  |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | £216 (Security Costs) |  |  |

| PART 2 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| General Considerations |  |  |  |  |  |  |  |  |  |  |
| Slips, trips and falls | Soft tissue injury e.g., sprain, bruising. Potential broken ankle or other breaks i.e. wrists etc. Links directly to weather and ground surfaces. | All participants and organisers/staff and spectators | 2 | 3 | 6 | Check venue conditions for holes, lumps, and other obstacles. | 1 | 3 | 3 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. SUSU incident reporting guide |
| Fire | Smoke inhalation, burns and more severe. Risk of extreme harm. | All participants and organisers/staff and spectators | 1 | 5 | 5 | Those leading the session must ensure they are aware of and fully understand the venue or locations fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the Volunteers/Event Staff the nearest emergency exit routes at the start of a session, and the importance of assisting others to leave calmly in case of an emergency. Consider accessibility requirements | 1 | 4 | 4 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. SUSU incident reporting guide |
| Setting up/moving or chairs/tables/other objects in the area. | Bruising or broken bones from tripping over table and chairs. | Meeting organisers and attendees | 2 | 3 | 6 | Make Event Volunteers aware of the potential risks, follow manual handling guidelines Ensure that at least 2 people carry tables and large objects. Setting up tables will be done by organisers. Work in teams when handling other large and bulky items. Request tools to support with move of heavy objects- SUSU Facilities/venue. E.g., hand truck, dolly, skates Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable. | 1 | 3 | 3 | Seek assistance if in need of extra help from facilities staff/venue staff if needed Seek medical attention from SUSU Reception if in need Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Electronics | Risk of injury and electric shock | Committee and attendees | 2 | 4 | 8 | Ensure no liquids are placed near electrical equipment Ensure all leads are secured with cable ties/mats etc | 1 | 4 | 4 | Request support and advice from SUSU IT/Tech teams e.g. via activities team For external venues pre-check equipment and last PAT testing dates Seek medical attention as required. |
| Accessibility: Entrances and Exits to the chosen area. | Participants may be prevented from attending the activity due to a lack of considerations of accessibility needs and requirements. They could also be prevented from leaving the area quickly in an emergency if the correct infrastructure and considerations have not been made. | Participants, committee | 1 | 5 | 5 | All areas chosen for activity will have their suitability checked. SUSU Building has step-free access to the studio with ramp. Studio will have routes clear for attendee with walker, so they can access the studio | 1 | 5 | 5 | In case of an emergency, call the emergency services on 999. If those with accessibility problems have not been able to exit, make the building manager and emergency services aware. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents during club or society activity could pose a reputational risk to the club, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name intro disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring that any incidents involving public or others are recorded and addressed. Ofcom Rules will be enforced throughout the broadcast. | 1 | 1 | 1 |  |
| Financial Risk: For the club or society, or potentially even SUSU if the club/soc finds itself in difficulty. | Club or society activity costing more than planned, weakening their financial position. Incidents with members of the public, participants, staff or members causing lawsuits and financial penalties. | The club or society Members subject to lawsuits SUSU if required to assist. | 1 | 1 | 1 | Surge has £1,000 emergency fund if costs do overrun. Event is planned with minimal spend so likelihood of the emergency fund being used is low. SUSU can offer clubs and societies loans – these will need to be agreed and a payment schedule decided upon. Clubs and societies that have to rely on a loan will be subject to development plans to ensure their future is protected. | 1 | 1 | 1 |  |
| Legal Compliance: Club or society activity going against set law. This includes breaches of the freedom of speech act | Fines imposed upon the student group as well as SUSU. Jail sentences. Reputational risk to the student group, SUSU and the wider University | The club or society, committee and members, SUSU or the Wider University. | 1 | 1 | 1 | All clubs and societies should ensure they are following set law at all times. If ever in doubt, they will contact the Activities team prior to the activity taking place. All who wish to bring in an external speaker must follow due process, available here This will be looked over by the University Legal Services team, and may require security being consulted and an extra risk assessment being submitted. | 1 | 1 | 1 | Check with the venue if a 24 hour licence is required for this event |
| Medical Issues: Pre-existing and process for any that appear during | Illness, death | Members, committee | 3 | 5 | 9 | All clubs and societies should have a process for if a medical issue occurs. All should know the location of the nearest first aider. Members do not need to disclose medical information to committee (GDPR), but all committee should know how to find a first aider and help quickly. If in a Southampton Sport space, contact reception. If in SUSU, contact reception. If no-one can be found, contact campus Security – 02380 59331 | 1 | 1 | 1 | In an emergency, contact 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy |
| Charity Fundraising |  |  |  |  |  |  |  |  |  |  |
| Handling and Storing Money – | Theft, Individuals being mugged. | Members and Participants | 3 | 4 | 12 | As Fundraising for own Society/Club No Card Machine will be present. All fundraising to be completed via QR code to A GoFundMe or Similar Platform. | 2 | 3 | 6 | No Cash to be accepted at all. Clubs and Societies are not to use Personal Card machines to take payments. |
| Venue/Location considerations | Require certain licenses/sign off | Organisers, Participates, SUSU | 1 | 4 | 4 | Ensure the venue has the relevant licenses required for your event ahead of time. Ensure your event has the required sign off by the venue's security teams. Ensure proper booking process is followed for ALL bookings on and off campus. With no event going forward without Activities Approving the Risk Assessment. On campus - Ivvy Booking/uni room booking - Risk assessment - Contract Off campus - Risk assessment - Any bookings/contracts with external providers. | 1 | 2 | 2 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. Follow SUSU incident report policy |
| Lone working | Stolen goods, injury to individual misuse of card reader. | Volunteers | 3 | 3 | 9 | Ensure no one is left alone as a volunteer at a fundraising event especially if using a Sum-up Card reader. Event led to brief volunteers to operate the card readers in pairs and briefed on how to handle situations surrounding these. | 3 | 1 | 3 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. Follow SUSU incident report policy |
| Adverse weather | Injury, Illness, Slipping, Burns | Event organisers, event attendees, | 4 | 3 | 12 | Lead organiser to check the weather is suitable for activities on the day Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, hydrate Fans and water will be provided in the studio. Wet weather will cause the redbrick event to be moved inside the studio If Cancellation is required ensure all relevant parties are contacted. SUSU – subookings@soto.ac.uk Uni – roombookings@soton.ac.uk Or your external contacts. | 4 | 1 | 4 | If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date |
| 24 hour Events |  |  |  |  |  |  |  |  |  |  |
| Fatigue (Including dehydration and hunger) | Participants and volunteers on the day may become tired if they have not properly slept, eaten or drank. | Event Attendees and Organisers | 3 | 3 | 9 | - All participants and volunteers have been advised to properly eat and drink prior and during their go. - Volunteers have also been encouraged to bring food and drink with them to consume during their go. - Access to bottled water or a Water Fountain/Tap throughout the event. - All volunteer shifts won’t be longer than 12 hours | 2 | 2 | 4 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Use of Toilets overnight | Event attendees and organisers not having any facilities to use. | Event attendees and Volunteers | 2 | 2 | 4 | - Requested for toilet facilities to be left open for duration of event. - Pre event conversations had with university security team. - Facilities/security team to leave entrance open for toilet use. | 1 | 2 | 2 | - If building is not left open contact university security - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. Follow SUSU incident report policy |
| Spilling hot/Boling temperature water | Rash, redness or burns on the affected area. | Volunteers (user) and those in the vicinity | 2 | 2 | 4 | - Only committee/volunteers to use the kettle. - Kettle to be placed in a safe location away from activity and participants to lower chance of being knocked over. - Ensure distance from activity and those taking part in activity | 1 | 3 | 3 | - If building is not left open contact university security - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 (Ext: 3311) Building 32, University Road Highfield Campus. Follow SUSU incident report policy |
| Risk to Safety and public disturbance at night | Conflict, Threating behaviour, assault | Participants and event organisers | 2 | 2 | 4 | - University security aware of the event prior to the day. - SUSU Duty manager informed of the event. - Everyone to be encouraged to stay in a minimum of pairs at all times if they need to leave. Otherwise, will be encouraged to always stay with the group. | 1 | 2 | 22 | - If building is not left open contact university security - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 (Ext: 3311) Building 32, University Road Highfield Campus. Follow SUSU incident report policy |
| REDBRICK PORTION OF THE EVENT |  |  |  |  |  |  |  |  |  |  |
| Rain | Slipping Damage to Equipment | Event organisers Attendees | 4 | 1 | 4 | - Ensure there are no weather warnings for the day of the event - Committee to check location and ensure it is still suitable - Do not allow running in the vicinity | 2 | 1 | 4 | - If there are weather warnings or rain is too heavy or too constant, postpone the event - Any incidents to be logged through the incident report form |
| Wind | Damage to equipment Equipment blowing away, causing damage to property or people | Event organisers Attendees Those in the vicinity | 3 | 4 | 12 | - Check if wind is expected to reach >30mph on the day of the event - Move starting stream inside if conditions are poor - Committee to check location and ensure it is still suitable | 2 | 4 | 8 | - If there is moderate wind, set up near a building that is downwind to ensure minimum distance of potential disruption - Contact emergency services if needed |

| # PART 2B – Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # Risk Assessment Action Plan |  |  |  |  |  |  |  |
| # Part no. | # Action to be taken, incl. Cost | # By whom | # Target date |  | # Review date | # Outcome at review date |  |
| # 1 | # Committee member to check weather and make a call if event is okay to go ahead | Theo Brown | Wednesday 3rd June 2026 |  | # 6th June 2026 |  |  |
| # 2 | # Committee member to ensure all supplies are there, eg: access to hot water, toliets etc | # BEFORE: Theo Brown # And # Committee members on duty throughout the event | # 4th June 2026 |  | # 6th June 2026 |  |  |
| # 3 | Committee to Read and share SUSU Expect respect policy | Relevant committee members – president to ensure complete. | 5th June 2026 |  | # 6th June 2026 |  |  |
| # 4 | Set Up Just Giving/Fundraising Platform and/or book Sum-up Card Machines | Relevant committee members – president to ensure complete. | 31st May 2026 |  | # 4th June 2026 |  |  |
| # 5 | # Check if a 24 hour liscenece is required (this is usually required for all indoor 24 hour events) | Relevant committee members – president to ensure complete. | 31st May 2026 |  | # 5th June 2026 |  |  |
| # 6 | # Confirm and list participants to SUSU | Theo Brown | 31st May 2026 |  | # 5th June 2026 |  |  |
| # Responsible committee member signature: |  |  |  |  | # Responsible committee member signature: # Howie Dickinson |  |  |
| # Print Name: Theo Brown |  |  |  | # Date 12/04/2026 | # Print name: Howie Dickinson |  | # Date 12/04/2026 |

Assessment Guidance

| - Eliminate | Remove the hazard wherever possible which negates the need for further controls | If this is not possible then explain why |  |
| --- | --- | --- | --- |
| - Substitute | Replace the hazard with one less hazardous | If not possible then explain why |  |
| - Physical controls | Examples: enclosure, fume cupboard, glove box | Likely to still require admin controls as well |  |
| - Admin controls | Examples: training, supervision, signage |  |  |
| - Personal protection | Examples: respirators, safety specs, gloves | Last resort as it only protects the individual |  |

| LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 | 4 | 8 | 12 | 16 | 20 |
|  | 3 | 3 | 6 | 9 | 12 | 15 |
|  | 2 | 2 | 4 | 6 | 8 | 10 |
|  | 1 | 1 | 2 | 3 | 4 | 5 |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  |  | IMPACT |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

Risk process

- Identify the impact and likelihood using the tables above.

- Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.

- If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.

- If the residual risk is green, additional controls are not necessary.

- If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable.

- If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.

- Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.

- The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |