This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group. You will also need to complete a charity form linked here.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan- Please fill out all applicable fields |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: Lily Hemsley | Email Address for Main Contact: Lh1g25@soton.ac.uk | Club or Society: Student Scout and Guide Organisation (SSAGO) | Contact Number: 07517403538 |
| 1B) Event Information: |  |  |  |
| Event Name: SSAGO Volunteering Talk | Event Date: 29/09/2026 | Event Venue/Venues: Highfield Campus 28/1019 and 28/1021 | Total Attendees: Roughly 20 students and 6 guests |
| Event Timings: | Set Up: 7pm Event Start: 7:30pm Event End: 8:45pm Pack Down: 8:45-9pm |  |  |
| Event Break down: (This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity.) | Volunteers arrive from 7:20pm in room 1019. Talk starts at 7:30pm in 1019 with a quick introduction and benefits of volunteering with Scouts/ Guides. Introduction to guests, who will have stalls set up in room 1021. Students can mingle and speak to Scout and Guide representatives in 1021. Students leave by 8:45 and everything is packed down by 9pm. |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Boxoffice: You can set up Box-office tickets through your group's hub page for guidance on this click here: | No | How Much Are your Tickets? And how many are available? | N/A |

| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | Talk run by SSAGO Committee to recruit our members (and anyone else interested) to become volunteers at local Scouting and Guiding units. Aims to match members to opportunities and also publicise opportunities in the area. We will invite 3 Scout and 3 Guide representatives from the area to speak about their opportunities – this will likely be someone from Network and someone from Inspire (sections for older members in Scouting/ Guiding) and two representatives for volunteering opportunities in each of Girlguiding and Scouting. All guests will have valid Scout or Guide DBS checks. |
| --- | --- |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | Lily Hemsley (Guide Liaison) – main organiser Daniel Isard (Scout Liaison) – main organiser Matthew Pownall (Chair) Claire Zumpe (Quartermaster) Bryony Gardener (Secretary) Oliver Stubley (Treasurer) Molly Clarke (Social Sec) Lottie Ellard (Social Sec) Jasmine Currey (Welfare) Ben Lewis (Welfare) |
| Tech Requirements (For a full list of what you can hire click here) | No specialist equipment – will use projectors in the room (if there are some) and our laptops |
| Facilities Requirements | 25x chairs (will find in the building) |
| Food Requirements (For full guidance on this click here) | None |
| Security & First Aid Requirements (Who are the qualified first aiders in the group should a medical emergency occur?) | Lily, Daniel, Matthew, Claire, and Oliver are all first-aid qualified through Scouting/ Guiding Daniel will be first-aider |

| Decorations that you are providing | Guest speakers will bring their own resources for the stalls |  |  |
| --- | --- | --- | --- |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | None |  |  |
| 1C) Only Required If External Company/External Speaker On Site For Event |  |  |  |
| Business/External Speaker Name: Southampton Scouting Southampton Girlguiding | Main Contact Name: Joseph Butterworth Anna Remnant | Contact Email Address: joseph.butterworth@southamptoncitys couts.org.uk southamptoncentraldivisioncomm@gm ail.com | Contact Number: 07710 831503 07815 906902 |
| Time of Arrival On Site: 7pm Time of Departure: 9pm | Companies Risk Assessment link: None as attendees are voluntary individuals | Companies Insurance Link: https://www.unityinsuranceservices.co .uk/sites/default/files/TSA_TWIMC_PL_ 26-27.pdf https://www.girlguiding.org.uk/globala ssets/docs-and-resources/finance-insurance-and-property/girlguiding-public-liability-insurance-2026.pdf | Companies Public Liability Information Link: https://www.unityinsuranceservices.co .uk/scout-insurance/public-liability-insurance https://www.girlguiding.org.uk/inform ation-for-volunteers/running-your-unit/finance-insurance-and-property/insurance/public-liability- insurance/ |

## If you are inviting an external speaker for your event, you will be required to submit this form at least three weeks before the event. For more guidance on this please click here.

| PART 2A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Adverse Weather | - Injury - Illness - Slipping - Burns | All who attend | 4 | 3 | 12 | - Lead organiser to check the weather is suitable for activities on the day - Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites - In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, hydrate - Equipment such as gazebos can be requested from SUSU in advance of event. | 4 | 1 | 4 | - If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |

| PART 2A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Slips, trips and falls | Physical injury | Event organisers and attendees | 2 | 4 | 8 | - All boxes and equipment to be stored away from main protest area, e.g. stored under tables - Floors to be kept clear and dry, and visual checks to be maintained throughout the event by organizers. - Extra vigilance will be paid to make sure that any spilled objects are cleaned up quickly and efficiently in the area. - Report any trip hazards to facilities teams asap. If cannot be removed mark off with hazard signs | 1 | 4 | 4 | - Seek medical attention from SUSU Reception if in need - Contact facilities team via SUSU reception - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |

| PART 2A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Setting up of Equipment. E.g. Table and chairs | Bruising or broken bones from tripping over table and chairs. | Event organisers and attendees | 2 | 3 | 6 | - Make stall operators aware of the potential risks, follow manual handling guidelines - Ensure that 2 people carry tables. - Setting up tables will be done by organisers. - Work in teams when handling other large and bulky items. | 1 | 3 | 3 | - Seek assistance if in need of extra help from facilities staff if needed - Seek medical attention from SUSU Reception if in need - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |

| Overcrowding | Physical injury | Event organisers and attendees | 2 | 4 | 8 | - Do not push/shove - If large crowds form, barriers can be requested by SUSU facilities team (if available on the day) to assist with crowd management. - Book during quieter times when less activities taking place on Redbrick/book all available space - Inform other bookings on the Redbrick/in the area of the event | 1 | 4 | 4 | - Seek medical attention if problem arises - With support from a SUSU Activities coordinator Inform UoS security team of the event (– on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk) and liaise with them on need for security teams on the day - Security team may inform police of the event if required (e.g. marches) - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Fire | Injuries to all attendees, damage to infrastructure | All | 2 | 5 | 10 | - No cooking, smoking, or other activities involving fire within or near to the building. - All participants will be ready to evacuate in the case of a fire alarm and shown to the nearest fire exit. | 1 | 4 | 8 | - Seek assistance and medical attention in case of fire – call 999 for fire brigade and ambulance if necessary. - Notify SUSU and University security in case of any fire-related incident. |
| Disturbance to public, students and staff | Conflict, noise, crowds | Event organisers and attendees, general public | 2 | 2 | 4 | - Events planned for redbrick avoiding residential areas - UoS Security Teams informed of the event - Everybody will be encouraged to stay together as a group | 1 | 2 | 2 | - With support from a SUSU Activities coordinator Inform UoS security team of the event -University Security 24 hours – on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk |
| Poor behavior from attendees or organisers | Reputational damage to the society, University, and SUSU | SSAGO, University, SUSU, members | 1 | 2 | 2 | - Any poor behaviour will immediately be addressed and those acting in an unacceptable way will be asked to leave the event. - No tolerance of disturbance to the public, aggression, or other poor behaviour. | 1 | 2 | 2 | - Attempts will be made to de-escalate the situation where possible, but any continued aggressive behaviour will be reported to SUSU and attendees will be removed from the situation however is safest. - University Security to be called in serious situations. |

| PART 2A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
|  |  |  |  |  |  | - shouting, chants, whistles etc. will be kept to a minimum around busy university buildings and residential areas - If applicable book space during quieter times when less activities taking place in local lecture theatres (lunch, Wednesday afternoons) |  |  |  | - Inform UoS/SUSU communications team of the event- can brief others via SUSSSED |

| Counter protest, discrimination against the demonstration | Assault, Violence or threatening/ Aggressive Behaviour | Event organisers and attendees | 2 | 4 | 8 | - Event planned for Highfield campus- a route well signposted and known for students - Leaders to advise all participants to not engage/respond to any protests, aggressive behaviour- if safe to do so will encourage group to move on and remove themselves from situation- The event will be ended and students advised to return to campus if this continues - Prior information about event and what to expect given out so participants know what to expect via Facebook/social media posts - Participants made aware they could join and leave the event at any time. - Ensure that people are aware that this is an open space for discussion to discourage protest. | 1 | 4 | 4 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. - Any incidents will be reported via UoS reporting tools - Contact emergency services if needed - Organisers will, following the event, share relevant information on support/signpost via social media channels etc. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| PART 2A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Talks/debates - subjects that could be sensitive or personal to some members | The audience feels negative emotions around the topic or becomes distressed by images or events shown/discussed. | Members | 2 | 3 | 6 | Prior information about event and what to expect given out so participants know what to expect. Members made aware they could leave the event at any time. Members referred to enabling/signpost to support organisations (e.g. via presentation slide, or by speakers/committee members) SUSU reporting tool available | 1 | 3 | 3 | - Organisers will, following the event, share relevant information on support/signpost-Facebook/email/newsletter - Committee Wide Training - Seek guidance from activities/SUSU advice centre/UoS enabling team as required - Committee WIDE training |

PART 2B – Action Plan

Risk Assessment Action Plan

| Part no. | Action to be taken, incl. Cost | By whom | Target date | Review date | Outcome at review date |
| --- | --- | --- | --- | --- | --- |
| 1 | Event organisers to have submitted a SUSU groups External speaker form (if applicable) | Bryony Gardner | 25.09.2026 | 29.09.26 |  |
| 2 | Event organisers to ensure they have read and are familiar with the UoS Code of Practice on Freedom of speech and academic freedom. | Lily Hemsley | 25.09.2026 | 29.09.26 |  |
| 3 | UoS Security Team and legal services informed of event if applicable | SUSU Activities Team | Within 1 Week of submission of external speaker form. | 29.09.26 |  |
| 4 | Event purpose shared with participants-e.g. shared via social media channels, emails, ticketing platform | Lily Hemsley, Molly Clarke, Lottie Ellard | Within 1 Week of submission of external speaker form. | 29.09.26 |  |
| 5 | Events organiser to lead on an event briefing for volunteers/speakers/security staff | Lily Hemsley, Daniel Isard | 29.09.26 | 29.09.26 |  |
| 6 | If applicable, a weather check, the committee will be keeping an eye on the weather forecast and will confirm if the event can go ahead | Lily Hemsley, Daniel Isard | 29.09.26 | 29.09.26 |  |
| 7 | Committee to organise and arrange the room for the event, including moving tables and signposting between the two rooms | Bryony Gardner, Lily Hemsley, Daniel Isard | 29.09.26 | 29.09.26 |  |

| Responsible committee member signature: Print name: Bryony Gardner Date: 25.09.26 | Responsible committee member signature: Print name: Lily Hemsley Date: 25.09.26 |
| --- | --- |

# Assessment Guidance

| 1. Eliminate | Remove the hazard wherever possible which negates the need for further controls | If this is not possible then explain why | 1 |
| --- | --- | --- | --- |
| 2. Substitute | Replace the hazard with one less hazardous | If not possible then explain why | 2 |
| 3. Physical controls | Examples: enclosure, fume cupboard, glove box | Likely to still require admin controls as well | 3 |
| 4. Admin controls | Examples: training, supervision, signage |  | 4 |
| 5. Personal protection | Examples: respirators, safety specs, gloves | Last resort as it only protects the individual |  |
|  |  |  | 5 |

5

LIKELIHOOD

4

3

2

1

1	2	3	4	5

### IMPACT

Risk process

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

| 5 | 10 | 15 | 20 | 25 |
| --- | --- | --- | --- | --- |
| 4 | 8 | 12 | 16 | 20 |
| 3 | 6 | 9 | 12 | 15 |
| 2 | 4 | 6 | 8 | 10 |
| 1 | 2 | 3 | 4 | 5 |

Identify the impact and likelihood using the tables above.

- Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.

- If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.

- If the residual risk is green, additional controls are not necessary.

- If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable.

- If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.

- Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |

The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.