This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group. You will also need to complete a charity form linked here.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: Zoe Tay | Email Address for Main Contact: zeet1g23@soton.ac.uk | Club or Society: Actuarial Society | Contact Number: 07502724285 |
| 1B) Event Information: |  |  |  |
| Event Name: PwC Career Talk | Event Date: 16/02/2026 | Event Venue/Venues: B100/3023(S/R) | Total Attendees: 100 |
| Event Timings: | Set Up: 17:30 Event Start: 18:00 Event End: 19:30 Pack Down: 20:00 |  |  |
| Event Break down: (This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity.) | 17:30 – Set up venue, ensure PA system is working 18:00 – Doors open, guest arrival 18:15 – Start of lecture 19:15 – End of lecture 19:20 – Refreshments (pizza) is served 19:40 – Pack down 20:00 – Clear the venue |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Boxoffice: You can set up Box-office tickets through your group's hub page for guidance on this click here: | No | How Much Are your Tickets? And how many are available? |  |
| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | Career talk by Rees Cooper from PricewaterhouseCoopers (PwC), who will speak about actuarial work at PwC, career opportunities for actuarial students, and pathways into the profession, followed by a short Q&A session. |  |  |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | Event lead: Zoe Tay Doors: Gilliane Chow Food Lead: Divyansh Bhardwaj Volunteers for set up: Hidir Azlan Shah |  |  |
| Tech Requirements (For a full list of what you can hire click here) | Microphone Screen with presentation PA system |  |  |
| Facilities Requirements | Seatings in the lecture hall |  |  |
| Food Requirements (For full guidance on this click here) | Dominos pizza (will cater for any allergies and dietary requirements) |  |  |
| Security & First Aid Requirements (Who are the qualified first aiders in the group should a medical emergency occur?) | - We will provide first aid kit in case of any emergency |  |  |
| Decorations that you are providing | No |  |  |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | No |  |  |
| 1C) Only Required If External Company/External Speaker On Site For Event |  |  |  |
| Business Name: PricewaterhouseCoopers (PwC) | Business Contact Name: Rees Cooper | Email Address: rees.m.cooper@pwc.com | Contact Number: |
| Arrival On Site: 18:00 Departure time: | Companies Risk Assessment link: | Companies Insurance Link: | Companies Public Liability Information Link: |

If you are inviting a external company or individual on to campus for your event you will be required to submit this form to legalservices@soton.ac.uk at least 15 working days before the event. For more guidance on this please click here.

| PART 2A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Slips, trips and falls | Physical injury | Event organisers and attendees | 2 | 3 | 6 | - All boxes and equipment to be stored away from main protest area, e.g. stored under tables - Floors to be kept clear and dry, and visual checks to be maintained throughout the event by organizers. - Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. - Report any trip hazards to facilities teams asap. If cannot be removed mark off with hazard signs | 1 | 3 | 3 | - Seek medical attention from SUSU Reception if in need - Contact facilities team via SUSU reception - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Fire | Smoke inhalation, burns. Risk of extreme harm. | All participants and organisers, any staff and spectators | 2 | 5 | 10 | Those leading the session must ensure they are aware of and fully understand the venue or location’s fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the participants the nearest emergency exit routes at the start of a session, and the importance of leaving calmly in case of an emergency. Avoid build-up of debris in the activity area. Consider accessibility requirements. | 1 | 5 | 5 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident reporting guide |
| Setting up of Equipment. E.g. Table and chairs | Bruising or broken bones from tripping over table and chairs. | Event organisers and attendees | 2 | 3 | 6 | - Make stall operators aware of the potential risks, follow manual handling guidelines - Ensure that 2 people carry tables. - Setting up tables will be done by organisers. - Work in teams when handling other large and bulky items. | 1 | 3 | 3 | - Seek assistance if in need of extra help from facilities staff if needed - Seek medical attention from SUSU Reception if in need - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Overcrowding | Physical injury | Event organisers and attendees | 2 | 4 | 8 | - Do not push/shove - If large crowds form, barriers can be requested by SUSU facilities team (if available on the day) to assist with crowd management. - Book during quieter times when less activities taking place on Redbrick/book all available space - Inform other bookings on the Redbrick/in the area of the event | 1 | 4 | 4 | - Seek medical attention if problem arises - With support from a SUSU Activities coordinator Inform UoS security team of the event (– on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk) and liaise with them on need for security teams on the day - Security team may inform police of the event if required (e.g. marches) - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Disturbance to public, students and staff | Conflict, noise, crowds | Event organisers and attendees, general public | 2 | 2 | 4 | - Events planned for redbrick avoiding residential areas - UoS Security Teams informed of the event - Everybody will be encouraged to stay together as a group - shouting, chants, whistles etc. will be kept to a minimum around busy university buildings and residential areas - If applicable book space during quieter times when less activities taking place in local lecture theatres (lunch, Wednesday afternoons) | 1 | 2 | 2 | - With support from a SUSU Activities coordinator Inform UoS security team of the event -University Security 24 hours – on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk - Inform UoS/SUSU communications team of the event- can brief others via SUSSSED |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents causing reputational damage to the group, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name into disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring all members are reminded that they are representing the club/society, SUSU and the University, often in branded clothing. Members are reminded that they need to adhere to SUSU’s Code of Conduct. - Consider risks at activities as well as digital presence (e.g. social media posts) | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Follow SUSU incident reporting guide |
| Events involving Food | Allergies Food poisoning Choking | All | 3 | 5 | 15 | Only order/buy food at establishments with appropriate food hygiene (EHO) rating. Food to only be provided/eaten when other activities are stopped. Follow good food hygiene practices - no handling food when ill, tie back hair, wash hands regularly using warm water and soap, refrigerate necessary products. For store-bought items/snacks, keep packaging to hand for ingredient and allergen information. | 1 | 5 | 5 | SUSU food hygiene level 2 course available for completion- requests made to Activities Team. Call for first aid/emergency services a required . Report incidents via SUSU incident report procedure. |
| Talks/debates - subjects that could be sensitive or personal to some members | The audience feels negative emotions around the topic or becomes distressed by images or events shown/discussed. | Members | 2 | 3 | 6 | Prior information about event and what to expect given out so participants know what to expect. Members made aware they could leave the event at any time. Members referred to enabling/signpost to support organisations (e.g. via presentation slide, or by speakers/committee members) SUSU reporting tool available | 1 | 3 | 3 | - Organisers will, following the event, share relevant information on support/signpost- Facebook/email/newsletter - Committee Wide Training - Seek guidance from activities/SUSU advice centre/UoS enabling team as required - committee WIDE training |

| # PART 2B – Action Plan |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # Risk Assessment Action Plan |  |  |  |  |  |  |  |  |
| # Part no. | # Action to be taken, incl. Cost | # By whom | # Target date |  | # Review date |  | # Outcome at review date |  |
| # 1 | # Providing first aid kit in case of any emergency | # Gilliane Chow | # 12/10/2025 |  |  |  |  |  |
| Responsible committee member signature: Amiera |  |  |  |  | Responsible committee member signature: Zoe |  |  |  |
| # Print name: Amiera Amryzal |  |  |  | # Date: 8/10/2025 |  | # Print name: Zoe Tay |  | # Date: 8/10/2025 |

Assessment Guidance

| - Eliminate | Remove the hazard wherever possible which negates the need for further controls | If this is not possible then explain why |  |
| --- | --- | --- | --- |
| - Substitute | Replace the hazard with one less hazardous | If not possible then explain why |  |
| - Physical controls | Examples: enclosure, fume cupboard, glove box | Likely to still require admin controls as well |  |
| - Admin controls | Examples: training, supervision, signage |  |  |
| - Personal protection | Examples: respirators, safety specs, gloves | Last resort as it only protects the individual |  |

| LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 | 4 | 8 | 12 | 16 | 20 |
|  | 3 | 3 | 6 | 9 | 12 | 15 |
|  | 2 | 2 | 4 | 6 | 8 | 10 |
|  | 1 | 1 | 2 | 3 | 4 | 5 |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  |  | IMPACT |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

Risk process

- Identify the impact and likelihood using the tables above.

- Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.

- If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.

- If the residual risk is green, additional controls are not necessary.

- If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable.

- If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.

- Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.

- The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |