This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group. You will also need to complete a charity form linked here.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: Jamie Charlton | Email Address for Main Contact: jc22g23@soton.ac.uk | Club or Society: Southampton Quadball Club | Contact Number: +44 7930 862904 |
| 1B) Event Information: |  |  |  |
| Event Name: Southampton Quadball Charity Games | Event Date: Saturday 11th October 2025 | Event Venue/Venues: Southampton Common (exact location: https://maps.app.goo.gl/4yBXen9KKyQgwwiW8 ) | Total Attendees: 30-60 |
| Event Timings: | Set Up: 9:00am Event Start: 10:00am Event End: 6:00pm Pack Down: 6:00pm |  |  |
| Event Break down: (This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity.) | 9:00 – 10:00 – All equipment and pitches set up by committee and team members 10:00 – Players participating in the pre-game training arrive and training begins. Teams outside of Southampton can choose to arrive at this time and participate 12:30 – Pre-game training ends, any other participating teams arrive and players have lunch 13:00 – 16:30 – Spectators arrive and games begin on two pitches starting on the hour every hour for a total of 8 games 17:30 – Announce which teams scored highest and congratulate players, have a short speech from a charity spokesperson 18:00 – 18:30 – Players pack down pitches and store equipment |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Boxoffice: You can set up Box-office tickets through your group's hub page for guidance on this click here: | Not ticketed, but advance donations are accepted on our Boxoffice: SQC Charity Match Donation | How Much Are your Tickets? And how many are available? | £5 – suggested player’s donation £2 – suggested spectator’s donation Not limited |
| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | 8-10 friendly tournament-style games of quadball raising money for Beyond Reflections. It will be a freshers-friendly event encouraging new players to take part in organised matches in order to recruit members for the society as well. The morning will be dedicated to training new players and preparing them for a game, and games will start in the afternoon when spectators arrive. Teams who score the most goals and win the most games will be congratulated at the end but everyone will receive a prize in the form of a small bag with a society logo sticker, society branded lollipop and beaded bracelet. All proceeds from player and spectator box office tickets will go to the charity, and there will be a donation table with a RAG card machine if spectators want to donate more on the day. Quadball (previously quidditch) is a full-contact sport, so anyone intending to play are required to bring a moulded mouthguard and no play will be allowed without one, with new players required to attend the pre-game training in order to ensure safe tackling. Time and interest permitting, a no-contact match may be conducted at the end of the day where anyone can join in. Players and spectators are expected to provide their own food. |  |  |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | Event leads: Jamie Charlton, Bronwyn Powell Event managers (committee): Elliot Simcox, Amy Tamblyn, Harry Nelson Volunteers for set up: James Richardson, Arthur East, Raj Mukuntharaj, Emma Staines, Ryan Fairhurst |  |  |
| Tech Requirements (For a full list of what you can hire click here) | None |  |  |
| Facilities Requirements | 20x Chairs 4x Tables 2x Outdoor Gazebos (if possible) |  |  |
| Food Requirements (For full guidance on this click here) | Players and spectators will be responsible for their own food Lollipops included in prize bags are store bought, sealed and include a list of ingredients and allergens on the packaging |  |  |
| Security & First Aid Requirements (Who are the qualified first aiders in the group should a medical emergency occur?) | Each match will have a designated first aider, normally a course-qualified volunteer player from a team that is not currently playing. In the event of an emergency, 999 will be contacted immediately. Any injury or incident will have a SUSU incident report filled out. |  |  |
| Decorations that you are providing | Banners and flags promoting our team and Beyond Reflections |  |  |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | Anything subsidised (e.g. mouthguards for new players) will come from the society’s finances, not proceeds from this event |  |  |
| 1C) Only Required If External Company/External Speaker On Site For Event |  |  |  |
| Business Name: | Business Contact Name: | Email Address: | Contact Number: |
| Arrival On Site: Departure time: | Companies Risk Assessment link: | Companies Insurance Link: | Companies Public Liability Information Link: |

If you are inviting a external company or individual on to campus for your event you will be required to submit this form to legalservices@soton.ac.uk at least 15 working days before the event. For more guidance on this please click here.

| PART 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  |  | (2) Risk assessment |  |  |  |  |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences |  | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  |  |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  |  | Likelihood |  | Impact |  | Score |  | Control measures (use the risk hierarchy) |  | Likelihood | Impact | Score |  |
| General Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Misuse of university meeting spaces | Injury due to falling or tripping on stairs, chairs, desks or other equipment in the space (see below). Breaking university equipment in the spaces. Reputational damage to the university if offensive or inappropriate behaviour occurs (see below). |  | Participants, or the club, SUSU or the University’s reputation | 2 |  | 2 |  | 4 |  | Advise all participants on appropriate social and physical behaviour before using a university space. Ensuring that any incidents are recorded and addressed. Ensuring all members are reminded that they are representing the club/society, SUSU and the University in (usually) branded clothing. |  | 1 | 1 | 1 |  |
| Slips, trips and falls | Soft tissue injury e.g., sprain, bruising. Potential broken ankle or other breaks i.e. wrists etc. Links directly to weather and ground surfaces. |  | All participants and organisers/staff and spectators | 2 |  | 3 |  | 6 |  | Check venue conditions for holes, lumps, and other obstacles. All boxes and equipment to be stored away from main meeting area, e.g. stored under tables. Any cables to be organised as best as possible, e.g. cable ties to be used if necessary. Floors to be kept clear and dry, and visual checks to be maintained throughout the meeting by organisers. Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. Report any trip hazards to facilities teams/venue staff asap. If cannot be removed, mark off with hazard signs. |  | 1 | 3 | 3 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. SUSU incident reporting guide |
| Fire | Smoke inhalation, burns and more severe. Risk of extreme harm. |  | All participants and organisers/staff and spectators | 1 |  | 5 |  | 5 |  | Those leading the session must ensure they are aware of and fully understand the venue or locations fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the Volunteers/Event Staff the nearest emergency exit routes at the start of a session, and the importance of assisting others to leave calmly in case of an emergency. Consider accessibility requirements |  | 1 | 4 | 4 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy.SUSU incident reporting guide |
| Setting up/moving or chairs/tables/other objects in the area. | Bruising or broken bones from tripping over table and chairs. |  | Meeting organisers and attendees | 2 |  | 3 |  | 6 |  | Make Event Volunteers aware of the potential risks, follow manual handling guidelines Ensure that at least 2 people carry tables and large objects. Setting up tables will be done by organisers. Work in teams when handling other large and bulky items. Request tools to support with move of heavy objects- SUSU Facilities/venue. E.g., hand truck, dolly, skates Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable. |  | 1 | 3 | 3 | Seek assistance if in need of extra help from facilities staff/venue staff if needed Seek medical attention from SUSU Reception if in need Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Overcrowding | Physical injury, distress, exclusion |  | Event organisers and attendees | 1 |  | 3 |  | 3 |  | Do not push/shove If large crowds form, barriers can be requested by SUSU facilities team (if available on the day) to assist with crowd management. Book during quieter times when less activities taking place on Redbrick/book all available space Inform other bookings on the Redbrick/in the area of the event Use ticketing system (SUSU Box Office) for regular sessions/meetings to avoid exceeding venue capacity. Ensure space meets needs of members e.g. considering location & accessibility of space (use AcessAble database to check accessibility information of venues). If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. Committee to consult members on needs and make reasonable adjustments where possible |  | 1 | 3 | 3 | Seek medical attention if problem arises All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident reporting guide With support from a SUSU Activities coordinator Inform UoS security team of the event (– on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk) and liaise with them on need for security teams on the day. Security team may inform police of the event if required (e.g. marches). Welfare Officer to complete WIDE training. |
| Electronics | Risk of eye strain, injury, electric shock |  | Committee and attendees | 2 |  | 4 |  | 8 |  | Ensure regular breaks (ideally every 20mins) when using screens Ensure screen is set up to avoid glare, is at eye height where possible Ensure no liquids are placed near electrical equipment Ensure all leads are secured with cable ties/mats etc For external venues, pre-check equipment and last PAT testing dates. |  | 1 | 4 | 4 | Request support and advice from SUSU IT/Tech teams e.g. via activities team Seek medical attention as required Follow SUSU incident reporting guide |
| Accessibility: Entrances and Exits to the chosen area. | Participants may be prevented from attending the activity due to a lack of considerations of accessibility needs and requirements. They could also be prevented from leaving the area quickly in an emergency if the correct infrastructure and considerations have not been made. |  | Participants, committee | 1 |  | 5 |  | 5 |  | All areas chosen for activity will have their suitability checked. If a closed activity for members, members will be consulted to ensure there are no accessibility requirements. If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. |  | 1 | 5 | 5 | In case of an emergency, call the emergency services on 999. If those with accessibility problems have not been able to exit, make the building manager and emergency services aware. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. Follow SUSU incident reporting guide |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents during club or society activity could pose a reputational risk to the club, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name intro disrepute. |  | The club, SUSU or the University’s reputation | 2 |  | 1 |  | 2 |  | Ensuring all parts of this risk assessment are adhered to. Ensuring that any incidents involving public or others are recorded and addressed. Ensuring all members are reminded that they are representing the club/society, SUSU and the University in (usually) branded clothing. Members are reminded that they need to adhere to SUSU’s Code of Conduct. Consider risks at activities as well as digital presence (e.g. social media posts) |  | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Follow SUSU incident reporting guide |
| Financial Risk: For the club or society, or potentially even SUSU if the club/soc finds itself in difficulty. | Club or society activity costing more than planned, weakening their financial position. Incidents with members of the public, participants, staff or members causing lawsuits and financial penalties. |  | The club or society Members subject to lawsuits SUSU if required to assist. | 1 |  | 1 |  | 1 |  | Clubs and societies required to complete financial forecasting and budget for the year. All encouraged to review membership fees yearly to ensure they are able to comfortably cover costs. SUSU can offer clubs and societies loans – these will need to be agreed and a payment schedule decided upon. Clubs and societies that have to rely on a loan will be subject to development plans to ensure their future is protected. |  | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Follow SUSU incident reporting guide |
| Legal Compliance: Club or society activity going against set law. This includes breaches of the freedom of speech act | Fines imposed upon the student group as well as SUSU. Jail sentences. Reputational risk to the student group, SUSU and the wider University |  | The club or society, committee and members, SUSU or the Wider University. | 1 |  | 1 |  | 1 |  | All clubs and societies should ensure they are following set law at all times. If ever in doubt, they will contact the Activities team prior to the activity taking place. All who wish to bring in an external speaker must follow due process, available here This will be looked over by the University Legal Services team, and may require security being consulted and an extra risk assessment being submitted. |  | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Follow SUSU incident reporting guide |
| Medical Issues: Pre-existing and process for any that appear during | Illness, death |  | Members, committee | 3 |  | 5 |  | 9 |  | All clubs and societies should have a process for if a medical issue occurs. All should know the location of the nearest first aider. Members do not need to disclose medical information to committee (GDPR), but all committee should know how to find a first aider and help quickly. If in a Southampton Sport space, contact reception. If in SUSU, contact reception. If no-one can be found, contact campus Security – 02380 59331 |  | 1 | 1 | 1 | In an emergency, contact 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow Ensure that any incidents involving public or others are recorded and addressed. Follow SUSU incident reporting guide |
| Charity Fundraising |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Handling and storing card readers | - Theft - Individuals being mugged/robbed - Loss/misplacement leading to financial loss |  | Members and Participants | 3 |  | 4 |  | 12 |  | Southampton RAG procedures will be followed: - Charity Event form completed, and RAG approval will be given - All food hygiene certificates and event risk assessment to be approved by activities team - Sum-up Card machine to be requested and collected from SUSU reception. - Should not be storing money. ALL donations to be taken via Sumup Machine or Just Giving Pages |  | 2 | 3 | 6 | No Cash to Be Accepted at all. No card machines to be left unattended. No Volunteers to be left alone with the card machine In the event of theft committee members will: - Highlight the incident to any community police officers in the area/report to 111 - Report to SUSU Duty manager and Complete a SUSU incident report |
| Abuse of Members and Volunteers | Members of the public or students may act violently towards volunteers. Eg: Because they disagree with the cause. |  | Volunteers and Participants | 4 |  | 3 |  | 12 |  | No Volunteers are ever to be left alone. Always have at least 2 people at a stall or at an Event. |  | 2 | 3 | 6 | - Report to SUSU Duty manager and Complete a SUSU incident report - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Venue/Location considerations | Require certain licenses/sign off |  | Organisers, Participates, SUSU | 1 |  | 4 |  | 4 |  | Ensure the venue has the relevant licenses required for your event ahead of time. Ensure your event has the required sign off by the venue's security teams. Ensure proper booking process is followed for ALL bookings on and off campus. With no event going forward without Activities Approving the Risk Assessment. On campus - Ivvy Booking/uni room booking - Risk assessment - Contract Off campus - Risk assessment - Any bookings/contracts with external providers. |  | 1 | 2 | 2 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. - Follow SUSU incident reporting guide |
| Lone working | Stolen goods, injury to individual misuse of card reader. |  | Volunteers | 3 |  | 3 |  | 9 |  | Ensure no one is left alone as a volunteer at a fundraising event especially if using a Sum-up Card reader. Event led to brief volunteers to operate the card readers in pairs and briefed on how to handle situations surrounding these. |  | 3 | 1 | 3 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. - Follow SUSU incident reporting guide |
| Sports activity | Injuries such as scrapes, bruises, concussions, over exertion, broken bones or strains from contact within the sport, balls being thrown or tripping and falling |  | Participants and spectators | 3 |  | 5 |  | 15 |  | Adequate training in how to play the sport safely by experienced coaches is mandatory for any first time players. Coaches will decide and enforce whether or not a player is able to participate safely. Personal protective equipment (mouthguards) will be required and no play will be conducted without them. All players will be checked for unsafe personal wear (jewellery, loose clothing, metal studded shoes, objects in pockets etc.) and made to remove it by coaches before playing. See ‘Sports Activity Considerations’ below for much more detailed assessments. |  | 2 | 4 | 8 | At least one qualified first aider will be assigned to a match and present at the morning training to respond to medical situations that arise. In the case of a medical emergency, 999 will be called immediately. A SUSU incident report will be filled out for any incidents that do occur. |
| Adverse weather | Injury, Illness, Slipping, Burns |  | Event organisers, event attendees, | 4 |  | 3 |  | 12 |  | Lead organiser to check the weather is suitable for activities on the day. Extreme weather considerations will be decided two days in advance Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, hydrate If Cancellation is required ensure all relevant parties are contacted. SUSU – subookings@soto.ac.uk Uni – roombookings@soton.ac.uk Or your external contacts. |  | 4 | 1 | 4 | If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date |
| Alcoholic/External Events |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Alcohol consumption | Participants may become at risk as a result of alcohol consumption Members of the public may act violently towards participants. |  | Event organisers, event attendees, | 2 |  | 5 |  | 10 |  | Members are responsible for their individual safety though and are expected to act sensibly Initiation behaviour not to be tolerated and drinking games to be discouraged For socials at bars/pubs etc bouncers will be present at most venues. Bar Security staff will need to be alerted and emergency services called as required. Where possible the consumption of alcohol will take place at licensed premises. The conditions on the license will be adhered to and alcohol will not be served to customers who have drunk to excess Committee to select ‘student friendly’ bars/clubs and contact them in advance to inform them of the event Society to follow and share with members Code of conduct/SUSU Expect Respect policy |  | 1 | 3 | 5 | Follow SUSU incident report policy Call emergency services as required 111/999 Committee WIDE training |
| Travel | Vehicle’s collision -causing serious injury |  | Event organisers, event attendees, Members of the public | 4 |  | 3 |  | 12 |  | Members are responsible for their individual safety though and are expected to act sensibly Local venues known to University of Southampton (UoS) students chosen Event organisers will be available to direct people between venues. Attendees will be encouraged to identify a ‘buddy’, this will make it easier for people to stay together. They will be encouraged (but not expected) to look out for one another and check in throughout the night where possible. Avoid large groups of people totally blocking the pavement or spilling in to the road. Anybody in the group who is very drunk or appears unwell and therefore not safe should be encouraged to go home ideally with someone else. If required a taxi will be called for them (ideally SUSU safety bus will be used, or radio taxis). Be considerate of other pedestrians & road users, keep disturbance & noise down. |  | 2 | 2 | 4 | Where possible venues chosen for socials will be local/known to members and within a short distance from each other. Contact emergency services as required 111/999 Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Travel by car, train, bus, plane when leaving the local area. | Vehicle collision – causing anything from minor to severe injuries, as well as mental health issues. |  | Members, those driving, members of the public | 4 |  | 3 |  | 12 |  | Committee to check that drivers have the relevant licences and insurance for the mode of travel. This includes if they have completed a SUSU minibus test. Members expected to drive or travel in a sensible manor, with those doing otherwise to face disciplinary action (from the club in the first instance). Can cause reputational issues, especially if driving SUSU branded vehicles. Importance of this to be reminded. |  | 2 | 2 | 4 | Contact emergency services as required 111/999 Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Spiked Drinks/Alcohol Poisoning | Participants may consume too much alcohol during this event or be spiked. This could result in a loss of consciousness or self- control |  | Event organisers, event attendees, | 2 |  | 5 |  | 10 |  | Supervision, the event will be run by the society committee These attend each venue. Ideally, they will not drink to excess during the event Bouncers/trained staff in Venues should watch for excessive drinking and watch people who are believed to have consumed a lot of alcohol. Report any suspicious behaviour to staff. Participants encouraged to stay with a nominated ‘buddy’ where possible. The organizers have confirmed the premise is licensed. Action organizers (b). - The consumption of alcohol will take place at licensed premises. The conditions on the license will be adhered to and alcohol will not be served to customers who have drunk to excess. Action licensee. Games involving binge drinking or the consumption of excessive amounts of alcohol are not to be undertaken.- Society to follow Code of conduct/Expect Respect policy |  | 2 | 3 | 6 | Members are responsible for their individual safety though and are expected to act sensibly when walking around. For anyone who is too inebriated it will be suggested to them that they should return home rather than continue on the social. Taxis will be called if required (look at SUSU safety Bus, Radio Taxis options) If they need to go to the hospital they will also be accompanied there. Participants advised to avoid leaving drinks unattended and if you think anything has been added to a drink; report it; try and retain the drink for testing. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Members getting lost or separated. Members leaving an event/activity alone or without notifying others. | During the event participants may decide they want to leave, or they may get lost on the way |  | Event organisers, event attendees, | 3 |  | 3 |  | 9 |  | If a person leaves without warning all efforts will be done to locate them. Stress however that attendees are responsible for their individual safety. Supervision, the event will be run by the society committee These attend each venue. Ideally, they will not drink to excess during the event Venues chosen local and within a short distance from each other. Will look to select venues known to UoS students and within student areas. |  | 2 | 2 | 4 | Follow SUSU incident report policy Call emergency services as required |
| Violent or offensive behaviour | Participants may become violent or offensive due to the consumption of too much alcohol. Members of the public may act violently towards participants. |  | Event organisers, event attendees, | 2 |  | 5 |  | 10 |  | Bouncers will be present at most venues. Bar Security staff will need to be alerted and emergency services called as required. The consumption of alcohol will take place at licensed premises. The conditions on the license will be adhered to and alcohol will not be served to customers who have drunk to excess Committee to select ‘student friendly’ bars/clubs and contact them in advance to inform them of the event Society to follow and share with members Code of conduct/SUSU Expect Respect policy |  | 1 | 3 | 5 | If the situation becomes very serious and results in the participant being arrested then it will be made clear that they cannot be accompanied to the police station. Follow SUSU incident report policy Call emergency services as required |
| Slips, trips and falls as a result of alcohol | Consumption of too much alcohol may result in participants falling and subsequently injuring themselves. |  | Event organisers, event attendees, | 3 |  | 2 |  | 6 |  | Committee to check that chosen venues meet the following requirements: - Venue is in good condition with no major trip hazards. - Bar staff monitor the condition of the floors & mop up split drinks. - Security staff & Bar Staff provide first aid cover. DJ’s or bands equipment placed so as not to form a trip hazard. Power supply leads taped down. |  | 3 | 1 | 3 | If necessary, emergency services will be called Request first aid at venue Follow SUSU incident report policy |
| Allergies - food and drink | Allergic reactions to food and drink when out |  | Event organisers, event attendees, | 3 |  | 5 |  | 15 |  | Attendees responsible for own welfare I such instances- follow guidelines of venues. First aid requested from bar staff as required. |  | 1 | 5 | 5 | Call Emergency Services/alert bar staff |
| Sports Activity Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Equipment: any equipment the sport requires/uses needs to be risk assessed. | Cut/abrasion/ bruising from sharp edges. Is the equipment safe to be used? | All participants and bystanders. |  |  | 2 |  | 2 |  | 4 |  | Check all equipment prior to use. Is it safe to use? Does it have any sharp edges? Is it damaged in any way? Check any stands – are they safe? Are they likely to fall? Are they damaged or do they have any sharp edges? Do those leading the session have the appropriate training to demonstrate and use the equipment correctly? Those leading the session to remain vigilant to ensure participants are using the equipment as demonstrated. | 1 | 1 | 2 | Seek medical attention if problem arises Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Moving/setting up equipment: Goals, hoops, nets, carrying anything else | Various forms of injuries up to and including possible sprains and breakages | All participants and organisers/staff. |  |  | 2 |  | 3 |  | 6 |  | Large or heavy equipment to be carried by 2 people. Request tools to aid with the moving of heavy objects – SUSU facilities/venue e.g., hand truck, dolly, skates etc. Any equipment not in use that is not fixed should be removed from the activity area. | 1 | 2 | 3 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Being hit by dodgeballs (bludgers) or volleyballs (quaffles) (thrown balls) | Concussion if hit on the head. Otherwise, potential bruising. | All participants and organisers/staff and spectators as well as members of the public who may be walking past |  |  | 2 |  | 4 |  | 8 |  | This is controlled by the balls being slightly deflated making them easier to hold so there is more control. It also means they have less of an impact on contact. We will regularly check balls for lumps and tears. Players are advised not to aim for each other’s heads in close vicinity and pass volleyballs (quaffles) rather than throwing them to hit each other, further minimising the risk. If members of the public come too near play then we will stop immediately and advise them to move further away for their own safety. | 1 | 4 | 4 | If the person who has been hit by the ball is showing signs of concussion or is confused, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Removal of Jewellery, plus any other objects in pockets etc | Entrapment/ things getting stuck, collisions with others that could cause cuts or bruises. | All participants and organisers/staff. |  |  | 2 |  | 2 |  | 4 |  | Participants asked to remove jewellery and objects from pockets prior to joining in. Those leading the session must ensure this has been done. | 1 | 2 | 2 | If any injury occurs, seek medical attention. If severe, call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Over-exertion or exhaustion. Strenuous exercise and the effect on the body | Muscle injury – strains and pulls. | All participants and organisers/staff |  |  | 3 |  | 3 |  | 9 |  | Those leading the session should ensure a proper and thorough warm up is carried out prior to the session that focuses on the areas that are likely to be used the most i.e., arms. | 2 | 3 | 6 | If any injury occurs, seek medical attention. If severe, call 999 in an emergency (although unlikely for muscular) Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Participant Attire: Is the clothing they are wearing, including shoes, relevant to the sport or activity | Injury can occur if people are not wearing attire appropriate to the sport or activity. | All participants and organisers/staff and spectators |  |  | 2 |  | 3 |  | 6 |  | Ensure all participants are wearing suitable clothing (nothing in pockets) and appropriate footwear. Is specific safety equipment required i.e., helmet, pads, gum shield etc? | 1 | 3 | 3 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Extreme Weather | Heat or sun – risk of sunburn, heat exhaustion and dehydration. Cold – risk of hypothermia. Weather directly influences ground surfaces (see below) and the risk of slips, trips and falls (see above) | All participants and organisers/staff and spectators |  |  | 3 |  | 3 |  | 9 |  | Ensure regular drinks breaks are taken, and that each participant and staff member is advised to bring their own drinks bottle. If it is hot or sunny, ensure participants have taken steps to reduce their chance of harm – i.e., use of sun cream, hats and having available shaded area. If it is cold, ensure participants have suitable attire to enable them to keep warm. | 1 | 3 | 3 | If anyone is affected by the heat or cold, seek immediate medical attention. If severe, call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Ground Surfaces | Hard, uneven or slippery surfaces, usually linked to weather, that can cause slips trips and falls (see section 1). | All participants and organisers/staff and spectators |  |  | 2 |  | 3 |  | 6 |  | Check areas for hazards prior to session starting. Ensure participants are wearing suitable clothing (nothing in pockets) and appropriate footwear. | 1 | 3 | 3 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Tackling (sport appropriate) | Players can get injured from dangerous tackles – worst case broken legs or other limbs | Players/Participants |  |  | 2 |  | 4 |  | 8 |  | Ensure players are wearing relevant safety equipment i.e. shin pads, mouth guards etc. Ensure that players are properly trained on how to tackle safely and according to the sport’s rules by having coaches lead a mandatory training session before any contact is introduced. | 1 | 4 | 4 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Injury from insufficient warmups | Pulled or strained muscles | Players/Participants |  |  | 3 |  | 3 |  | 9 |  | Players/participants told the benefits of an effective warm up and encouraged to complete. Warmups led by an appropriately qualified or experienced individual. Appropriate recovery methods also discussed to ensure muscles are more pliable to warm up. | 1 | 3 | 9 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Qualification of coaches/instructors | Participants could be hurt or hurt each other if the coach does not possess relevant qualifications to be able to deliver the sport or activity safely. | Players/Participants |  |  | 3 |  | 3 |  | 9 |  | Clubs will source coaches/instructors that have the relevant qualifications to deliver their sport to that target audience (for example, football coaches will need a UEFA C/FA level 2 to be able to coach a team). Clubs are to research this and liaise with the students union. | 1 | 3 | 3 |  |
| Lighting | Players/Participants unable to see each other, the equipment or obstacles clearly, resulting in a higher risk of injury. | Players/Participants, Coaches/Instructors |  |  | 5 |  | 4 |  | 20 |  | Training and matches will only take place where there is sufficient light. Coaches and committee are deemed to be responsible for determining what is a safe light level. If lights are not working, this will be reported to Southampton Sport and the session stopped. SUSU Sports Coordinators will not schedule training or games in unlit areas past the predicted sunset. | 1 | 4 | 4 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Ability of players | Inexperienced players may play incorrectly resulting in potential risk of injury to themselves or others. | Players/Participants, Coaches/Instructors |  |  | 3 |  | 5 |  | 15 |  | Coaches will ensure that all players have the necessary protective equipment no matter experience or ability. They will also make sure that all first-time players who intend to play in the games have attended the full training session on the day. Coaches to decide whether it is safe for a player/participant to be part of that team or training. Coaches and committee to ensure that their team is playing against other teams of a similar level, training and in a safe environment. | 1 | 5 | 5 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Medical emergency | Members may sustain injury /become unwell pre-existing medical conditions Sickness Distress | Members |  |  | 3 |  | 5 |  | 15 |  | Advise participants; to bring their personal medication Members/Committee to carry out first aid if necessary and only if qualified and confident to do so Contact emergency services as required 111/999 Contact SUSU Reception/Venue staff for first aid support | 2 | 5 | 15 | Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |

| PART 2B– Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Assessment Action Plan |  |  |  |  |  |  |  |
| Part no. | Action to be taken, incl. Cost | By whom | Target date |  | Review date | Outcome at review date |  |
| 1 | Complete a Charity Event form and send this to suactivties@soton.ac.uk | Relevant committee members – president to ensure complete. | 28/07/25 |  | 22/09/25 |  |  |
| 2 | Committee to Read and share SUSU Expect Respect policy | Relevant committee members – president to ensure complete. | 15/09/25 |  | 22/09/25 |  |  |
| 3 | Set Up Just Giving/Fundraising Platform and/or book Sum-up Card Machines | Relevant committee members – president to ensure complete. | 28/07/25 |  | 22/09/25 |  |  |
| 4 | Equipment to be checked regularly | Committee - president to ensure complete | Ongoing |  | Ongoing |  |  |
| 5 | Risk assessment to be shared with and read by committee and made available to all participants | Committee - president to ensure complete | 15/09/25 |  | 22/09/25 |  |  |
| Responsible committee member signature: |  |  |  |  | Responsible committee member signature: |  |  |
| Print name: Jamie Charlton |  |  |  | Date 9/09/25 | Print name: Amelia Tamblyn |  | Date 11/9/2025 |

Assessment Guidance

| - Eliminate | Remove the hazard wherever possible which negates the need for further controls | If this is not possible then explain why | 1 2 3 4 5 |
| --- | --- | --- | --- |
| - Substitute | Replace the hazard with one less hazardous | If not possible then explain why |  |
| - Physical controls | Examples: enclosure, fume cupboard, glove box | Likely to still require admin controls as well |  |
| - Admin controls | Examples: training, supervision, signage |  |  |
| - Personal protection | Examples: respirators, safety specs, gloves | Last resort as it only protects the individual |  |

| LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 | 4 | 8 | 12 | 16 | 20 |
|  | 3 | 3 | 6 | 9 | 12 | 15 |
|  | 2 | 2 | 4 | 6 | 8 | 10 |
|  | 1 | 1 | 2 | 3 | 4 | 5 |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  |  | IMPACT |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

Risk process

Identify the impact and likelihood using the tables above.

Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.

If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.

If the residual risk is green, additional controls are not necessary.

If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable.

If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.

Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.

The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |