This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group. You will also need to complete a charity form linked here.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: Bethany Milne | Email Address for Main Contact: am4n23@soton.ac.uk | Club or Society: Southampton Video Games & Esports Society | Contact Number: 07871 964758 |
| 1B) Event Information: |  |  |  |
| Event Name: SVGE Presents: Speedruns & Showcases | Event Date: 15-03-2026 | Event Venue/Venues: SUSU Concourse | Total Attendees: 50 (up to 20 at a time) including spectators; 12 (up to 6 at a time) excluding spectators |
| Event Timings: | Set Up: Starts 09:00 Event Start: 11:00 Event End: 19:00-20:00 Pack Down: Complete by 21:00 |  |  |
| Event Break down: (This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity.) | 09:00-11:00 Set up tech 11:00 Welcome speech 11:10 First performance starts Performances of video games and board games, as dictated by schedule (specifics to be determined, see https://oengus.io/marathon/svge-2026 for details); 15-minute breaks between each 18:55-19:55 Last performance ends (malleable, depends on how long performances last which can vary significantly), thank you/goodbye speech 19:00-20:00 Pack down begins 21:00 Pack down ends Donations can be made throughout (online through Tiltify [see Charity Form] and contribute to incentives [something happens when donation goal reached] and bid wars [multiple options, option with most money raised wins]) |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Boxoffice: You can set up Box-office tickets through your group's hub page for guidance on this click here: | No | How Much Are your Tickets? And how many are available? | N/A |
| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | 8-9 hour gaming event raising money for the Rose Road Association! Individuals will take part in performances of video games and board games; performances include but are not limited to speedrunning, and will be listed in advance at https://oengus.io/marathon/svge-2026/schedule/release once finalised (submissions are also listed at https://oengus.io/marathon/svge-2026/submissions). Performances will be of any length up to 3 hours and will be separated by 15-minute breaks. Online donations will be encouraged throughout, with fundraising being done through Tiltify (set up as an individual user with funds going directly to Rose Road without touching SUSU or any person bank account). There will always be at least 2 committee members present, and the event will take place within the SUSU Concourse. |  |  |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | Event lead: Bethany Milne Tech lead: Alex New Hosting lead: Brandon Koh |  |  |
| Tech Requirements (For a full list of what you can hire click here) | Tripod for camera |  |  |
| Facilities Requirements | Staging Screen and speakers present in room |  |  |
| Food Requirements (For full guidance on this click here) | None |  |  |
| Security & First Aid Requirements (Who are the qualified first aiders in the group should a medical emergency occur?) |  |  |  |
| Decorations that you are providing | None |  |  |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | Tripod and staging costs will come out of society account, as per signed contract. No other costs are present. |  |  |
| 1C) Only Required If External Company/External Speaker On Site For Event |  |  |  |
| Business Name: Rose Road Association | Business Contact Name: Jack Williamson | Email Address: JackWilliamson@roseroad.org.uk | Contact Number: 023 8072 1202 |
| Arrival On Site: 10:45am-11am Departure time: 11:30am | Companies Risk Assessment link: [in development, will send on dedicated Teams chat when complete] | Companies Insurance Link: [sent on dedicated Teams chat] | Companies Public Liability Information Link: [same as Companies Insurance Link, sent on dedicated Teams chat] |

If you are inviting a external company or individual on to campus for your event you will be required to submit this form to legalservices@soton.ac.uk at least 15 working days before the event. For more guidance on this please click here.

| PART 2 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| General Considerations |  |  |  |  |  |  |  |  |  |  |
| Slips, trips and falls | Soft tissue injury e.g., sprain, bruising. Potential broken ankle or other breaks i.e. wrists etc. | All participants and organisers/staff and spectators | 2 | 3 | 6 | All boxes and equipment to be stored away from the main meeting area, e.g. stored under tables. Any cables to be organised as best as possible, e.g. cable ties to be used if necessary. Floors to be kept clear and dry, and visual checks to be maintained throughout the meeting by organisers. Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. Report any trip hazards to facilities teams/venue staff asap. If cannot be removed, mark off with hazard signs. | 1 | 3 | 3 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. SUSU incident reporting guide |
| Fire | Smoke inhalation, burns and more severe. Risk of extreme harm. | All participants and organisers/staff and spectators | 2 | 5 | 10 | Those leading the session must ensure they are aware of and fully understand the venue or locations fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the participants the nearest emergency exit routes at the start of a session, and the importance of leaving calmly in case of an emergency. Avoid build-up of debris in the activity area. Consider accessibility requirements | 1 | 5 | 5 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. SUSU incident reporting guide |
| Manual handling, including setting up of equipment. E.g. table and chairs | Bruising or broken bones from tripping over table and chairs. | Meeting organisers and attendees | 2 | 3 | 6 | Make Event Volunteers aware of the potential risks, follow manual handling guidelines Ensure that at least 2 people carry tables and large objects. Setting up tables will be done by organisers. Work in teams when handling other large and bulky items. Request tools to support with move of heavy objects- SUSU Facilities/venue. E.g., hand truck, dolly, skates Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable. | 1 | 3 | 3 | Seek assistance if in need of extra help from facilities staff/venue staff if needed Seek medical attention from SUSU Reception if in need Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Overcrowding / Inadequate Meeting Space | Physical injury, distress, exclusion | Event organisers and attendees | 2 | 3 | 6 | Do not push/shove. If large crowds form, barriers can be requested by SUSU facilities team (if available on the day) to assist with crowd management. Ensure space meets needs of members e.g. considering location & accessibility of space (use AcessAble database to check accessibility information of venues). Consider all accessibility requirements and ensure that the area chosen is as accessible as possible. Committee to consult members on needs and make reasonable adjustments where possible Provide remote meeting options for members. | 1 | 3 | 3 | Seek medical attention if problem arises With support from a SUSU Activities coordinator Inform UoS security team of the event (– on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk) and liaise with them on need for security teams on the day All incidents are to be reported on as soon as possible ensuring the duty manager/health and safety officer has been informed. Follow SUSU incident reporting guide |
| Electronics | Risk of eye strain, electric shock, injury due to trip hazards, causing fire | Committee and attendees | 2 | 4 | 8 | Ensure regular breaks (ideally every 20mins) when using screens Ensure screen is set up to avoid glare, is at eye height where possible Ensure no liquids are placed near electrical equipment Ensure all leads are secured with cable ties/mats etc Ensure all relevant equipment has passed PAT testing | 1 | 4 | 4 | Request support and advice from SUSU IT/Tech teams e.g. via activities team Seek medical attention as required. Follow SUSU incident reporting guide |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents during club or society activity could pose a reputational risk to the club, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name intro disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring that any incidents involving public or others are recorded and addressed. Ensuring all members are reminded that they are representing the club/society, SUSU and the University, often in branded clothing. Members are reminded that they need to adhere to SUSU’s Code of Conduct. Consider risks at activities as well as digital presence (e.g. social media posts). Ensure proper moderation of public SVGE chat rooms. | 1 | 1 | 1 |  |
| Financial Risk: For the club or society, or potentially even SUSU if the club/soc finds itself in difficulty. | Club or society activity costing more than planned, weakening their financial position. Incidents with members of the public, participants, staff or members causing lawsuits and financial penalties. | The club or society Members subject to lawsuits SUSU if required to assist. | 1 | 1 | 1 | Clubs and societies required to complete financial forecasting and budget for the year. All encouraged to review membership fees yearly to ensure they are able to comfortably cover costs. SUSU can offer clubs and societies loans – these will need to be agreed and a payment schedule decided upon. Clubs and societies that have to rely on a loan will be subject to development plans to ensure their future is protected. | 1 | 1 | 1 |  |
| Members leaving an event/activity alone or without notifying others. | Getting lost, increased risk to personal safety. | Event organisers, event attendees | 2 | 3 | 6 | If a person leaves without warning all efforts will be made to locate them. Stress however that attendees are responsible for their individual safety. Committee to supervise the event. | 1 | 2 | 2 | Follow SUSU incident reporting guide Call emergency services as required. |
| Legal Compliance: Club or society activity going against set law. This includes breaches of the freedom of speech act | Fines imposed upon the student group as well as SUSU. Jail sentences. Reputational risk to the student group, SUSU and the wider University | The club or society, committee and members, SUSU or the Wider University. | 1 | 1 | 1 | All clubs and societies should ensure they are following set law at all times. If ever in doubt, they will contact the Activities team prior to the activity taking place. All who wish to bring in an external speaker must follow due process, available here This will be looked over by the University Legal Services team, and may require security being consulted and an extra risk assessment being submitted. | 1 | 1 | 1 |  |
| Medical Issues: Pre-existing and process for any that appear during | Members may sustain injury /become unwell Pre-existing medical conditions, sickness, distress Death | Members, committee | 1 | 5 | 5 | Advise participants to bring their personal medication if it might be required. All should know the location of the nearest first aider. Members do not need to disclose medical information to committee (GDPR), but all committee should know how to find a first aider and help quickly. (In SUSU, so contact reception.) If no-one can be found, contact campus Security – 02380 59331 Contact emergency services as required – 111/999. Members can be referred to The Student Hub (02380 599 599, studenthub@soton.ac.uk) in case of distress | 1 | 4 | 4 | Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident reporting guide |
| Charity Fundraising |  |  |  |  |  |  |  |  |  |  |
| Handling and storing Card Readers – Charity Fundraiser | - Theft - Individuals being mugged/robbed - Loss/misplacement leading to financial loss | Members and Participants | 3 | 4 | 12 | Southampton RAG procedures will be followed: - Charity Event form completed, and RAG approval will be given - Event risk assessment to be approved by activities team - Should not be storing money - all donations to be taken via online methods (Tiltify if possible, otherwise other method to be discussed with and approved by SUSU) | 2 | 3 | 6 | No Cash to Be Accepted at all. In the event of theft committee members will: - Highlight the incident to any community police officers in the area/report to 111 - Report to SUSU Duty manager and Complete a SUSU incident report |
| Abuse of Members and Volunteers | Members of the public or students may act violently towards volunteers. Eg: Because they disagree with the cause. | Volunteers and Participants | 4 | 3 | 12 | No Volunteers are ever to be left alone. Always have at least 2 people at an Event. | 2 | 3 | 6 | - Report to SUSU Duty manager and Complete a SUSU incident report - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Venue/Location considerations | Require certain licenses/sign off | Organisers, Participates, SUSU | 1 | 4 | 4 | Ensure the event has the required sign off by the SUSU’s security teams. Ensure proper booking process is followed. The event will not go forward without Activities Approving the Risk Assessment. On campus - Ivvy Booking - Risk assessment - Contract | 1 | 2 | 2 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. Follow SUSU incident report policy |
| Lone working | Stolen goods, injury to individual. | Volunteers | 3 | 3 | 9 | Ensure no one is left alone as a volunteer at a fundraising event. | 3 | 1 | 3 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. Follow SUSU incident report policy |
| Adverse weather | Injury, Illness, Slipping, Burns | Event organisers, event attendees, | 4 | 3 | 12 | Lead organiser to check the weather is suitable for activities on the day (primarily travel to event) Cancellation window is 2 weeks Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, hydrate If Cancellation is required ensure all relevant parties are contacted. SUSU – subookings@soto.ac.uk | 4 | 1 | 4 | If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date |
| Fatigue (Including dehydration and hunger) | Participants and volunteers on the day may become tired if they have not properly slept, eaten or drank. | Event Attendees and Organisers | 3 | 3 | 9 | - All participants and volunteers have been advised to properly eat and drink prior to and during their periods. - Volunteers have also been encouraged to bring food and drink with them to consume during their go. - Access to a Water Fountain/Tap throughout the event. | 2 | 2 | 4 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Use of Toilets prior to SUSU officially opening | Event volunteers and organisers not having any facilities to use. | Organisers and Volunteers | 2 | 2 | 4 | - Requested for toilet facilities to be left open for duration of event. - Pre event conversations had with university security team. - Facilities/security team to leave entrance open for toilet use. | 1 | 2 | 2 | - If building is not left open contact university security - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. Follow SUSU incident report policy |

| # PART 2B – Action Plan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # Risk Assessment Action Plan |  |  |  |  |  |  |
| # Part no. | # Action to be taken, incl. Cost | # By whom | # Target date | # Review date | # Outcome at review date |  |
| # 6 | # Committee member to check weather and make a call if event is okay to go ahead | Relevant committee members – president to ensure complete. | 13/03/2026 |  |  |  |
| # 7 | # Committee member to ensure all supplies are there, e.g. access to toilets | # Relevant committee members – president to ensure complete. | # 15/03/2026 |  |  |  |
| # 2 | Complete a Charity Event form and send this to suactivties@soton.ac.uk | Relevant committee members – president to ensure complete. | Immediate, 26/02/2026 |  |  |  |
| # 3 | Committee to re-read and share SUSU Expect respect policy | Relevant committee members – president to ensure complete. | Immediate, 27/02/2026 |  |  |  |
| # 5 | Set Up Fundraising Platform | Relevant committee members – president to ensure complete. | 09/03/2026 |  |  |  |
| # 1 | # Complete a Request for Consideration of an Activity under the University of Southampton’s Code of Practice to Secure Freedom of Speech within the Law form and send this to legalservices@soton.ac.uk | Relevant committee members – president to ensure complete. | # Immediate, 22/02/2026 |  |  |  |
| # 4 | # Discuss with SU Activities and Security to ensure that toilets and first aid are available throughout the event | Relevant committee members – president to ensure complete. | # 02/03/2026 |  |  |  |
| # Responsible committee member signature: AMilne |  |  |  | # Responsible committee member signature: David |  |  |
| # Print name: Andrew Milne (preferred name Bethany Milne) - Social And Events Secretary |  |  | # Date 26/02/2026 | # Print name: David Deng - Webmaster |  | # Date 02/03/2026 |

Assessment Guidance

| - Eliminate | Remove the hazard wherever possible which negates the need for further controls | If this is not possible then explain why |  |
| --- | --- | --- | --- |
| - Substitute | Replace the hazard with one less hazardous | If not possible then explain why |  |
| - Physical controls | Examples: enclosure, fume cupboard, glove box | Likely to still require admin controls as well |  |
| - Admin controls | Examples: training, supervision, signage |  |  |
| - Personal protection | Examples: respirators, safety specs, gloves | Last resort as it only protects the individual |  |

| LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 | 4 | 8 | 12 | 16 | 20 |
|  | 3 | 3 | 6 | 9 | 12 | 15 |
|  | 2 | 2 | 4 | 6 | 8 | 10 |
|  | 1 | 1 | 2 | 3 | 4 | 5 |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  |  | IMPACT |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

Risk process

- Identify the impact and likelihood using the tables above.

- Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.

- If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.

- If the residual risk is green, additional controls are not necessary.

- If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable.

- If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.

- Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.

- The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |