This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group. You will also need to complete a charity form linked here.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: Isobel Hayes | Email Address for Main Contact: ih7g23@soton.ac.uk | Club or Society: Wildlife society | Contact Number: 07786477980 |
| 1B) Event Information: |  |  |  |
| Event Name: | Event Date: 22nd October, 2025 | Event Venue/Venues: 06/1077 | Total Attendees: This is uncertain; the max will be 81 |
| Event Timings: | Set Up: 18:45/19:00 Event Start: 19:30 Event End: 21:00 Pack Down: 21:30 |  |  |
| Event Break down: (This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity.) | 18:45/19:00 -set up 19:00 – Doors Open 19:00 –19:30 – arrival of audience (tickets are checked at door by committee member) 19:30 – 20:00 – Chris Packham introduction; his recent work, what his role is within Wild Justice 20:00 – 20:30 – Discussion into the work of wild justice on the planning/infrastructure bill; questions will be asked by a member of wild soc committee (these can be sent in advance to SUSU activities team if needed) 20:30 – 21:00 – Questions put forward to the audience 21:00- 21:30 – Set down |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Boxoffice: You can set up Box-office tickets through your group's hub page for guidance on this click here: | Yes ‘Chris Packham on; Wild Justice, and advocating for nature’ | How Much Are your Tickets? And how many are available? | Tickets are free, there will be 71 available – 10 will be reserved for committee members |
| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | - Chris Packham is an activist, author, naturalist and TV presenter, alongside a director at Wild Justice. - He has agreed to give a talk to wildlife society surrounding the activities of Wild Justice, specifically around the planning and infrastructure bill. - The date agreed upon is the 22nd October, 7pm, in the room 06/1077 The event will be ticketed, and advertised on SUSU box office. - The event will involve Chris talking about this work, and a member of wildlife society asking him any relevant questions on environmental legislation Questions will then be opened to the audience at the end. |  |  |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | Event lead: Wildlife Society Person in discussion with Chris Packham; Isobel Hayes (president) Doors/ tickets; Vee Arias (Social Secretary) Other committee present; - Harry Woollard (Mammalogy rep) - Charlie Young (Mycology Rep) - Lauren Hamilton (treasurer) - James Lawson (Insect Rep) - Michael Moore-Saxton (Herpetology Rep) |  |  |
| Tech Requirements (For a full list of what you can hire click here) | 2x Microphones Screen with presentation |  |  |
| Facilities Requirements | n/a |  |  |
| Food Requirements (For full guidance on this click here) | No food requirements; members can bring snacks should they wish to do so. |  |  |
| Security & First Aid Requirements (Who are the qualified first aiders in the group should a medical emergency occur?) | To be confirmed |  |  |
| Decorations that you are providing | n/a |  |  |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | No budget expected as this is a free event for members and we only need the room |  |  |
| 1C) Only Required If External Company/External Speaker On Site For Event |  |  |  |
| Business Name: Wild Justice | Business Contact Name: Wild Justice/Chris Packham | Email Address: pa@chrispackham.co.uk | Contact Number: to be confirmed |
| Arrival On Site: 19:00 Departure time: 21:30 | Companies Risk Assessment link: | Companies Insurance Link: | Companies Public Liability Information Link: |

If you are inviting a external company or individual on to campus for your event you will be required to submit this form to legalservices@soton.ac.uk at least 15 working days before the event. For more guidance on this please click here.

| PART 2A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Adverse Weather | - Injury - Illness - Slipping - Burns | All who attend | 4 | 3 | 12 | - Lead organiser to check the weather are suitable for activities on the day - SUSU/UoS Facilities team checks of buildings and spaces prior to the event - Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites - In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, hydrate | 4 | 1 | 4 | - If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Fire hazard | Smoke inhalation, burns. Risk of extreme harm | All participants and organisers, any staff and spectators | 2 | 5 | 10 | Those leading the session must ensure they are aware of and fully understand the venue or location’s fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the participants the nearest emergency exit routes at the start of a session, and the importance of leaving calmly in case of an emergency. Avoid build-up of debris around seating and doors. Consider accessibility requirements. | 2 | 2 | 4 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident reporting guide |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents causing reputational damage to the group, Southampton University Students’ Union or Southampton University itself. | Audience, Chris Packham, Committee | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring all members are reminded that they are representing the club/society, SUSU and the University, often in branded clothing. Members are reminded that they need to adhere to SUSU’s Code of Conduct. Consider risks at activities as well as digital presence (e.g. social media posts) | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Follow SUSU incident reporting guide |
| Slips, trips and falls | Physical injury | Event organisers and attendees | 2 | 4 | 8 | - All boxes and equipment to be stored away from main protest area, e.g. stored under tables - Floors to be kept clear and dry, and visual checks to be maintained throughout the event by organizers. - Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. - Report any trip hazards to facilities teams asap. If cannot be removed mark off with hazard signs | 1 | 4 | 4 | - Seek medical attention from SUSU Reception if in need - Contact facilities team via SUSU reception - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Setting up of Equipment. E.g. Table and chairs | Bruising or broken bones from tripping over table and chairs. | Event organisers and attendees | 2 | 3 | 6 | - Make stall operators aware of the potential risks, follow manual handling guidelines - Ensure that 2 people carry tables. - Setting up tables will be done by organisers. - Work in teams when handling other large and bulky items. | 1 | 3 | 3 | - Seek assistance if in need of extra help from facilities staff if needed - Seek medical attention from SUSU Reception if in need - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Overcrowding | Physical injury | Event organisers and attendees | 2 | 4 | 8 | - Do not push/shove - If large crowds form, barriers can be requested by SUSU facilities team (if available on the day) to assist with crowd management. - Book during quieter times when less activities taking place on Redbrick/book all available space - Inform other bookings on the Redbrick/in the area of the event | 1 | 4 | 4 | - Seek medical attention if problem arises - With support from a SUSU Activities coordinator Inform UoS security team of the event (– on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk) and liaise with them on need for security teams on the day - Security team may inform police of the event if required (e.g. marches) - Contact emergency services if needed - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Disturbance to public, students and staff | Conflict, noise, crowds | Event organisers and attendees, general public | 2 | 2 | 4 | - Events planned for redbrick avoiding residential areas - UoS Security Teams informed of the event - Everybody will be encouraged to stay together as a group - shouting, chants, whistles etc. will be kept to a minimum around busy university buildings and residential areas - If applicable book space during quieter times when less activities taking place in local lecture theatres (lunch, Wednesday afternoons) | 1 | 2 | 2 | - With support from a SUSU Activities coordinator Inform UoS security team of the event -University Security 24 hours – on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk - Inform UoS/SUSU communications team of the event- can brief others via SUSSSED |
| Counter protest, discrimination against the demonstration | Assault, Violence or threatening/ Aggressive Behaviour | Event organisers and attendees | 2 | 4 | 8 | - Event planned for Highfield campus- a route well signposted and known for students - Leaders to advise all participants to not engage/respond to any protests, aggressive behaviour- if safe to do so will encourage group to move on and remove themselves from situation- The event will be ended and students advised to return to campus if this continues - Prior information about event and what to expect given out so participants know what to expect via Facebook/social media posts - Participants made aware they could join and leave the event at any time. - Ensure that people are aware that this is an open space for discussion to discourage protest. | 1 | 4 | 4 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. - Any incidents will be reported via UoS reporting tools - Contact emergency services if needed - Organisers will, following the event, share relevant information on support/signpost via social media channels etc. |
| Talks/debates - subjects that could be sensitive or personal to some members | The audience feels negative emotions around the topic or becomes distressed by images or events shown/discussed. | Members | 2 | 3 | 6 | Prior information about event and what to expect given out so participants know what to expect. Members made aware they could leave the event at any time. Members referred to enabling/signpost to support organisations (e.g. via presentation slide, or by speakers/committee members) SUSU reporting tool available | 1 | 3 | 3 | - Organisers will, following the event, share relevant information on support/signpost- Facebook/email/newsletter - Committee Wide Training - Seek guidance from activities/SUSU advice centre/UoS enabling team as required - committee WIDE training |
| (Additional hazards if applicable) | (possible consequences) | (who may be affected) |  |  |  | - (Control Measures) |  |  |  | - (Additional measures) |

| # PART 2B – Action Plan |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # Risk Assessment Action Plan |  |  |  |  |  |  |  |  |
| # Part no. | # Action to be taken, incl. Cost | # By whom | # Target date |  | # Review date |  | # Outcome at review date |  |
| # 1 | # Tickets publicised on Box Office | # Committee | # 15/10/25 |  |  |  |  |  |
| # 2 | # UoS Security Team and SUSU Activities team informed of talk | # Isobel Hayes | # 10/10/25 |  |  |  |  |  |
| # 3 | # Legal team informed | # Isobel Hayes | # Completed |  |  |  |  |  |
| # 4 | # Microphones to be hired | # Isobel Hayes | # 13/10/25 |  |  |  |  |  |
| Responsible committee member signature: Isobel Hayes # At least 2 committee members need to sign Part B |  |  |  |  | Responsible committee member signature: Isobel Robertson # At least 2 committee members need to sign Part B |  |  |  |
| # Print name: (committee member name) |  |  |  | # Date: (09/10/25) |  | # Print name: Isobel Robertson |  | # Date: 09/10/25) |

Assessment Guidance

| - Eliminate | Remove the hazard wherever possible which negates the need for further controls | If this is not possible then explain why |  |
| --- | --- | --- | --- |
| - Substitute | Replace the hazard with one less hazardous | If not possible then explain why |  |
| - Physical controls | Examples: enclosure, fume cupboard, glove box | Likely to still require admin controls as well |  |
| - Admin controls | Examples: training, supervision, signage |  |  |
| - Personal protection | Examples: respirators, safety specs, gloves | Last resort as it only protects the individual |  |

| LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 | 4 | 8 | 12 | 16 | 20 |
|  | 3 | 3 | 6 | 9 | 12 | 15 |
|  | 2 | 2 | 4 | 6 | 8 | 10 |
|  | 1 | 1 | 2 | 3 | 4 | 5 |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  |  | IMPACT |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

Risk process

- Identify the impact and likelihood using the tables above.

- Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.

- If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.

- If the residual risk is green, additional controls are not necessary.

- If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable.

- If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.

- Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.

- The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |