This document contains both ‘Part 1: Event Information’ AND ‘Part 2: Risk Assessment’. Both parts are required to be completed by the organising group.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Information |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact for The Event: Ibrahim Khan | Email Address for Main Contact: Ik4g21@soton.ac.uk | Club or Society Name: Islamic Society | Contact Number: +44 7449 141494 |
| 1B) Event Information: |  |  |  |
| Event Name: Eid al-Adha | Event Date: 27/05/2026 (can also be on the 26 or 28, depending on lunar sighting). | Event Venue/s: Turner Sims Lawn (outside the prayer room) | Total Attendees: ~ 800 |
| Event Timings: | Set Up: 6:00 Event Start: 8:00 Event End: 11:00 Pack Down: 11:00 |  |  |
| Event Breakdown This includes everything happening at your event, including fundraising, food provision, any performance or sporting activity, etc. | Set Up – 6:30pm to 8:00pm • Committee arrives at the venue and conducts a brief safety and venue check. • Prayer area arranged (clear floor space organised into prayer rows). • Food stalls/tables set up around prayer room for distribution after the prayer. • Tables arranged for food items and drinks. • Decorations and Eid-themed banners placed around the venue. • Food items organised at serving points (mini pastry platters, cookie platters, two-bite brownies, sweets and chocolates, and tropical juice). • Walkways and fire exits checked to ensure they remain clear and unobstructed. • Volunteers briefed and assigned roles (crowd guidance, prayer row organisation, food distribution, general assistance). Event Start – 8:30pm • Guests begin arriving and are welcomed by committee members. • Volunteers guide attendees into organised prayer rows and ensure clear walkways for movement. • Committee members remain stationed at entry points to help manage the flow of attendees (expected attendance approximately 800 people). Main Programme (8:00am – 10:45am) • Guest arrival and settling into prayer areas. • Brief welcome and instructions for the prayer. • Eid prayer ceremony conducted. • Short Eid message/reflection following the prayer. • Opening of food stalls and distribution of refreshments including: - Mini pastry platters (Costco) - Cookie platters (Costco) - Two-bite brownies (Costco) - Sweets and chocolates (Costco) - Sunpride Tropical Juice • Social interaction and community celebration as attendees move through food stalls. • Committee and volunteers monitor food areas to prevent congestion and maintain safe movement around the venue. Event End – 11:00pm • Closing announcements and thanks to attendees and volunteers. • Guests begin exiting the venue in a calm and orderly manner. • Committee members ensure exits, corridors, and walkways remain clear. • Lost-property check and general venue walkthrough. Pack Down – 11:00pm to 11:30pm • Removal of decorations and signage. • Food stalls cleared and waste disposed of appropriately. • Tables moved back to original layout where required. • Final safety and cleanliness check before leaving the venue. |  |  |
| Overview of event concept Description of the activities taking place. This includes everything happening at your event e.g. fundraising, food provision and any performance or sporting activity) | The Islamic Society (ISoc) will be hosting an Eid al-Adha prayer ceremony followed by a short food celebration for students and members of the university community. The event will take place at Turner Sims Lawn and is expected to host approximately 800 attendees. Activities will begin with an organised congregational Eid prayer held in the open space, with attendees arranged in prayer rows. Following the prayer and a short Eid message, attendees will be invited to visit food stalls set up around the venue to collect light refreshments. The food provided will consist of pre-packaged items including mini pastry platters, cookie platters, two-bite brownies, sweets and chocolates, along with Sunpride Tropical Juice. The event is intended as a short community celebration of Eid al-Adha, allowing attendees to gather, pray together, and socialise. Movement around the venue will primarily occur during arrival and during the food distribution period. The event will be supervised by ISoc committee members and volunteers who will manage crowd flow, food distribution areas, and general safety throughout the event. |  |  |
| Volunteers hosting the event List all committee and volunteers that will be present and responsible for the event, as well as their role. | The event will be organised and supervised by members of the Islamic Society (ISoc) committee. All committee members will be present during the event and will take responsibility for the safe running and management of activities. Committee roles will include overseeing event coordination, managing attendee entry and crowd flow, organising the prayer area, supervising food distribution, and monitoring general safety throughout the event. Additional volunteers may be recruited closer to the event date to assist with tasks such as guiding attendees to the prayer area, helping manage queues at food stalls, and supporting with set-up and pack-down. All volunteers will be briefed by the committee prior to the start of the event and will operate under the supervision of the ISoc committee. |  |  |
| Food provision For full guidance on this click here. | Food will be pre-packaged items purchased from Costco Wholesale and provided to attendees through organised food stalls. Items include: • Mini pastry platters • Cookie platters • Two-bite brownies • Assorted sweets and chocolates Drinks will include Sunpride Tropical Juice. All food items are pre-prepared and packaged by the supplier and will only be distributed by ISoc committee members and volunteers. No cooking or food preparation will take place at the venue. |  |  |
| Security & First Aid Requirements Is external first aid or security being hired? Who are the qualified first aiders in the group should a medical emergency occur? | N/A |  |  |
| Provisional Budget If you would like a more extensive budget tracker, click here. | Projected ticket income: £0 (event is free to attend) Food and refreshments (pastries, cookies, brownies, sweets and juice): Donated/Privately funded / community contributions Decorations and event materials: £0 (existing society materials) Venue: £0 (university space) Total projected cost to ISoc: £0 Projected profit: £0 (community celebration event) |  |  |
| 1C) Only required if an external company/external speaker will be on site for the event - If you are inviting an external speaker to campus for your event, you are required to submit this form to legalservices@soton.ac.uk at least 15 working days before the event. For more guidance on this please click here. |  |  |  |
| Business Name: N/A | Business Contact Name: N/A | Email Address: N/A | Contact Number: N/A |
| Arrival On Site: N/A Departure time: N/A | Company’s Risk Assessment Link: N/A | Company’s Insurance Link: N/A | Company’s Public Liability Information Link: N/A |

Part 2A

Risk Assessment

| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |  |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Slips, trips and falls | Physical injury | Event organisers and attendees | 2 | 3 | 6 | All boxes and equipment to be stored away from main meeting area, e.g. stored under tables. Floors to be kept clear and dry, and visual checks to be maintained throughout the meeting by organisers. Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. Report any trip hazards to facilities teams/venue staff asap. If cannot be removed, mark off with hazard signs. | 1 | 4 | 4 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible, ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Manual handling, including setting up of equipment. E.g. table speakers and carpet. | Bruising or broken bones from tripping over table and chairs. | Meeting organisers and attendees | 2 | 3 | 6 | Follow manual handling guidelines. Ensure that at least 2 people carry tables or other bulky items. Setting up tables will be done by organisers. Work in teams when handling other large and bulky items. Request tools to support with the moving of heavy objects from SUSU Facilities/venue. E.g. hand truck, dolly, skates. Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable. | 1 | 3 | 3 | Seek assistance from facilities staff/venue staff if needed. Seek medical attention from SUSU/venue Reception if in need. Contact emergency services if needed. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Overcrowding / Inadequate Meeting Space | Physical injury, distress, exclusion | Event organisers and attendees | 2 | 3 | 6 | Do not push/shove. If large crowds form, request barriers from SUSU facilities team or external venue to assist with crowd management. Committee checks on space, lighting, access, tech available, etc. Use ticketing system (SUSU Box Office) for regular sessions/meetings to avoid exceeding venue capacity. Ensure space meets needs of members e.g. considering location & accessibility of space (use AcessAble database to check accessibility information of venues). If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. Committee to consult members on needs and make reasonable adjustments where possible Provide remote meeting options for members where possible. | 1 | 3 | 3 | Seek medical attention if problem arises. Liaise with SUSU reception/Activities Team and UoS Room Booking team on available spaces for meetings. Postpone meetings where space cannot be found. Welfare Officer to complete WIDE training. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents causing reputational damage to the group, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name into disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring all members are reminded that they are representing the club/society, SUSU and the University, often in branded clothing. Members are reminded that they need to adhere to SUSU’s Code of Conduct. | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Report any incidents to the Activities Team. |
| Travel by foot | Disturbance to neighbourhood, participants getting lost, increased risk to personal safety, vehicle collision causing serious injury | Event organisers, event attendees, Members of the public | 4 | 3 | 12 | Members are responsible for their individual safety and are expected to act sensibly. Local venues known to UoS students chosen. Event organisers will be available to direct people between venues. Attendees will be encouraged to identify a ‘buddy’, this will make it easier for people to stay together. They will be encouraged (but not expected) to look out for one another and check in throughout the night where possible. Avoid large groups of people totally blocking the pavement or spilling in to the road. Anybody in the group who is very drunk or appears unwell and therefore not safe should be encouraged to go home ideally with someone else. If required a taxi will be called for them (ideally SUSU Safety Bus will be used, or Radio Taxis). Be considerate of other pedestrians and road users, keep disturbance and noise down. | 2 | fire | 4 | Where possible venue chosen for the event will be local/known to members and within a short travel distance for members. Contact emergency services as required 111/999. Incidents are to be reported as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Travel by car, train, bus, plane when leaving the local area. | Vehicle collision – causing anything from minor to severe injuries, as well as mental health issues. | Members, those driving, members of the public | 2 | 5 | 10 | Group committee to check that drivers have the relevant licences and insurance for the mode of travel. This includes if they have completed a SUSU minibus test. Members expected to drive or travel in a sensible manner, with those doing otherwise to face disciplinary action (from the club/society in the first instance). Can cause reputational issues, especially if driving SUSU branded vehicles. Importance of this to be reminded. | 1 | 5 | 5 | Contact emergency services as required 111/999. Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Medical emergency | Members may sustain injury /become unwell Pre-existing medical conditions, sickness, distress | Members | 1 | 5 | 5 | Advise participants to bring their personal medication if it might be required. Members/Committee to carry out first aid if necessary and only if qualified and confident to do so. Contact emergency services as required 111/999. Contact SUSU Reception/venue staff for first aid support. Members can be referred to The Student Hub (02380 599 599, studenthub@soton.ac.uk) in case of distress. | 1 | 4 | 4 | Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Fire | Smoke inhalation, burns. Risk of extreme harm. | All participants and organisers, any staff and spectators | 1 | 5 | 5 | Those leading the session must ensure they are aware of and fully understand the venue or location’s fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the participants the nearest emergency exit routes at the start of a session, and the importance of leaving calmly in case of an emergency. Avoid build-up of debris in the activity area. Consider accessibility requirements. | 1 | 4 | 4 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Anti-social, violent, or offensive behaviour | Disturbance to the neighbourhood, reputational damage, injury and distress as a result of violence | Event organisers, event attendees, public | 2 | 5 | 10 | Bouncers/security will be present at most licensed venues. Bar/venue security staff will need to be alerted and emergency services called as required. Do not personally engage with any violent behaviour. Stay safe and inform the bar staff/police if necessary. The consumption of alcohol will take place at licensed premises. The conditions on the license will be adhered to and alcohol will not be served to customers who have drunk to excess. Committee to select ‘student friendly’ bars/clubs and contact them in advance to inform them of the event. Society to follow and share with members Code of conduct/SUSU Expect Respect policy. | 1 | 3 | 5 | If the situation becomes very serious and results in the participant being arrested then it will be made clear that they cannot be accompanied to the police station. Follow SUSU incident report policy. Call emergency services as required. |
| Adverse weather | Hypo- or hyperthermia, illness, injury, slipping, burns | Event organisers, event attendees | 3 | 4 | 12 | Lead organiser to check the weather are suitable for activities on the day. Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites. In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, and to hydrate (especially if drinking alcohol). | 2 | 2 | 4 | If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date. Contact emergency services if needed. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Events Involving Food | Allergies Food poisoning Choking | All | 3 | 5 | 15 | Only order/buy food at establishments with appropriate food hygiene (EHO) rating. Food to only be provided/eaten when other activities are stopped. Follow good food hygiene practices - no handling food when ill, tie back hair, wash hands regularly using warm water and soap, refrigerate necessary products. For store-bought items/snacks, keep packaging to hand for ingredient and allergen information. | 1 | 5 | 5 | SUSU food hygiene level 2 course available for completion- requests made to Activities Team. Call for first aid/emergency services a required . Report incidents via SUSU incident report procedure. |
| Choking | Food getting stuck in the throat making it painful | Anyone eating | 2 | 5 | 10 | · Advise people to eat slowly · Advise people to not talk whilst eating · Advise people to chew food properly before swallowing · Have water bottles placed around the hall for people to use for free, a chocking person can have water which will help relieve them. · A committee member/volunteer will hand the chocking person water if they don’t. | 1 | 4 | 4 | Medical attention will be called if needed. |
| Food-borne illness | Attendees becoming unwell | Anyone eating | 3 | 3 | 6 | Ensure that the food is from a place that has a good hygiene rating and follows good food preparation guidelines. Advise people who are unwell not to attend | 1 | 3 | 3 | Medical attention will be called if needed. |
| Food Allergy | Example- a person with a nut allergy comes in contact with nuts resulting in an allergic reaction. | Anyone with an allergy. | 2 | 5 | 10 | · Ensure that it's made clear what allergens are in which foods, including the 14 most common allergens. · Ensure that anyone with an allergy carries an EpiPen with them · Ensure that allergen free food is clearly separated from food with allergens · Ensure that all food distribute on the day is pre-packaged and clearly labelled with the ingredients and allergens etc | 1 | 3 | 3 | Medical attention will be sought by calling emergency services if required. |
| Children attending the event | Potential disruptions, accidents, or injuries due to unsupervised children | All attendees |  |  |  | The behaviour and supervision of children attending the event will be the sole responsibility of their parent or guardian Parents/guardians must ensure their children remain under control and do not pose a risk to themselves or others. Signage will remind attendees of this responsibility. Event organisers will not be responsible for supervising children. |  |  |  | All incidents are to be reported as soon as possible ensuring the duty manager/health and safety officer have been informed. Call emergency services and University Security: Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 (Ext:3311). |
| Disturbance to public, students and staff | Conflict, noise, crowds | Event organisers and attendees, general public | 2 | 2 | 4 | Events planned for redbrick avoiding residential areas UoS Security Teams informed of the event Everybody will be encouraged to stay together as a group shouting, chants, whistles etc. will be kept to a minimum around busy university buildings and residential areas If applicable book space during quieter times when less activities taking place in local lecture theatres (lunch, | 1 | 2 | 2 | With support from a SUSU Activities coordinator Inform UoS security team of the event -University Security 24 hours – on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk Inform UoS/SUSU communications team of the event- can brief others via SUSSSED |
| Counter protest, discrimination against the demonstration/Campaign | Assault, Violence or threatening/ Aggressive Behaviour | Event organisers and attendees | 2 | 4 | 8 | Event planned for ISoc Society- a route well signposted and known for students Leaders to advise all participants to not engage/respond to any protests, aggressive behaviour- if safe to do so will encourage group to move on and remove themselves from situation- The event will be ended and attendees advised to leave if this continues Prior information about event and what to expect given out so participants know what to expect via Facebook/social media posts Participants made aware they could join and leave the event at any time. Ensure that people are aware that this is an open space for discussion to | 1 | 3 | 5 | Event organisers to call University Security if necessary. Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 (Ext: 3311) Building 32, University Road Highfield Campus. |
| Insufficient Fire Safety awareness | If a fire alarm is triggered, people may not know where to go- Crushing, falls, burns and smoke inhalation arising from induced panic, reduced space in buildings and external walkways, obstructed fire exits, build-up of flammable materials i.e. waste cardboard/boxes | Those in the vicinity | 2 | 5 | 10 | ensure that members know where the nearest fire exist are and the meeting place is outside, should it be needed Build-up of rubbish is to be kept to a minimum. Excess build up is to be removed promptly and deposited in the designated areas. | 1 | 5 | 5 | All incidents are to be reported as soon as possible ensuring the duty manager/health and safety officer have been informed. Call emergency services and University Security: Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 (Ext:3311). |

| PART 2B – Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Assessment Action Plan |  |  |  |  |  |  |  |
| Part no. | Action to be taken, incl. Cost | By whom | Target date |  | Review date | Outcome at review date |  |
| 1 | Risk assessment shared with all organisers and checked through before the event Follow SUSU Food Provision Guidance for events involving home-cooked/prepared food or external catering. | Socials Officer | 27/04/2026 |  | 25/04/2026 |  |  |
| 2 | Committee to read and share SUSU Expect Respect Policy | Socials officer | 27/04/2026 |  | Continuous |  |  |
| 3 | Complete a financial assessment of the event | Treasure | 27/04/2026 |  | 27/04/2026 |  |  |
| 4 | Liaise with external companies (e.g. venue, DJ, caterers) for all necessary paperwork. | President | 27/04/2026 |  | 27/04/2026 |  |  |
| 5 | Make sure table and chairs are not disturbing people and it’s somewhere close to the designated area to reduce potential falls, slips. | Welfare officer | 27/05/2026 |  | 27/05/2026 |  |  |
| 6 | Packing up and Cleaning | Prayer room officer | 27/05/2026 |  | 27/05/2026 | Once attendees have been dismissed, volunteers to manage exits and afterwards pack up and clean up. |  |
| 7 | Adverse Weather | President | 27/05/2026 |  | 27/05/2026 | Lead organiser to check the weather are suitable for activities on the day and notifying attendees if plans need to change. |  |
| 8 | Manage Crowd | Prayer room officer | 27/05/2026 |  | 27/05/2026 | Attendees to be briefed from initial announcements, and volunteers to usher and control any crowd. |  |
| 9 | Set Up PA system and prayer mats | Prayer room officer | 27/05/2026 |  | 27/05/2026 | A few volunteers are trained for manual handling and technicality of the PA system. To also use the green space power outlet. To move carpets from prayer room to green space and spread them across for prayer. |  |
| Responsible committee member signature 1: |  |  |  |  | Responsible committee member signature 2: |  |  |
| Print name: Abubakar Ali Yusuf |  |  |  | Date: 14/05/2026 | Print name: second committee Ibrahim Khan |  | Date: 14/05/2026 |

Assessment Guidance

| - Eliminate |  |  |  |  | Remove the hazard wherever possible which negates the need for further controls |  |  |  | If this is not possible then explain why |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Substitute |  |  |  |  | Replace the hazard with one less hazardous |  |  |  | If not possible then explain why |  |
| - Physical controls |  |  |  |  | Examples: enclosure, fume cupboard, glove box |  |  |  | Likely to still require admin controls as well |  |
| - Admin controls |  |  |  |  | Examples: training, supervision, signage |  |  |  |  |  |
| - Personal protection |  |  |  |  | Examples: respirators, safety specs, gloves |  |  |  | Last resort as it only protects the individual |  |
| LIKELIHOOD | 5 | 5 | 10 | 15 |  | 20 | 25 |
|  | 4 | 4 | 8 | 12 |  | 16 | 20 |
|  | 3 | 3 | 6 | 9 |  | 12 | 15 |
|  | 2 | 2 | 4 | 6 |  | 8 | 10 |
|  | 1 | 1 | 2 | 3 |  | 4 | 5 |
|  |  | 1 | 2 | 3 |  | 4 | 5 |
|  |  | IMPACT |  |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |