This document contains both ‘Part 1: Event Plan’ AND ‘Part 2: Risk Assessment’. Both parts are required to be completed by the organising group.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact for The Event: Hanan Roble | Email Address for Main Contact: somsoc@soton.ac.uk | Club or Society Name: Somali Society led event, in collaboration with MSF | Contact Number: 07397108621 |
| 1B) Event Information: |  |  |  |
| Event Name: | Event Date: 03/12/2025 | Event Venue/s: Building 59p/Room 1005 | Total Attendees: 35-40 Attendees |
| Event Timings: | Set Up: 6PM – 7PM Event Start: 7PM Event End: 10PM Pack Down: 10PM-11PM |  |  |
| Event Breakdown This includes everything happening at your event, including fundraising, food provision, any performance or sporting activity, etc. | Example: 14:00 – 18:00 – Cooking and organising of food provision by Maryam Roble. 18:40 – 19:00 – Committee set up tables and decorations, event walkaround and sound check, team briefing 19:00 – Doors open 19:00-19:20 – Guests arrive (we scan their tickets, or they pay at the door using a SumUp Machine) and small-talk with one another, listening to some cultural music playing on the speakers, offering guests free squash, fizzy drinks, and beverages (potentially tea and coffee) 19:20-19:30 – Presentations regarding Somali culture. 19:30- 20:00 – Guests will partake in listening to music and playing their first game (ICE BREAKER) drinks will continue to be served to late comers. 20:00 – 20:30 –Guests will then play a second game (TRIVIA) 20:30-20:35 – Begin to serve food, individuals paying for the food using the SumUp machines. The food will consist of baked goods only. 20:35-21:00 – . Once food has been served/whilst food is being served by Maryam Roble, we’ll have a short mention of the charities involved i.e. Medicine Sans Frontiers, hopefully with a committee member of Friends of MSF. 21:00-21:45 – This time will be allotted for discussion and socialisation. 21:45-22:00 – Guests will begin to leave and be encouraged to leave. 22:00-23:00 – Committee members will stay to clean up after the event. |  |  |
| Is this a ticketed event? If so, please state the name of the ticket on Box Office You can set up Box Office tickets through your group's hub page. For guidance on this click here: | Yes, this is a ticketed event. The name of the ticket shall be ‘Somali Society Winter Charity Fundraiser’ | How much are your tickets? And how many are available? | The ticket price is £2 per ticket, with a maximum 50 tickets maximum |
| Overview of event concept Description of the activities taking place. This includes everything happening at your event e.g. fundraising, food provision and any performance or sporting activity) | A Winter Charity Fundraiser, organised by the Somali Society in collaboration with Friends of MSF, will be held on Wednesday, 3rd December 2025, from 7:00 PM to 10:00 PM at 59P/Room 1005, University of Southampton. The programme will include presentations on Somali Culture, as well as a presentation on the featured charity, Médecins Sans Frontières (MSF) (Charity Registration Number: 1026588). Attendees will have the opportunity to purchase a range of baked goods prepared by Maryam Roble, our events secretary, with a portion of all proceeds donated to MSF’s humanitarian relief efforts, this portion being all other funds raised external. The evening will also feature music, fostering a warm, educational, and inclusive atmosphere. This is an ALCOHOL-FREE EVENT. |  |  |
| Staff hosting the event List all committee and volunteers that will be present and responsible for the event, as well as their role. | Event lead: Fatima Ahmed and Hanan Roble Host: Fatima Ahmed and Hanan Roble Doors: Amir Saalah Food Lead: Maryam Roble has their Level 2 Food Hygiene and Allergen Certificate, so she will lead food organisation. Volunteers for set up: Hanan Roble and Maryam Roble |  |  |
| Tech Requirements For a full list of what you can hire click here. | 1x Microphone. 2x SumUp Card machines |  |  |
| Facilities Requirements | 60 x Chairs 5 x tables |  |  |
| Food Requirements For full guidance on this click here. | Food will be provided by Maryam Roble who has a Level 2 Food Safety and Hygiene Certificate, as well as allergen training. |  |  |
| Security & First Aid Requirements Who are the qualified first aiders in the group should a medical emergency occur? | Hanan Roble, Farida Mahmud, Fatima Ahmed. |  |  |
| Decorations that you are providing | Decorative Cultural Fabrics Streamers Balloons Homemade decorations |  |  |
| Provisional Budget If you would like a more extensive budget tracker, click here. | E.g.: Total Budget: £50 Ticket income: £80 (£2 x 40) Food Income: £30 Venue hire: £0 Decorations: £15 Tech: £0 Food: £35 £60 Profit - 100% of Profit will go towards MSF. |  |  |
| 1C) Only required if an external company/external speaker will be on site for the event |  |  |  |
| Business Name: | Business Contact Name: | Email Address: | Contact Number: |
| Arrival On Site: Departure time: | Company’s Risk Assessment Link: | Company’s Insurance Link: | Company’s Public Liability Information Link: |

- If you are inviting an external company or individual on to campus for your event, you are required to submit this form to legalservices@soton.ac.uk at least 15 working days before the event. For more guidance on this please click here.

Part 2A

Risk Assessment

| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |  |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Slips, trips and falls | Physical injury | Event organisers and attendees | 2 | 3 | 6 | All boxes and equipment to be stored away from main meeting area, e.g. stored under tables. Floors to be kept clear and dry, and visual checks to be maintained throughout the meeting by organisers. Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. Report any trip hazards to facilities teams/venue staff asap. If cannot be removed, mark off with hazard signs. | 1 | 4 | 4 | If the injury is serious and participant in a lot of pain or discomfort, seek medical attention immediately. Call 999 in an emergency. Any incidents need to be reported as soon as possible, ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. food |
| Manual handling, including setting up of equipment. E.g. table and chairs | Bruising or broken bones from tripping over table and chairs. | Meeting organisers and attendees | 2 | 3 | 6 | Follow manual handling guidelines. Ensure that at least 2 people carry tables or other bulky items. Setting up tables will be done by organisers. Work in teams when handling other large and bulky items. Request tools to support with the moving of heavy objects from SUSU Facilities/venue. E.g. hand truck, dolly, skates. Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable. | 1 | 3 | 3 | Seek assistance from facilities staff/venue staff if needed. Seek medical attention from SUSU/venue Reception if in need. Contact emergency services if needed. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Overcrowding / Inadequate Meeting Space | Physical injury, distress, exclusion | Event organisers and attendees | 2 | 3 | 6 | Do not push/shove. If large crowds form, request barriers from SUSU facilities team or external venue to assist with crowd management. Committee checks on space, lighting, access, tech available, etc. Use ticketing system (SUSU Box Office) for regular sessions/meetings to avoid exceeding venue capacity. Ensure space meets needs of members e.g. considering location & accessibility of space (use AcessAble database to check accessibility information of venues). If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. Committee to consult members on needs and make reasonable adjustments where possible Provide remote meeting options for members where possible. | 1 | 3 | 3 | Seek medical attention if problem arises. Liaise with SUSU reception/Activities Team and UoS Room Booking team on available spaces for meetings. Postpone meetings where space cannot be found. Welfare Officer to complete WIDE training. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Reputational Risk: For the club or society, as well as to SUSU and the University | Incidents causing reputational damage to the group, Southampton University Students’ Union or Southampton University itself. This could be controversial posts, conduct during a game, conduct during social, or anything else that brings the clubs/societies, SUSU or the University’s name into disrepute. | The club, SUSU or the University’s reputation | 2 | 1 | 2 | Ensuring all parts of this risk assessment are adhered to. Ensuring all members are reminded that they are representing the club/society, SUSU and the University, often in branded clothing. Members are reminded that they need to adhere to SUSU’s Code of Conduct. | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Report any incidents to the Activities Team. |
| Electronics | Risk of eye strain, injury, electric shock | Committee and attendees | 2 | 4 | 8 | Ensure regular breaks (ideally every 20mins) when using screens Ensure screen is set up to avoid glare, is at eye height where possible Ensure no liquids are placed near electrical equipment Ensure all leads are secured with cable ties/mats etc For external venues, pre-check equipment and last PAT testing dates. | 1 | 4 | 4 | Request support and advice from SUSU IT/Tech teams e.g. via activities team Seek medical attention as required Follow SUSU incident reporting guide |
| Accessibility: Entrances and Exits to the chosen area. | Participants may be prevented from attending the activity due to a lack of considerations of accessibility needs and requirements. They could also be prevented from leaving the area quickly in an emergency if the correct infrastructure and considerations have not been made. | Participants, committee | 1 | 5 | 5 | All areas chosen for activity will have their suitability checked. If a closed activity for members, members will be consulted to ensure there are no accessibility requirements. If an open activity, committee will consider all accessibility requirements and ensure that the area chosen is as accessible as possible. | 1 | 5 | 5 | In case of an emergency, call the emergency services on 999. If those with accessibility problems have not been able to exit, make the building manager and emergency services aware. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. Follow SUSU incident reporting guide |
| Legal Compliance: Club or society activity going against set law. This includes breaches of the freedom of speech act | Fines imposed upon the student group as well as SUSU. Jail sentences. Reputational risk to the student group, SUSU and the wider University | The club or society, committee and members, SUSU or the Wider University. | 1 | 1 | 1 | All clubs and societies should ensure they are following set law at all times. If ever in doubt, they will contact the Activities team prior to the activity taking place. All who wish to bring in an external speaker must follow due process, available here This will be looked over by the University Legal Services team, and may require security being consulted and an extra risk assessment being submitted. | 1 | 1 | 1 | Ensure that any incidents involving public or others are recorded and addressed. Follow SUSU incident reporting guide |
| Costumes/Fancy Dress | Props/costumes causing injury or offence | Participants Members of the public | 2 | 1 | 2 | Ask members to only bring small items and use sensibly. Members of the society are responsible for their own possessions and the use of them. Choose a theme unlikely to cause offence. Any participant wearing items deemed offensive asked to remove these. Society to follow and share with members Code of Conduct/SUSU Expect Respect policy. | 1 | 1 | 1 | SUSU Expect Respect policy to be followed. Committee WIDE training. Ensure that any incidents involving public or others are recorded and addressed. Report any incidents to the Activities Team. |
| Travel by foot | Disturbance to neighbourhood, participants getting lost, increased risk to personal safety, vehicle collision causing serious injury | Event organisers, event attendees, Members of the public | 4 | 3 | 12 | Members are responsible for their individual safety and are expected to act sensibly. Local venues known to UoS students chosen. Event organisers will be available to direct people between venues. Attendees will be encouraged to identify a ‘buddy’, this will make it easier for people to stay together. They will be encouraged (but not expected) to look out for one another and check in throughout the night where possible. Avoid large groups of people totally blocking the pavement or spilling in to the road. Anybody in the group who is very drunk or appears unwell and therefore not safe should be encouraged to go home ideally with someone else. If required a taxi will be called for them (ideally SUSU Safety Bus will be used, or Radio Taxis). Be considerate of other pedestrians and road users, keep disturbance and noise down. | 2 | fire | 4 | Where possible venue chosen for the event will be local/known to members and within a short travel distance for members. Contact emergency services as required 111/999. Incidents are to be reported as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Travel by car, train, bus, plane when leaving the local area. | Vehicle collision – causing anything from minor to severe injuries, as well as mental health issues. | Members, those driving, members of the public | 2 | 5 | 10 | Group committee to check that drivers have the relevant licences and insurance for the mode of travel. This includes if they have completed a SUSU minibus test. Members expected to drive or travel in a sensible manner, with those doing otherwise to face disciplinary action (from the club/society in the first instance). Can cause reputational issues, especially if driving SUSU branded vehicles. Importance of this to be reminded. | 1 | 5 | 5 | Contact emergency services as required 111/999. Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Medical emergency | Members may sustain injury /become unwell Pre-existing medical conditions, sickness, distress | Members | 1 | 5 | 5 | Advise participants to bring their personal medication if it might be required. Members/Committee to carry out first aid if necessary and only if qualified and confident to do so. Contact emergency services as required 111/999. Contact SUSU Reception/venue staff for first aid support. Members can be referred to The Student Hub (02380 599 599, studenthub@soton.ac.uk) in case of distress. | 1 | 4 | 4 | Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Fire | Smoke inhalation, burns. Risk of extreme harm. | All participants and organisers, any staff and spectators | 1 | 5 | 5 | Those leading the session must ensure they are aware of and fully understand the venue or location’s fire procedures. Those leading must make sure that all exit routes are clearly highlighted and report any issues immediately to the venue. Highlight to all the participants the nearest emergency exit routes at the start of a session, and the importance of leaving calmly in case of an emergency. Avoid build-up of debris in the activity area. Consider accessibility requirements. | 1 | 4 | 4 | In case of an emergency, please pull nearest fire alarm and ensure all participants leave the venue calmly and safely. Once in a safe position to do so, call the emergency services on 999. Any incidents need to be reported as soon as possible ensuring duty manager/health and safety officers have been informed. Follow SUSU incident report policy. |
| Anti-social, violent, or offensive behaviour | Disturbance to the neighbourhood, reputational damage, injury and distress as a result of violence | Event organisers, event attendees, public | 2 | 5 | 10 | Bouncers/security will be present at most licensed venues. Bar/venue security staff will need to be alerted and emergency services called as required. Do not personally engage with any violent behaviour. Stay safe and inform the bar staff/police if necessary. The consumption of alcohol will take place at licensed premises. The conditions on the license will be adhered to and alcohol will not be served to customers who have drunk to excess. Committee to select ‘student friendly’ bars/clubs and contact them in advance to inform them of the event. Society to follow and share with members Code of conduct/SUSU Expect Respect policy. | 1 | 3 | 5 | If the situation becomes very serious and results in the participant being arrested then it will be made clear that they cannot be accompanied to the police station. Follow SUSU incident report policy. Call emergency services as required. |
| Adverse weather | Hypo- or hyperthermia, illness, injury, slipping, burns | Event organisers, event attendees | 3 | 4 | 12 | Lead organiser to check the weather are suitable for activities on the day. Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites. In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, and to hydrate (especially if drinking alcohol). | 2 | 2 | 4 | If adverse weather is too extreme to be controlled, the event should ultimately be cancelled or postponed to a different date. Contact emergency services if needed. All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Financial risk | Group debt | Group members, SUSU | 4 | 3 | 12 | A cost/-balance sheet has been created for this event. How much profit is expected to be made? The expected profit for this event is £60-£100 The contingency plan for not enough tickets being sold is for the event to continue, but perhaps on a smaller scale. | 2 | 3 | 6 | Contact SUSU Activities Team if you have any questions or concerns about this – we would rather know sooner than later! |
| Charity Fundraising |  |  |  |  |  |  |  |  |  |  |
| Handling and Storing Money – | Theft, Individuals being mugged. | Members and Participants | 3 | 4 | 12 | As Fundraising for own Society/Club no Card Machine will be present. All fundraising to be completed via QR code to A GoFundMe or Similar Platform. | 2 | 3 | 6 | No Cash to be accepted at all. Clubs and Societies are not to use Personal Card machines to take payments. |
| Handling and storing card readers – | - Theft - Individuals being mugged/robbed - Loss/misplacement leading to financial loss | Members and Participants | 3 | 4 | 12 | Southampton RAG procedures will be followed: - Charity Event form completed, and RAG approval will be given - All food hygiene certificates and event risk assessment to be approved by activities team - Sum-up Card machine to be requested and collected from SUSU reception. - Should not be storing money all donations to be taken via Sumup Machine or Just Giving Pages | 2 | 3 | 6 | No Cash to Be Accepted at all. No card machines to be left unattended. No Volunteers to be left alone with the card machine In the event of theft committee members will: - Highlight the incident to any community police officers in the area/report to 111 - Report to SUSU Duty manager and Complete a SUSU incident report |
| Abuse of Members and Volunteers | Members of the public or students may act violently towards volunteers. Eg: Because they disagree with the cause. | Volunteers and Participants | 4 | 3 | 12 | No Volunteers are ever to be left alone. Always have at least 2 people at a stall or at an Event. | 2 | 3 | 6 | - Report to SUSU Duty manager and Complete a SUSU incident report - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Venue/Location considerations | Require certain licenses/sign off | Organisers, Participates, SUSU | 1 | 4 | 4 | Ensure the venue has the relevant licenses required for your event ahead of time. Ensure your event has the required sign off by the venue's security teams. Ensure proper booking process is followed for ALL bookings on and off campus. With no event going forward without Activities Approving the Risk Assessment. On campus - Ivvy Booking/uni room booking - Risk assessment - Contract Off campus - Risk assessment Any bookings/contracts with external providers. | 1 | 2 | 2 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Lone working | Stolen goods, injury to individual misuse of card reader. | Volunteers | 3 | 3 | 9 | Ensure no one is left alone as a volunteer at a fundraising event especially if using a Sum-up Card reader. Event led to brief volunteers to operate the card readers in pairs and briefed on how to handle situations surrounding these. | 3 | 1 | 3 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. |
| Bake Sale/Evening Party Fundraiser | Aside from food risks, dance risks, and other evening party/fundraiser risk within this risk assessment, possible risks include mentioning of distressing information when referencing the charities involved | Guests | 4 | 2 | 8 | We could give participants warning that there will be distressing information presented in advance before presentations, giving students the opportunity to leave | 2 | 2 | 4 | Students can seek the Student Hub, Wellbeing Team on campus: Tel: (0)23 8059 9599 |
| Food |  |  |  |  |  |  |  |  |  |  |
| Serving and preparation of food | - Allergies - Food poisoning - Choking | All | 3 | 5 | 15 | - Homemade items to be avoided by those with allergies - precautions should be made by those with appropriate food hygiene training (Level 2 +) - Only order/buy food at establishments with appropriate food hygiene rating - Food to only be provided/eaten when other activities are stopped Follow good food hygiene practices- no handling food when ill, tie back hair, wash hands and equipment regularly using warm water and cleaning products, refrigerate necessary products | 1 | 5 | 5 | SUSU food hygiene level 2 course available for completion- requests made to activities team Call for first aid/emergency services a required Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Contamination of food through food preparation. | Illness, Food poisoning, Allergy. | ALL | 2 | 3 | 6 | - Ensure all food is prepared in advance and done in a clean and hygienic environment. In line with the level 2 food hygiene training. - Ensure all ingredients used when making items are withing there used by or best before dates. - Ensure all frozen food is thoroughly defrosted before use. Endeavour to not cross contaminate foo such as nuts and let customers know if cross contamination is a possibility. | 1 | 3 | 3 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Storage and Display of Food | Illness, Food poisoning, Allergy. | All | 2 | 3 | 6 | Keep any products containing fresh produce in the fridge. Do not leave any food out for longer than 4 hours. - Store all products in a clean sealable container away from raw foods. Transport cakes in a clean sealable container. | 1 | 3 | 3 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Food Allergies and Dietary requirements | Illness, Allergic reaction | Customers | 3 | 5 | 15 | - Where possible remove common allergens form ingredients. allergen-chart-1.docx (live.com) Lists all 14 of the core allergens. - Ensure each cake is labelled with its name and list of ingredients. - Have a list available of all ingredients for any products sold at the stall. - Always use recipes from reputable sources. Make sure to keep any packaging. | 1 | 5 | 5 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. - For more information on allergens: Providing food at community and charity events ¦ Food Standards Agency Follow SUSU incident report policy |
| Hot Plates | Injuries/burns from the heat | All attendees | 2 | 5 | 10 | - Only the stall holders/volunteers to use the hotplate. - Customers to be kept at a minimum of 4ft from the hot plate. - Fire safety equipment on hand. Protective clothing e.g. oven gloves to be used. |  |  |  | - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. Follow SUSU incident report policy |
| Electrical Issues | Serious/ Fatal injuries because of electric shock | Volunteers and customers | 2 | 4 | 8 | - Electrical equipment to be kept away from water or any water-based work station - Customers to be kept at a minimum of 4ft away from any electrical faults - Fire safety equipment on hand | 1 | 5 | 5 | - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. Follow SUSU incident report policy |
| Gas hobs and ovens | Serious or Fatal injuries as a result of explosion/release of gas or hot oven. | Customers and Volunteers | 2 | 5 | 10 | - Always use protective equipment such as oven gloves when cooking. - Only use Gas hobs and ovens at your events that have been provided by SUSU or in volunteers homes. Make sure anyone using the appliances are confident to do so. | 1 | 5 | 5 | - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. Follow SUSU incident report policy |
| Stock/Food Falling | Physical Injury, Illness, Food poisoning | All Participants | 3 | 2 | 6 | - Enusre all stock is stored correctly and not stacked to high. - If any products fall that these are not sold and disposed of in food waste. | 1 | 2 | 2 | - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. - SUSU food hygiene level 2 course available for completion- requests made to activities team Follow SUSU incident report policy |
| Food Temperature | Food poisoning, illness, perished stock | All participants | 2 | 3 | 6 | - Keep any products containing fresh produce in the fridge. - Do not leave any food out for longer than 4 hours. - Ensure all products or produce are stored as describe on packaging. Ensure all items are cooked to correct temperatures from reputable recipes or packaging. | 1 | 3 | 3 | - SUSU food hygiene level 2 course available for completion- requests made to activities team - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure Follow SUSU incident report policy |
| Use of Knives for Cutting Food | Cuts and injuries | Volunteers and stall operators | 2 | 2 | 4 | - Make stall operators aware of the potential risks. - Where possible use wooden cutlery. - Knife not to be left unattended and stored away safely when not in use. - Ensure the Knife is suitable for the task and the food you are cutting. When carrying the Knife ensure the blade is pointing down. |  |  |  | - Call for first aid/emergency services a required - Report incidents via SUSU incident report procedure. Follow SUSU incident report policy |
| Use of boiling water | Physical injury, i.e. burns Condensation in urn that can lead to mould build up | Event organisers Attendees | 3 | 2 | 6 | Committee ensure sensible use of boiling water supplies and thorough cleaning of receptacles after using the urn to avoid bacteria forming - Ensure people are careful when carrying vessels with hot water in. | 2 | 2 | 4 | - Seek medical attention from SUSU Reception/venue staff if in need. - Contact facilities team via SUSU reception/venue staff. - Contact emergency services if needed. - All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy. |
| Talks/debates - subjects that could be sensitive or personal to some members | The audience feels negative emotions around the topic or becomes distressed by images or events shown/discussed. | Members | 2 | 3 | 6 | Prior information about event and what to expect given out so participants know what to expect. If inviting external speakers, follow UoS Code of Practice to Secure Freedom of Speech within the Law. Do not confirm speaker’s attendance before final confirmation from UoS Legal Services & SUSU Activities Team is given. More info on the process for inviting external speakers can be found here. Be aware this process can take time, so be sure to give plenty of notice. Members made aware they could leave the event at any time. Members referred to The Student Hub (02380 599 599, studenthub@soton.ac.uk), and/ore signpost to support organisations (e.g. via presentation slide, or by speakers/committee members). SUSU reporting tool available. | 1 | 3 | 3 | Organisers will, following the event, share relevant information on support/signpost- Facebook/email/newsletter. Committee WIDE training. - Seek guidance from Activities/SUSU Advice Centre/UoS Student Hub as required. |
| Counter protest, discrimination against the demonstration/Campaign | Distress due to threatening/ aggressive behaviour, injury due to assault/violence | Event organisers and attendees | 2 | 4 | 8 | Event planned for Highfield campus - a route well signposted and known for students. Leaders to advise all participants to not engage/respond to any counter protests or aggressive behaviour. If safe to do so, encourage group to move on and remove themselves from situation. The event will be ended and students advised to return to campus if this continues. Prior information about event and what to expect given out so participants know what to expect, e.g. via Facebook/social media posts. Participants made aware they could join and leave the event at any time. Ensure that people are aware that this is an open space for discussion to discourage protest. | 1 | 4 | 4 | Event organisers to call University Security if necessary. Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 (Ext: 3311) Building 32, University Road Highfield Campus. Any incidents will be reported via UoS reporting tools Contact emergency services if needed Organisers will, following the event, share relevant information on support/signpost via social media channels etc. Follow SUSU incident reporting guide |

| PART 2B – Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Assessment Action Plan |  |  |  |  |  |  |  |
| Part no. | Action to be taken, incl. Cost | By whom | Target date |  | Review date | Outcome at review date |  |
| 1 | Risk assessment shared with all organisers and checked through before the event Follow SUSU Food Provision Guidance for events involving home-cooked/prepared food or external catering. | Relevant committee members – president to ensure complete. | 20/11/2025 |  | 01/12/2025 |  |  |
| 2 | Committee to read and share SUSU Expect Respect Policy | Relevant committee members – president to ensure complete. | 20/11/2025 |  | 01/12/2025 |  |  |
| 3 | Complete a financial assessment of the event | Vice President Hanan Roble | 20/11/2025 |  | 01/12/2025 |  |  |
| 4 | Liaise with external companies (e.g. venue, DJ, caterers) for all necessary paperwork. | Events Secretary Maryam Roble | 20/11/2025 |  | 01/12/2025 |  |  |
| 5 | Reviewing venue layout and identifying hazard | Events Secretary Maryam Roble | 20/11/2025 |  | 01/12/2025 |  |  |
|  | Ensuring all volunteers and staff are aware of safety procedures | Welfare Officers Amir Saalah | 20/11/2025 |  | 01/12/2025 |  |  |
|  | Communicating rules and expectations clearly to attendees | Vice President Hanan Roble | 20/11/2025 |  | 01/12/2025 |  |  |
|  | Documenting any specific precautions taken for the event | Events Secretary Maryam Roble | 20/11/2025 |  | 01/12/2025 |  |  |
|  | Compile and display clearly all listed ingredients and allergies in line with Natasha's law | Events Secretary Maryam Roble |  |  |  |  |  |
| Responsible committee member signature 1: |  |  |  |  | Responsible committee member signature 2: |  |  |
| Print name: Vice President Hanan Roble |  |  |  | Date: 17/11/2025 | Print name: Events Secretary Maryam Roble |  | Date: 17/11/2025 |

Assessment Guidance

| - Eliminate |  |  |  |  | Remove the hazard wherever possible which negates the need for further controls |  |  |  | If this is not possible then explain why |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Substitute |  |  |  |  | Replace the hazard with one less hazardous |  |  |  | If not possible then explain why |  |
| - Physical controls |  |  |  |  | Examples: enclosure, fume cupboard, glove box |  |  |  | Likely to still require admin controls as well |  |
| - Admin controls |  |  |  |  | Examples: training, supervision, signage |  |  |  |  |  |
| - Personal protection |  |  |  |  | Examples: respirators, safety specs, gloves |  |  |  | Last resort as it only protects the individual |  |
| LIKELIHOOD | 5 | 5 | 10 | 15 |  | 20 | 25 |
|  | 4 | 4 | 8 | 12 |  | 16 | 20 |
|  | 3 | 3 | 6 | 9 |  | 12 | 15 |
|  | 2 | 2 | 4 | 6 |  | 8 | 10 |
|  | 1 | 1 | 2 | 3 |  | 4 | 5 |
|  |  | 1 | 2 | 3 |  | 4 | 5 |
|  |  | IMPACT |  |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |