| Risk Assessment |  |  |  |  |
| --- | --- | --- | --- | --- |
| Risk Assessment for the activity of | Southampton Surgical Society |  | Date | 25/04/2026 |
| Group Name | Southampton Surgical Society | Assessor | Name of committee member completing the RA |  |
| Supervisor | President: Ethan Alford Vice President: Nasif Bhuiyan | Signed off | N/A, please upload to groupshub for digital sign-off by SUSU Activities team |  |
| Description of event/activity | Risk Assessment for the Southern Surgical Conference (SSC). Heartbeat Education Centre, Southampton General Hospital from 09:10 to 17:00 The Southern Surgical Conference will explore the theme of global surgery. Participants will rotate through four workshops: trauma and orthopaedic surgery, cardiothoracic surgery, oral and maxillofacial surgery, and plastic surgery. Workshops will be led by consultants, registrars, and surgical trainees. The event will conclude with announcements, closing remarks, and post-attendance feedback forms to issue certificates. |  |  |  |

This Document Contains both Part 1: Event Plan & Part 2: Risk Assessment. Both parts are required to be completed by the organising group. You will also need to complete a charity form linked here.

| Part 1 |  |  |  |
| --- | --- | --- | --- |
| Event Plan |  |  |  |
| 1A) Contact Information: |  |  |  |
| Main Contact For The Event: | Email Address for Main Contact: | Club or Society: | Contact Number: |
| 1B) Event Information: |  |  |  |
| Event Name: Southern Surgical Conference | Event Date: 25/04/26 | Event Venue/Venues: Southampton General Hospital, Heartbeat Centre | Total Attendees: 80-100 |
| Event Timings: | Set Up: 7.30AM Event Start: 8.30AM Event End: 5PM Pack Down: 5.30PM |  |  |
| Event Break down: (This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity.) | 08:30 – 09:00 Registration (open until 09:30) 09:00 – 09:10 Welcome and housekeeping 09:10 – 09:35 Talk 1 (restricted to 20-minutes with a 5-minute buffer time) 09:35 – 10:00 Talk 2 (restricted to 20-minutes with a 5-minute buffer time) 10:00 – 10:25 Talk 3 (restricted to 20-minutes with a 5-minute buffer time) 10:25 – 10:50 Talk 4 (restricted to 20-minutes with a 5-minute buffer time) 10:50 – 11:20 Coffee break, sponsor stands and networking opportunities 11:20 – 11:45 Talk 5 (ONLINE) (restricted to 20-minutes with a 5-minute buffer time) 11:45 – 12:25 Oral presentation competition 12:25 – 12:35 Sponsorship announcements 12:35 – 13:30 Lunch, sponsor stands and networking opportunities 13:30 – 14:20 Workshop 1 (40-minute workshops with 10-minute transitions): • Trauma and Orthopaedic Surgery: External fixation • Cardiothoracic Surgery: Da Vinci Machine, VATs and Wet-Lab • Plastic Surgery: Skin graft • Oral and Maxillofacial Surgery: Plating 14:20 – 15:10 Workshop 2 (40-minute workshops with 10-minute transitions): • Trauma and Orthopaedic Surgery: External fixation • Cardiothoracic Surgery: Da Vinci Machine, VATs and Wet-Lab • Plastic Surgery: Skin graft • Oral and Maxillofacial Surgery: Plating 15:10 – 15:20 Afternoon break, sponsor stands and networking opportunities Southern Surgical Conference 15:20 – 16:10 Workshop 3 (40-minute workshops with 10-minute transitions): • Trauma and Orthopaedic Surgery: External fixation • Cardiothoracic Surgery: Da Vinci Machine, VATs and Wet-Lab • Plastic Surgery: Skin graft • Oral and Maxillofacial Surgery: Plating 16:10 – 16:50 Workshop 4 (40-minute workshops with 10-minute transitions): • Trauma and Orthopaedic Surgery: External fixation • Cardiothoracic Surgery: Da Vinci Machine, VATs and Wet-Lab • Plastic Surgery: Skin graft • Oral and Maxillofacial Surgery: Plating 16:50 – 16:55 Break and lecture theatre transition 16:55 – 17:00 Closing remarks, oral presentation awards and feedback forms |  |  |
| Is this a Ticketed Event? If so please state the Name of the ticket on Boxoffice: You can set up Box-office tickets through your group's hub page for guidance on this click here: | Yes – Southern Surgical Conference Yet to promote, box office page will be made after promotion begins. | How Much Are your Tickets? And how many are available? | Eg: £10 for whole conference x75 £5 for talks and lunch only x10 |
| Overview of Event Concept: (Description of the activities taking place. This includes everything happening at your event eg: fundraising, food provision and any performance or sporting activity) | The Southern Surgical Conference will explore the theme of global surgery.Participants will rotate through four workshops: trauma and orthopaedic surgery, cardiothoracic surgery, oral and maxillofacial surgery, and plastic surgery. Workshops will be led by consultants, registrars, and surgical trainees. The event will conclude with announcements, closing remarks, and post-attendance feedback forms to issue certificates. |  |  |
| Staff Hosting the event (List all committee & Volunteers that will be present and responsible for the event, as well as their role) | Nasif Bhuiyan (Lead) Ethan Alford Shreyaa Ramadore Anisa Qazvini Connor Morton Dhairya Shah Janine Xu Al Razzak Rojbin Yijit |  |  |
| Food arrangements (For full guidance on this click here) | Food Provided by Surgical Society Shreyaa Ramadore has done the food safety training. |  |  |
| Security & First Aid arrangements (Who are the qualified first aiders in the group should a medical emergency occur?) | All Hosts have completed first aid training as part of medicine degree. |  |  |
| Provisional Budget: (if you would like a more extensive budget tracker click here.) | Digital Services £13.00 1 £13.00 Prizes £50.00 1 £50.00 Total £63.00 Consumables Item Estimated Cost Quantity Total Lanyards £1.73 100 £173.00 Passes £1.20 100 £120.00 Sutures £10.99 16 £165.84 Suture Pads £6.77 20 £135.40 Skin £0.75 80 £60.00 Saw Bones £17.00 20 £340.00 Dry-Lab £25.00 1 £25.00 Total £1,019.24 Catering Item Estimated Cost Quantity Sandwiches Costco £25.00 4 £100.00 Pastries £14.00 5 £70.00 Coffee £13.99 1 £13.99 Paper Cups £5.00 2 £10.00 Paper Plates £5.00 2 £10.00 Tissue £5.00 2 £10.00 Bin Bags £2.00 1 £2.00 Total £365.99 Other Item Estimated Cost Quantity Total Cards £6.75 2 £13.50 Chocolates £17.99 3 £53.97 CPD Award £100.00 1 £100.00 Printing £50.00 N/A £50.00 Total £217.47 Total Expenditure £1,665.70 |  |  |
| 1C) Only Required If External Company/External Speaker On Site For Event |  |  |  |
| Business Name: | Business Contact Name: | Email Address: | Contact Number: |
| Arrival On Site: Departure time: | Companies Risk Assessment link: | Companies Insurance Link: | Companies Public Liability Information Link: |

If you are inviting a external company or individual on to campus for your event you will be required to submit this form to legalservices@soton.ac.uk at least 15 working days before the event. For more guidance on this please click here.

| PART A |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Risk identification |  |  | (2) Risk assessment |  |  |  | (3) Risk management |  |  |  |
| Hazard | Potential Consequences | Who might be harmed (user; those nearby; those in the vicinity; members of the public) | Inherent |  |  |  | Residual |  |  | Further controls (use the risk hierarchy) |
|  |  |  | Likelihood | Impact | Score | Control measures (use the risk hierarchy) | Likelihood | Impact | Score |  |
| Slips, trips and falls | Physical injury | Event organisers and attendees | 2 | 4 | 8 | - All boxes and equipment to be stored away from main meeting area, e.g. stored under tables - Any cables to be organised as best as possible - Cable ties/to be used if necessary - Floors to be kept clear and dry, and visual checks to be maintained throughout the meeting by organizers. - Extra vigilance will be paid to make sure that any spilled food products/objects are cleaned up quickly and efficiently in the area. Report any trip hazards to facilities teams/venue staff asap. If cannot be removed mark off with hazard signs | 1 | 4 | 4 | - Seek medical attention from SUSU Reception/venue staff if in need - Contact facilities team via SUSU reception/venue staff - Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Setting up of Equipment. E.g. Table and chairs | Bruising or broken bones from tripping over table and chairs. | Meeting organisers and attendees | 2 | 3 | 6 | - Make stall operators aware of the potential risks, follow manual handling guidelines - Ensure that at least 2 people carry tables. - Setting up tables will be done by organisers. - Work in teams when handling other large and bulky items. - Request tools to support with move of heavy objects- SUSU Facilities/venue. E.g. hand truck, dolly, skates Make sure anyone with any pre-existing conditions isn’t doing any unnecessary lifting and they are comfortable | 1 | 3 | 3 | - Seek assistance if in need of extra help from facilities staff/venue staff if needed - Seek medical attention from SUSU Reception if in need - Contact emergency services if needed All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Inadequate meeting space- overcrowding, not inclusive to all members | Physical injury, distress, exclusion | Event organisers and attendees | 1 | 3 | 3 | - Committee check on room pre-booking, checks on space, lighting, access, tech available - Ensure space meets needs of members e.g. considering location & accessibility of space - Committee to consult members on needs and make reasonable adjustments where possible | 1 | 3 | 3 | - Seek medical attention if problem arises - Liaise with SUSU reception/activities team on available spaces for meetings - Postpone meetings where space cannot be found - Look at remote meeting options for members - Committee WIDE training All incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Activities involving electrical equipment e.g. laptops/ computers | Risk of eye strain, injury, electric shock | Event organisers and attendees | 2 | 4 | 8 | - Ensure regular breaks (ideally every 20mins) when using screens - Ensure screen is set up to avoid glare, is at eye height where possible - Ensure no liquids are placed near electrical equipment Ensure all leads are secured with cable ties/mats etc | 1 | 4 | 4 | - Request support and advice from SUSU IT/Tech teams e.g. via activities team - For external venues pre-check equipment and last PAT testing dates Seek medical attention as required |
| Socials-Travel | Vehicles collision -causing serious injury | Event organisers, event attendees, Members of the public | 4 | 3 | 12 | - Members are responsible for their individual safety though and are expected to act sensibly - local venues known to UoS students chosen - Event organisers will be available to direct people between venues. - Attendees will be encouraged to identify a ‘buddy’, this will make it easier for people to stay together. They will be encouraged (but not expected) to look out for one another and check in throughout the night where possible. - Avoid large groups of people totally blocking the pavement or spilling in to the road. - Anybody in the group who is very drunk or appears unwell and therefore not safe should be encouraged to go home ideally with someone else. If required a taxi will be called for them (ideally SUSU safety bus will be used, or radio taxis). Be considerate of other pedestrians & road users, keep disturbance & noise down. | 2 | fire | 4 | - Where possible venues chosen for socials will be local/known to members and within a short distance from each other. - Contact emergency services as required 111/999 - Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Socials/Meetings- Medical emergency | Members may sustain injury /become unwell pre-existing medical conditions Sickness Distress | Members | 3 | 5 | 15 | - Advise participants; to bring their personal medication - Members/Committee to carry out first aid if necessary and only if qualified and confident to do so - Contact emergency services as required 111/999 Contact SUSU Reception/Venue staff for first aid support |  | 5 | 15 | - Incidents are to be reported on the as soon as possible ensuring the duty manager/health and safety officer have been informed. Follow SUSU incident report policy |
| Insufficient Fire Safety awareness | If a fire alarm is triggered, people may not know where to go- Crushing, falls, burns and smoke inhalation arising from induced panic, reduced space in buildings and external walkways, obstructed fire exits, build-up of flammable materials i.e. waste cardboard/boxes. | Members | 2 | 10 | 5 | - ensure that members know where the nearest fire exist are and the meeting place is outside, should it be needed Build-up of rubbish is to be kept to a minimum. Excess build up is to be removed promptly and deposited in the designated areas. | 1 | 5 | 5 | - All incidents are to be reported as soon as possible ensuring the duty manager/health and safety officer have been informed. - Call emergency services and University Security (on campus) or venue staff (external venue) - Emergency contact number for Campus Security: - Tel: +44 (0)23 8059 3311 - (Ext:3311) Follow SUSU incident report policy |
| Suturing activities involving needles, sharps, and any other surgical instruments, including surgical instruments, e.g. bone saws or drills for fracture fixation. | Surgical instruments causing injury | Participants of workshops, including, (fracture) fixation workshops, suturing workshops, and any other surgical skill workshops. | 2 | 2 | 4 | - Ensure members are informed and advised on how to use surgical instruments safely - Provide appropriate PPE for the activities including gloves, aprons, etc - Provide sharps bins for disposal of single-use sharps and needles - Provide adequate supervision by trained and experienced staff and facilitators during workshop sessions, including trained surgeons or deliverers of equipment involved in the activities of this nature - Maintain an inventory of surgical instruments before, during, and after sessions Provide and maintain safe storage for surgical equipment | 1 | 2 | 2 | Follow SUSU incident report policy Seek medical attention as required Call emergency services as required 111/999 |
| Events involving Food | - Allergies - Food poisoning Choking | All | 3 | 5 | 15 | - Individual event risk assessment to be carried out for events involving members making/serving food. - Homemade items to be avoided by those with allergies and should be made by those with appropriate food hygiene training (Level 2 +) - Only order/buy food at establishments with appropriate food hygiene rating - Food to only be provided/eaten when other activities are stopped Follow good food hygiene practices- no handling food when ill, tie back hair, wash hands and equipment regularly using warm water and cleaning products, refrigerate necessary products | 1 | 5 | 5 | SUSU food hygiene level 2 course available for completion- requests made to activities team Call for first aid/emergency services a required Report incidents via SUSU incident report procedure |
| Adverse Weather | - Injury - Illness - Slipping Burns | All who attend | 4 | 3 | 12 | - Lead organiser to check the weather are suitable for activities on the day - SUSU/UoS Facilities team checks of buildings and spaces prior to the event - Warn those attending to prepare by wearing appropriate clothing and footwear e.g. via social media posts, email invites - In the case of hot weather organisers to advice participants to bring/wear appropriate level sunscreen, hydrate In the case of amber or red weather warning, committee to cancel or postpone event | 4 | 1 | 4 | Consider ending the activity early if the weather turns or gets worse. Call for first aid/emergency services a required Report to SUSU Duty manager and Complete a SUSU incident report |
| Overcrowding | - Physical injury | Event organisers and attendees | 1 | 3 | 3 | - Do not push/shove - If large crowds form, barriers can be requested by SUSU facilities team (if available on the day) to assist with crowd management. - Book during quieter times when less activities taking place on Redbrick/book all available space - Inform other bookings on the Redbrick/in the area of the event | 1 | 3 | 3 | Seek medical attention if problem arises With support from a SUSU Activities coordinator Inform UoS security team of the event (– on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk) and liaise with them on need for security teams on the day Security team may inform police of the event if required (e.g. marches) |
| Disturbance to public, students and staff | - Conflict, noise, crowds | Event organisers and attendees, general public | 2 | 2 | 4 | - Events planned for redbrick avoiding residential areas - UoS Security Teams informed of the event - Everybody will be encouraged to stay together as a group - shouting, chants, whistles etc. will be kept to a minimum around busy university buildings and residential areas - If applicable book space during quieter times when less activities taking place in local lecture theatres (lunch, Wednesday afternoons) | 1 | 2 | 2 | - With support from a SUSU Activities coordinator Inform UoS security team of the event -University Security 24 hours – on campus 3311, off campus 02380 593311. unisecurity@soton.ac.uk Inform UoS/SUSU communications team of the event- can brief others via SUSSSED |
| Counter protest, discrimination against the demonstration/Campaign | - Assault, Violence or threatening/ Aggressive Behaviour | Event organisers and attendees | 2 | 4 | 8 | - Event planned for Highfield campus- a route well signposted and known for students - Leaders to advise all participants to not engage/respond to any protests, aggressive behaviour- if safe to do so will encourage group to move on and remove themselves from situation- The event will be ended and students advised to return to campus if this continues - Prior information about event and what to expect given out so participants know what to expect via Facebook/social media posts - Participants made aware they could join and leave the event at any time. - Ensure that people are aware that this is an open space for discussion to discourage protest. | 1 | 4 | 4 | - Event organisers to call University Security if necessary. - Emergency contact number for Campus Security: Tel: +44 (0)23 8059 3311 - (Ext: 3311) - Building 32, University Road Highfield Campus. - Any incidents will be reported via UoS reporting tools - Contact emergency services if needed - Organisers will, following the event, share relevant information on support/signpost via social media channels etc. |
| Talks/debates - subjects that could be sensitive or personal to some members. External delegates, including external speakers and attendees. | - The audience feels negative emotions around the topic or becomes distressed by images or events shown/discussed. | Members | 2 | 3 | 6 | - Prior information about event and what to expect given out so participants know what to expect. - Members made aware they could leave the event at any time. - Members referred to enabling/signpost to support organisations (e.g. via presentation slide, or by speakers/committee members) - SUSU reporting tool available - Any external speakers will verified with the SUSU legal team prior to the event. | 1 | 3 | 3 | - Organisers will, following the event, share relevant information on support/signpost- Facebook/email/newsletter - Committee Wide Training - Seek guidance from activities/SUSU advice centre/UoS enabling team as required - committee WIDE training |
| Overcrowding at Stall | Reduced space in walkways and entrances. - Risk of Students panicking because of tight spaces / confinement. Crushing against fixed structures from pushing and shoving. Aggressive behaviour. | Members, visitors | 2 | 3 | 6 | - A maximum of 3 representatives to be at the stall at any one time - Request that orderly ques are formed - Ensure all items are stored under tables and monitor area in front of stall to ensure this is clear - Ensure that organisers /volunteers do not block walkways when engaging with attendees - Follow instructions given by support staff/staff on directions and entry and exit points - Do not move tables if this has been placed for you by staff. | 1 | 3 | 3 | - Seek medical attention if problem arises - Seek support from facilities staff |
| Falling Objects e.g. banners | Injury Bruising Damage to equipment | Members, visitors | 2 | 3 | 6 | - Tables to be safely secured by staff where possible – ask for support from facilities team - Ensure banner is secured and on a flat surface - Ensure banners or objects are not obscuring walkways or exits-ideally place behind or to the side of stall where space allows- ensuring distance between stalls/stall holders | 1 | 2 | 2 | - Seek medical attention if problem arises - Seek support from facilities staff |

| # PART B – Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # Risk Assessment Action Plan |  |  |  |  |  |  |  |
| # Part no. | # Action to be taken, incl. Cost | # By whom | # Target date |  | # Review date | # Outcome at review date |  |
| # 1 | Individual risk assessments for individual events with higher risk levels and anything not covered by generic assessment. This includes: - Trips and Tours - Fundraising events e.g. Bake Sales - External Speaker Events - Events involving home-cooked/prepared food or external catering # Other large or medium- to high-risk events e.g. balls, club nights, pub crawls, sporting activities. | # Relevant committee members – president to ensure complete. This includes the president, vice president and any members involved in the hosting or organisation of the event. | # All events |  | # Immediately after events and overall review in July 2026 |  |  |
| # 2 | # Committee to read and share SUSU Expect Respect Policy | # Relevant committee members – president to ensure complete. This includes the president, vice president and any members involved in the hosting or organisation of the event. | # Immediately |  | # By the end of September 2025, i.e. immediately. | # Completed |  |
| # 3 | # Ensuring safe disposal or removal of sharps and any other surgical equipment that may pose a risk should inadequate storage or disposal occur. | # Relevant committee members – president to ensure complete. This includes the president, vice president and any members involved in the hosting or organisation of the event. | # Immediately after an event |  | # After any workshop sessions or events involving equipment. |  |  |
| # 4 | # Fire and Safety mandatory training (completed by all medical students as part of VLE training). | # All committee | # Immediately |  | # Immediately | # Everyone has successfully completed their VLE Fire and Safety Mandatory Training and has been awarded a certificate from the hospital trust. |  |
| # 5 | # Undertake VLE Mandatory Training including Fire Safety, Prevent Strategy, Safeguarding Adults, Health and Safety Awareness, Infection Prevention, Equality, Diversity and Inclusion, Data Security and Child Protection. | # All committee | # Immediately |  | # Immediately | # All committee have successfully completed their VLE Mandatory Training and have obtained certificates from University Hospital Southampton. |  |
| # Responsible manager’s signature: |  |  |  |  | # Responsible manager’s signature: |  |  |
| # Print name: NASIF BHUIYAN |  |  |  | # Date: 23/03/26 | # Print name: SHREYAA RAMADORE |  | # Date: # 23/03/26 |

Assessment Guidance

| - Eliminate | Remove the hazard wherever possible which negates the need for further controls | If this is not possible then explain why |  |
| --- | --- | --- | --- |
| - Substitute | Replace the hazard with one less hazardous | If not possible then explain why |  |
| - Physical controls | Examples: enclosure, fume cupboard, glove box | Likely to still require admin controls as well |  |
| - Admin controls | Examples: training, supervision, signage |  |  |
| - Personal protection | Examples: respirators, safety specs, gloves | Last resort as it only protects the individual |  |

| LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 | 4 | 8 | 12 | 16 | 20 |
|  | 3 | 3 | 6 | 9 | 12 | 15 |
|  | 2 | 2 | 4 | 6 | 8 | 10 |
|  | 1 | 1 | 2 | 3 | 4 | 5 |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  |  | IMPACT |  |  |  |  |

| Impact |  | Health & Safety |
| --- | --- | --- |
| 1 | Trivial - insignificant | Very minor injuries e.g. slight bruising |
| 2 | Minor | Injuries or illness e.g. small cut or abrasion which require basic first aid treatment even in self-administered. |
| 3 | Moderate | Injuries or illness e.g. strain or sprain requiring first aid or medical support. |
| 4 | Major | Injuries or illness e.g. broken bone requiring medical support >24 hours and time off work >4 weeks. |
| 5 | Severe – extremely significant | Fatality or multiple serious injuries or illness requiring hospital admission or significant time off work. |

Risk process

- Identify the impact and likelihood using the tables above.

- Identify the risk rating by multiplying the Impact by the likelihood using the coloured matrix.

- If the risk is amber or red – identify control measures to reduce the risk to as low as is reasonably practicable.

- If the residual risk is green, additional controls are not necessary.

- If the residual risk is amber the activity can continue but you must identify and implement further controls to reduce the risk to as low as reasonably practicable.

- If the residual risk is red do not continue with the activity until additional controls have been implemented and the risk is reduced.

- Control measures should follow the risk hierarchy, where appropriate as per the pyramid above.

- The cost of implementing control measures can be taken into account but should be proportional to the risk i.e. a control to reduce low risk may not need to be carried out if the cost is high but a control to manage high risk means that even at high cost the control would be necessary.

| Likelihood |  |
| --- | --- |
| 1 | Rare e.g. 1 in 100,000 chance or higher |
| 2 | Unlikely e.g. 1 in 10,000 chance or higher |
| 3 | Possible e.g. 1 in 1,000 chance or higher |
| 4 | Likely e.g. 1 in 100 chance or higher |
| 5 | Very Likely e.g. 1 in 10 chance or higher |